PROJECT NUMBER: [INSERT PROJECT NUMBER]

PROJECT NAME: [INSERT PROJECT NAME]

MAJOR WORKS SUBCONTRACT

(MWSC-ACT-2014)

(FOR USE WITH MCC-ACT-2013)

[LAST AMENDED: 5 August 2014  - PLEASE REMOVE this note and complete all prompts PRIOR TO EXECUTION.  TEMPLATE NOT TO BE USED WHERE THERE IS SIGNIFICANT COMMONWEALTH GOVERNMENT FUNDING FOR THE PROJECT]

Table of Contents

1.	GLOSSARY OF TERMS, INTERPRETATION AND MISCELLANEOUS	2

1.1	Glossary of Terms	2

1.2	Interpretation	16

1.3	Miscellaneous	17

2.	COMMENCEMENT	19

2.1	Nature of Subcontract	19

2.2	Subcontractor's Obligations	19

2.3	Contractor's Obligations	19

2.4	Delayed Access	20

3.	PERSONNEL	21

3.1	Contractor's Representative	21

3.2	Replacement of Contractor's Representative	21

3.3	Parties' Conduct	21

3.4	Contractor's Representative's Representative	21

3.5	Subcontractor's Representative	21

3.6	Key People	21

3.7	Removal of Persons	22

3.8	Industrial Relations	22

3.9	Project Review	26

4.	SECURITY	28

4.1	Form	28

4.2	Release	28

4.3	Interest	28

4.4	Related Company Guarantee	28

5.	RISKS AND INSURANCE	30

5.1	Construction Risks Insurance	30

5.2	Other Risks	30

5.3	Not used	30

5.4	Contractor Insurance Obligations	30

5.5	Subcontractor Insurance Obligations	30

5.6	Failure to Insure	32

5.7	Period of Insurance	32

5.8	Notice of Potential Claim	32

5.9	Procedure upon Loss or Damage	33

5.10	Cross Liability	33

6.	DESIGN AND DOCUMENTATION	34

6.1	Contractor's Documents	34

6.2	Subcontractor's Design	34

6.3	Contractor's Representative may Review Design Documentation	34

6.4	No Obligation to Review	34

6.5	Copies of Design Documentation	35

6.6	Fitness for Purpose	35

6.7	Availability	35

6.8	Licence over Project Documents	35

6.9	Intellectual Property Warranties	36

6.10	Intellectual Property Rights	36

6.11	Resolution of Ambiguities	36

6.12	Access to Premises and Project Documents	36

6.13	Design Certification	37

6.14	Samples	38

7.	SITE	39

7.1	Subcontractor to Inform Itself	39

7.2	Site Information	39

7.3	Notice of Latent Conditions	39

7.4	Subcontractor's Entitlement	39

7.5	Site Access	40

7.6	Subcontractor's Obligation to Provide Access	40

7.7	Non-Reliance	40

8.	CONSTRUCTION	41

8.1	Description of Subcontract Works	41

8.2	All Work Included	41

8.3	Statutory Requirements	41

8.4	Change in Statutory Requirements or Variance with Subcontract	41

8.5	Subcontracting	42

8.6	Subsubcontractor Warranties	43

8.7	Provisional Sum Work	43

8.8	Design for Provisional Sum Work to be Prepared by Contractor - Option 1	43

8.8	Design for Provisional Sum Work to be Prepared by Subcontractor - Option 2	44

8.9	Tendering Provisional Sum Work	44

8.10	Price Adjustment for Tendered Provisional Sum Work	44

8.11	Price Adjustment for Other Provisional Sum Work	44

8.12	Further Allowance for Provisional Sum Work	45

8.13	Co-operation with Other Contractors	45

8.14	Setting Out	45

8.15	Survey	45

8.16	Safety	45

8.17	Work Health and Safety Management	46

8.18	Plant, Equipment and Work	48

8.19	Cleaning Up	48

8.20	The Environment	48

8.21	Urgent Protection	49

8.22	Valuable Objects Found on Site	49

8.23	The Contractor May Act	49

8.24	Access Hours	49

8.25	Imported Items	49

8.26	Salvaged Materials	50

8.27	Project Signboards	50

8.28	Measurements and Dimensions	51

8.29	Territory's Actions	51

9.	QUALITY	52

9.1	Construction	52

9.2	Project Plans	52

9.3	Contractor's Representative's Right to Inspect	53

9.4	Testing	54

9.5	Costs of Testing	54

9.6	Defects	54

9.7	Correction of Defect or Variation	54

9.8	Claim for Correction of Defect	54

9.9	Claim for Variation	55

9.10	Acceptance of Work	55

9.11	Extension of Defects Liability Period	55

9.12	Common Law Rights not Affected	56

9.13	Commissioning and Handover	56

9.14	Maintenance during Defects Liability Period	56

9.15	Defects Liability Period Review and Report	57

10.	TIME	58

10.1	Progress and Time for Completion	58

10.2	Programming	58

10.3	Subcontractor Not Relieved	58

10.4	Acceleration by Subcontractor	58

10.5	Delays Entitling Claim	59

10.6	Claim	59

10.7	Conditions Precedent to Extension	59

10.8	Extension of Time	60

10.9	Reduction in Extension of Time	60

10.10	Unilateral Extensions	60

10.11	Agreed Damages	60

10.12	Suspension	61

10.13	Instruction to Accelerate	61

10.14	Partial Acceleration	61

10.15	Acceleration	62

10.16	Contractor's Rights to Liquidated Damages Not Affected	62

11.	VARIATIONS	63

11.1	Variation Price Request	63

11.2	Variation Order	63

11.3	Cost of Variation	63

11.4	Omissions	64

11.5	Daywork	64

11.6	Valuation of Daywork	64

11.7	Variations Requested by Subcontractor	65

11.8	Contractor's Representative's Determination	65

11.9	Variation Approved by Contractor's Representative	65

11.10	Managing Contractor Contract Variation	66

12.	PAYMENT	67

12.1	Payment Obligation	67

12.2	Payment Claims	67

12.3	Conditions Precedent	67

12.4	Payment Statements	68

12.5	Payment	69

12.6	Payment on Account	69

12.7	Unfixed Goods and Materials	69

12.8	Release of Additional Approved Security	70

12.9	Completion Payment Claim and Notice	70

12.10	Release after Completion Payment Claim and Notice	71

12.11	Final Payment Claim and Notice	71

12.12	Release after Final Payment Claim and Notice	71

12.13	Interest	71

12.14	Correction of Payment Statements	72

12.15	Right of Set-Off	72

12.16	Payment of Workers and Subcontractors	72

12.17	GST	73

12.18	Quantities in Schedule of Rates	73

12.19	Limits of Accuracy	73

12.20	Security of Payment Legislation	74

12.21	Accounting Records	75

12.22	Cost Allocation Advice	75

12.23	Facilities and Infrastructure Accounting	75

12.24	Not used	75

13.	Completion	76

13.1	Subcontractor to Notify	76

13.2	Contractor's Representative to Inspect	76

13.3	Unilateral Issue of Completion Notice	76

13.4	Take Over Upon Completion	76

13.5	Part of the Subcontract Works or a Stage	76

13.6	Effect of Notice of Completion	77

13.7	Liquidated Damages	77

13.8	Liability to the Territory	77

13.9	Incentive	78

14.	TERMINATION	79

14.1	Preservation of Rights	79

14.2	Subcontractor Default	79

14.3	Contents of Notice of Default	79

14.4	Termination for Insolvency or Breach	79

14.5	Contractor's Entitlements after Termination	80

14.6	Subcontractor's Entitlements after Termination	80

14.7	Termination for Convenience	80

14.8	Costs	80

14.9	Termination of Managing Contractor Contract	81

14.10	Consequences Following Managing Contractor Contract Termination	81

15.	DISPUTES	83

15.1	Notice of Dispute	83

15.2	Expert Determination	83

15.3	The Expert	83

15.4	Not Arbitration	83

15.5	Procedure for Determination	84

15.6	Disclosure of Interest	84

15.7	Costs	84

15.8	Conclusion of Expert Determination	84

15.9	Agreement with Expert	84

15.10	Determination of Expert	84

15.11	Executive Negotiation	85

15.12	Arbitration Agreement	85

15.13	Arbitration	85

15.14	Proportional Liability	86

15.15	MCC Dispute Procedures	87

15.16	Managing Contractor Contract Disputes	87

15.17	Procedure for Managing Contractor Contract Disputes	87

15.18	Further Procedures	88

15.19	Continuation of Subcontractor's Activities	88

16.	NOTICES	89

16.1	Notice of Variation	89

16.2	Notices of Other Claims	89

16.3	Prescribed Notices	89

16.4	Continuing Events	90

16.5	Time Bar	90

16.6	Other Provisions Unaffected	90

16.7	Address for Service	90

16.8	Receipt of Notices	90

17.	WOL	92

17.1	Design and Construction	92

17.2	Consultation	92

17.3	WOL Proposals	92

17.4	Reporting	92

17.5	Post Occupancy Evaluation	92

17.6	Rights and Obligations Not Affected	93

18.	GENERAL	94

18.1	Workplace Gender Equality	94

18.2	Not used	94

18.3	Not used	94

18.4	IT Equipment	94

18.5	Protection of Personal Information	94

18.6	Moral Rights	96

18.7	Freedom of Information	97

18.8	Long Service Leave	98

18.9	Assignment	98

18.10	Publicity	98

18.11	Not used	98

18.12	Building Code of Australia Certification	98

19.	Not used	99

20.	COMMERCIAL-IN-CONFIDENCE INFORMATION	100

20.1	General	100

20.2	Commercial-in-Confidence Information	100

21.	Not used	101

22.	National code of practice for the construction industry	101

22.1	General	101

22.2	Responsibility not Affected	101

22.3	Notice of Effect on Compliance with National Code	101

22.4	Records	101

22.5	Access and Documents	101

FORMAL AGREEMENT

This Subcontract is made on                   day of

Parties	The contractor set out in the Subcontract Particulars (Contractor)

The subcontractor set out in the Subcontract Particulars (Subcontractor)

A.	The Australian Capital Territory (Territory) and the Contractor entered the Managing Contractor Contract (as described in the Subcontract Particulars) for the design and construction of the MCC Works (as described in the Subcontract Particulars).

B.	The Contractor wishes to subcontract certain obligations under the Managing Contractor Contract to the Subcontractor under this Subcontract.

C.	The Contractor and the Subcontractor therefore promise to carry out and complete their respective obligations in accordance with:

the attached Conditions of Subcontract; and

the other documents referred to in clause 1.1 of the Conditions of Subcontract as constituting the Subcontract.

SIGNED as an agreement.

| Executed by the Contractor by or in the presence of: |  |  |  |
| --- | --- | --- | --- |
| Signature of Director |  |  | Signature of Secretary/other Director |
| Name of Director in full |  |  | Name of Secretary/other Director in full |

| Executed by the Subcontractor by or in the presence of: |  |  |  |
| --- | --- | --- | --- |
| Signature of Director |  |  | Signature of Secretary/other Director |
| Name of Director in full |  |  | Name of Secretary/other Director in full |

CONDITIONS OF SUBCONTRACT

- GLOSSARY OF TERMS, INTERPRETATION AND MISCELLANEOUS

Glossary of Terms

Unless the context otherwise indicates, whenever used in this Subcontract, each word or phrase in the headings in this clause 1.1 has the meaning given to it under the relevant heading.

Accredited Building Surveyor

A person who is a building surveyor accredited by the Australian Institute of Building Surveyors.

Act of Prevention

Any one of:

a breach of the Subcontract by the Contractor;

any other act or omission of the Territory, the MCC Contract Administrator, the Contractor, the Contractor's Representative or an Other Contractor engaged by the Contractor; or

a Variation the subject of a direction by the Contractor's Representative, except where the Variation is instructed in the circumstances described in clause 9.9(b).

Approval

Any licence, permit, consent, approval, determination, certificate, notice or other requirement of any Commonwealth, State, Territory or local authority, body or other organisation having any jurisdiction in connection with the Site, the Subcontract Works or the Subcontractor's Activities or under any other applicable Statutory Requirement, which must be obtained or satisfied to:

carry out the Subcontractor's Activities; or

service, occupy and use the completed Subcontract Works or a completed Stage.

Approved Security

An unconditional undertaking (duly stamped) in the form set out in the Schedule of Collateral Documents and otherwise on terms, and given by a financial institution, approved by the Contractor.

Award Date

The date on which the Formal Agreement, to which these Conditions of Subcontract are attached, has been completed and signed by the Contractor and the Subcontractor.

Building Code of Australia

The Building Code of Australia that applies in the State or Territory where the Works are located, as amended from time to time, produced and maintained by the Australian Building Codes Board on behalf of the Commonwealth Government and each State and Territory Government.

Change of Control

In relation to the Subcontractor, where a person who did not (directly or indirectly) effectively Control the Subcontractor at the Award Date, either alone or together with others, acquires Control of the Subcontractor.

Claim

Includes any claim for an increase in the Subcontract Price, for payment of money (including damages) or for an extension of time:

under, arising out of, or in any way in connection with, the Subcontract, including any direction of the Contractor's Representative;

arising out of, or in any way in connection with, the Subcontractor's Activities, the Subcontract Works or either party's conduct before the Subcontract; or

otherwise at law or in equity including:

by statute;

in tort for negligence or otherwise, including negligent misrepresentation; or

for restitution.

Collateral Warranty

A warranty in the form set out in the Schedule of Collateral Documents.

Commissioning and Handover Plan

The commissioning and handover plan prepared by the Subcontractor and approved by the Contractor's Representative, which must set out in adequate detail the procedures the Subcontractor will implement to manage the Subcontractor 's Activities from a commissioning and handover perspective to ensure:

the timely, efficient and comprehensive commissioning of the Subcontract Works (including the inspection and testing process);

the smooth handover of the Subcontract Works to the Territory; and

that all required planned and unplanned maintenance is provided during the Defects Liability Period,

in accordance with the Subcontract, the Contractor's Commissioning and Handover Plan and the Commissioning, Handover and Takeover Guidelines.

Commissioning, Handover and Takeover Guidelines

The guidelines set out in the Schedule of Collateral Documents (if any).

Commonwealth

Commonwealth of Australia.

Completion

The point in time when, in respect of the Subcontract Works or a Stage:

the Subcontract Works are, or the Stage is, complete except for minor Defects:

which do not prevent the Subcontract Works or the Stage from being reasonably capable of being used for the intended purpose of the Subcontract Works or the Stage; and

which can be corrected without prejudicing the convenient use of the Subcontract Works or the Stage;

those tests which are required by the Subcontract to be carried out and passed before the Subcontract Works or the Stage reach Completion have been carried out and passed;

all documents and other information referred to in the Subcontract, including all Approvals, which are required for the use, operation and maintenance of the Subcontract Works or the Stage have been supplied to the Contractor's Representative; and

without limiting paragraph (c), the Subcontractor has done everything which the Subcontract requires it to do as a condition precedent to Completion, including those things described in Annexure 1 and in the Subcontract Particulars.

Construction Risks Insurance

A policy of insurance for material damage to the Works and liabilities to third parties arising from the Works with coverage as set out in the terms of the policy.

Consultant Deed of Covenant

A consultant deed of covenant in the form set out in the Schedule of Collateral Documents.

Consultant Design Certificate

The certificate set out in the Schedule of Collateral Documents.

Contamination

The presence in, on or under land, air or water of a substance (whether a solid, liquid, gas, odour, heat, sound, vibration or radiation) at a concentration above the concentration at which the substance is normally present in, on or under land, air or water in the same locality, that presents a risk of Environmental Harm, including harm to human health or any other aspect of the Environment, or could otherwise give rise to a risk of non-compliance with any Statutory Requirement for the protection of the Environment.

Contractor

The person named in the Subcontract Particulars.

Contractor Risks

Any one of:

war, invasion, act of foreign enemies, hostilities (whether war is declared or not), civil war, rebellion, revolution, insurrection or military or usurped powers, martial law or confiscation by order of any government or public authority;

the use or threat of unlawful violence against persons or property which does not arise out of any individual relationship between the perpetrator and the victim, or for purposes of robbery, but which is directed at victims as members of a class, race, organisation, nationality, religious or ethnic group, or which is intended to intimidate, coerce or inflict revenge upon any civilian population, government, institution or corporation; and

ionising radiations or contamination by radioactivity from any nuclear fuel or from any nuclear waste from the combustion of nuclear fuel not caused by the Subcontractor or any subsubcontractor or any of their employees or agents.

Contractor's Commissioning and Handover Plan

The commissioning and handover plan described in the Subcontract Particulars, amended as approved under the Managing Contractor Contract.

Contractor's Environmental Management Plan

The environmental management plan described in the Subcontract Particulars, as amended from time to time in accordance with the Managing Contractor Contract.

Contractor's Program

The program prepared by the Contractor for the MCC Works as amended from time to time.

Contractor's Representative

The person named in the Subcontract Particulars or any other person nominated by the Contractor from time to time under clause 3.2 to replace that person.

Contractor's Site Management Plan

The site management plan described in the Subcontract Particulars, amended as approved under the Managing Contractor Contract.

Contractor's Work Health and Safety Plan

The work health and safety plan described in the Subcontract Particulars, amended and reviewed in accordance with the Managing Contractor Contract.

Control

Includes:

the ability to exercise or control the exercise of the right to vote in respect of more than 50% of the voting shares or other form of voting equity in a corporation;

the ability to dispose or exercise control over the disposal of more than 50% of the shares or other form of equity in a corporation;

the ability to appoint or remove all or a majority of the directors of a corporation;

the ability to exercise or control the exercise of the casting of a majority of the votes cast at the meetings of the board of directors of a corporation; and

any other means, direct or indirect, of dominating the decision making and financial and operating policies of a corporation.

Date for Completion

In respect of:

the Subcontract Works or a Stage, subject to paragraph (b), the date, or period of time, specified in the Subcontract Particulars; or

any new Stage directed under clause 13.5(c), the date, or period of time, specified in the direction,

as adjusted under the Subcontract.

Date of Completion

The date of Completion set out in a Notice of Completion.

Defect

Any defect, shrinkage, fault or omission in the Subcontract Works including any aspect of the Subcontract Works which is not in accordance with the requirements of this Subcontract.

Defects Liability Period

The period which commences on the Date of Completion of the Subcontract Works or a Stage, and which continues for the period described in the Subcontract Particulars, as extended by clause 9.11.

Design Documentation

All design documentation (including drawings, specifications, reports, models, samples and calculations) in computer readable and written forms necessary for the Subcontractor to complete any part of the Subcontract Works which is not fully designed and documented in the Subcontract Works Description.

direction

Any agreement, approval, authorisation, certificate, consent, decision, demand, determination, direction, explanation, failure to consent, instruction, notice, notification, order, permission, rejection, request or requirement.

Environment

Includes:

ecosystems and their constituent parts, including people and communities;

natural and physical resources;

the qualities and characteristics of locations, places and areas; and

the social, economic, aesthetic and cultural aspects of a thing mentioned in paragraphs (a), (b) or (c).

Environmental Clearance Certificate

The Environmental Clearance Certificate issued by the Territory relating to the MCC Works or the Subcontractor's Activities and any conditions incorporated in that certificate.

Environmental Harm

Any actual or threatened adverse impact on, or damage to, the Environment.

Environmental Incident

Any Environmental Harm or Contamination caused by or in relation to the Subcontractor's Activities.

Environmental Management Plan

The environmental management plan prepared by the Subcontractor and approved by the Contractor's Representative which must set out in adequate detail the procedures the Subcontractor will implement to manage the Subcontractor's Activities from an environmental perspective and describe how the Subcontractor proposes to ensure the Subcontractor's Activities will be performed consistently so as to maximise the achievement of:

the Environmental Requirements;

the Statutory Requirements;

the ESD Principles; and

the Environmental Objectives,

in accordance with the Subcontract and the Contractor's Environmental Management Plan.

Environmental Objectives

The Environmental Objectives are to:

encourage best practice environmental management through planning, commitment and continuous improvement;

prevent and minimise adverse impacts on the Environment;

identify the potential for, and respond to, Environmental Incidents, accidents and emergency situations and take corrective action;

identify and control possible environmental hazards associated with the Subcontract Works and the Subcontractor's Activities;

establish procedures to ensure that no hazardous substance is stored on Territory land without approval;

recognise and protect any special environmental characteristics of the Site (including cultural heritage significance);

define roles and responsibilities for personnel;

ensure environmental training and awareness programmes are provided to employees and subsubcontractors;

ensure subsubcontractors implement the Environmental Management Plan;

define how the management of the Environment during the Subcontractor's Activities is reported and performance evaluated;

describe all monitoring procedures required to identify impacts on the Environment as a result of the Subcontract Works and the Subcontractor's Activities;

implement complaint reporting procedures and maintain records of complaints and response to complaints; and

establish and maintain programs and procedures for periodic Environmental Management Plan audits to be carried out.

Environmental Requirements

Includes:

the Environmental Clearance Certificate;

the Territory Environmental Requirements; and

any other matter or requirement specified in the Subcontract Particulars.

ESD

Ecologically sustainable development.

ESD Principles

Means:

efficient and effective use of natural resources in a way that maintains the ecological processes on which life depends;

increased energy conservation and efficiency;

sustainable use of renewable energy resources;

reduction or elimination of toxic and harmful substances in facilities and their surrounding environments;

improvements to interior and exterior environments leading to increased productivity and better health;

efficiency in resource and materials utilisation, especially water resources;

selection of materials and products based on their life-cycle environmental impacts;

increased use of materials and products with recycled content;

recycling of construction waste and building materials after demolition;

reduction in harmful waste products produced during construction;

facility maintenance and operational practices that reduce or minimise harmful effects on people and the natural environment;

maintaining the cultural, economic, physical and social wellbeing of people and communities; and

the additional specific matters (if any) relating to ESD specified in the Subcontract Particulars.

Executive Negotiators

The representatives of the parties nominated in the Subcontract Particulars or any person nominated by the relevant party to replace that person from time to time by notice in writing to the other party.

Incentive Date

In respect of the Subcontract Works or a Stage, the date (if any) specified in the Subcontract Particulars.

Insolvency Event

Any one of the following:

the Subcontractor becomes, is declared to be, is taken under any applicable law (including the Corporations Act 2001 (Cth)) to be, admits to or informs the Contractor in writing or its creditors generally that the Subcontractor is insolvent, an insolvent under administration, bankrupt, unable to pay its debts or is unable to proceed with the Subcontract for financial reasons;

execution is levied against the Subcontractor by a creditor;

a garnishee order, mareva injunction or similar order, attachment, distress or other process is made, levied or issued against or in relation to any asset of the Subcontractor;

where the Subcontractor is an individual person or a partnership including an individual person, the Subcontractor:

commits an act of bankruptcy;

has a bankruptcy petition presented against him or her or presents his or her own petition;

is made bankrupt; or

applies for, agrees to, enters into, calls a meeting for the consideration of, executes or is the subject of an order or declaration in respect of:

a moratorium of any debts; or

a personal insolvency agreement or any other assignment, composition or arrangement (formal or informal) with creditors,

by which his or her assets are subjected conditionally or unconditionally to the control of a creditor or trustee;

where the Subcontractor is a corporation, any one of the following:

notice is given of a meeting of creditors with a view to the corporation entering into a deed of company arrangement;

a liquidator or provisional liquidator is appointed in respect of a corporation;

the corporation entering a deed of company arrangement with creditors;

a controller (as defined in section 9 of the Corporations Act 2001 (Cth)), administrator, receiver, receiver and manager, provisional liquidator or liquidator is appointed to the corporation;

an application is made to a court for the winding up of the corporation and not stayed within 14 days;

any application (not withdrawn or dismissed within 7 days) is made to a court for an order, an order is made, a meeting is convened or a resolution is passed, for the purpose of proposing or implementing a scheme of arrangement other than with the prior approval of the Territory under a solvent scheme of arrangement pursuant to Part 5.1 of the Corporations Act 2001 (Cth);

a winding up order or deregistration order is made in respect of the corporation;

the corporation resolves by special resolution that it be wound up voluntarily (other than for a members' voluntary winding-up);

as a result of the operation of section 459F(1) of the Corporations Act 2001 (Cth), the corporation is taken to have failed to comply with a statutory demand (as defined in the Corporations Act 2001 (Cth));or

a mortgagee of any property of the corporation takes possession of that property;

the Commissioner of Taxation issues a notice to any creditor of a person under the Taxation Administration Act 1953 (Cth) requiring that creditor to pay any money owing to that person to the Commissioner in respect of any tax or other amount required to be paid by that person to the Commissioner (whether or not due and payable) or the Commissioner advises that creditor that it intends to issue such a notice; or

anything analogous to anything referred to in paragraphs (a) to (f) or which has a substantially similar effect, occurs with respect to a person or corporation under any law of any jurisdiction.

Intellectual Property Rights

All statutory and other proprietary rights in respect of inventions, innovations, patents, utility models, designs, circuit layouts, mask rights, copyrights (including future copyrights), confidential information, trade secrets, know-how, trade marks and all other rights in respect of intellectual property as defined in Article 2 of the Convention establishing the World Intellectual Property Organisation of July 1967.

IRE Strategy

The Territory’s “Compliance with Industrial Relations and Employment Obligations Strategy for ACT Government Capital Works Projects” from time to time, or such substituted policy or strategy of the Territory.

IT Equipment

Any software, hardware or telecommunications equipment:

produced; or

provided, or required to be provided, to the Contractor or the Contractor's Representative,

under, for the purposes of or in connection with the Subcontract, the Subcontractor's Activities or the Subcontract Works by, for or on behalf of the Subcontractor.

Latent Conditions

Any ground conditions at the Site, excluding ground conditions resulting from inclement weather wherever occurring, which differ materially from those which should have been anticipated by a prudent, competent and experienced contractor if it had done those things which the Subcontractor is deemed to have done under clause 7.1.

Managing Contractor Contract

The managing contractor contract between the Contractor and the Territory described in the Subcontract Particulars.

MCC Contract Administrator

Means:

the person nominated in the Subcontract Particulars or any other person nominated by the Territory from time to time under the Managing Contractor Contract to administer the Managing Contractor Contract; and

any representative of that person appointed under the Managing Contractor Contract.

MCC Dispute Procedures

The dispute resolution procedures under the Managing Contractor Contract referred to in the first paragraph of clause 15.15.

MCC Works

The physical works, of which the Subcontract Works form part, which the Contractor must design (to the extent required by the Managing Contractor Contract), construct, commission, complete and hand over to the Territory in accordance with the Managing Contractor Contract, a brief description of which appears in the Subcontract Particulars.

Moral Rights

Has the meaning given by the Copyright Act 1968 (Cth).

Moral Rights Consent

A consent in the form set out in the Schedule of Collateral Documents.

Notice of Completion

A notice under clause 13.2(b)(i) by the Contractor's Representative stating that Completion of the Subcontract Works or a Stage has been achieved.

Other Contractor

Any contractor, consultant, artist, tradesperson or other person engaged to do work other than the Subcontractor and its subsubcontractors.

Plant, Equipment and Work

Those things used, or work undertaken, by the Subcontractor to construct the Subcontract Works or a Stage but which will not form part of the Subcontract Works or the Stage.

Professional Indemnity Insurance

A policy of insurance to cover claims made against the insured of civil liability for breach of professional duty (whether owed in contract or otherwise) by the Subcontractor or its subsubcontractors in carrying out the Subcontractor's Activities.

Project Documents

Includes:

Design Documentation prepared by the Subcontractor under clause 6.2;

programs;

Project Plans;

WOL Plan;

Approvals;

operation and maintenance manuals and warranties from subsubcontractors;

IT Equipment;

the documents which the Subcontractor is obliged to maintain under clause 12.21;

without limiting paragraphs (a) - (h), any other material:

produced; or

provided, or required to be provided, to the Contractor or the Contractor's Representative,

under, for the purposes of or in connection with the Subcontract, the Subcontractor's Activities or the Subcontract Works by, for or on behalf of the Subcontractor (including by subsubcontractors) including all documents, papers, books of account, labour time sheets, invoices (whether for services, materials, plant hire or otherwise), financial accounts, reports, software, databases or other information stored in any electronically-retrievable medium, technical information, plans, drawings (including as-built drawings), specifications, charts, calculations, tables, schedules, correspondence (including correspondence by third parties to the Subcontractor), internal memoranda, minutes of meetings, diary notes, audio material, visual material, audio-visual material, working papers, draft documents, any material relating to the Subcontractor's compliance with the WHS Legislation and any other material of a similar nature to those materials relating to or arising out of or in connection with the Subcontract, the Subcontractor's Activities or the Subcontract Works; and

without limiting paragraphs (a) - (i), all material at any time derived (under, for the purposes of or in connection with the Subcontract, the Subcontractor's Activities or the Subcontract Works) from, or based on, the material described in paragraphs (a) - (i).

Project Plans

The:

  - Environmental Management Plan;

  - Site Management Plan;

  - Commissioning and Handover Plan;

  - Work Health and Safety Plan; and

  - the additional plans referred to in the Subcontract Particulars.

Provisional Sum Work

The work or goods so described in the Subcontract Particulars for which the sum of money referred to in the Subcontract Particulars is included in the Subcontract Price.

Public Liability Insurance

A policy of liability insurance covering the Territory, the Contractor, the MCC Contract Administrator, the Contractor's Representative, the Subcontractor and all subsubcontractors for their respective liabilities:

to third parties; and

to each other,

for loss of or damage to property and death of or injury to any person, arising out of, or in any way in connection with, the Subcontractor's Activities.  This policy is not required to cover liabilities insured under Construction Risks Insurance, Workers Compensation Insurance, or Professional Indemnity Insurance.

Related Body Corporate

Has the meaning given to it in section 9 of the Corporations Act 2001 (Cth).

Schedule of Collateral Documents

The schedule of proforma documents applicable to the Territory’s Major Works Subcontract (MWSC-ACT-2014):

posted on the Territory’s website located at http://www.procurement.act.gov.au/tenders/standard_conditions_of_contract_and_tender (or any alternative location notified by the Territory), as amended from time to time by the Territory; and

which as at the Award Date include the documents referred to in the Subcontract Particulars.

Schedule of Rates

The schedule (if any) set out or referred to in the Subcontract Particulars, containing rates and prices to be used for the purpose of calculating the Subcontract Price.

Security of Payment Legislation

Means the Building and Construction Industry (Security of Payment) Act 2009 (ACT).

Site

The site for the Subcontract Works described in the Subcontract Particulars.

Site Management Plan

The site management plan prepared by the Subcontractor and approved by the Contractor's Representative which must set out in adequate detail all procedures the Subcontractor will implement to manage the Subcontractor's Activities on and near the Site including:

the matters specified in the Subcontract Particulars;

any other matters required by the Contractor's Representative,

in accordance with the Subcontract and the Contractor's Site Management Plan.

Special Conditions

The document referred to in the Subcontract Particulars.

Stage

A stage of the Subcontract Works:

described in the Subcontract Particulars; or

specified in a direction under clause 13.5(c).

Statutory Requirements

Means:

any law applicable to the carrying out of the Subcontractor's Activities, including Acts, ordinances, regulations, by-laws and other subordinate legislation;

Approvals (including any condition or requirement under them);

Territory Requirements; and

Environmental Requirements.

Subcontract

The contractual relationship between the parties constituted by:

the Formal Agreement;

the Special Conditions;

these Conditions of Subcontract;

the Subcontract Particulars;

the Subcontract Works Description; and

the other documents (if any) referred to in the Subcontract Particulars.

Subcontract Particulars

The particulars annexed to these Conditions of Subcontract and entitled "Subcontract Particulars".

Subcontract Price

The amount specified in the Subcontract Particulars as adjusted, subject to clause 16.5, under the Subcontract.

Subcontract Works

The physical works which the Subcontractor must design (to the extent required by the Subcontract), construct, commission, complete and hand over to the Contractor in accordance with the Subcontract, a brief description of which is set out in the Subcontract Particulars.

Subcontract Works Description

The documents referred to in the Subcontract Particulars.

Subcontractor

The person named in the Subcontract Particulars.

Subcontractor Deed of Covenant

A subcontractor deed of covenant in the form set out in the Schedule of Collateral Documents.

Subcontractor Design Certificate

The certificate set out in the Schedule of Collateral Documents.

Subcontractor's Activities

All things or tasks which the Subcontractor is, or may be, required to do to comply with its Subcontract obligations.

Subcontractor's Representative

The person named in the Subcontract Particulars or any other person from time to time appointed as Subcontractor's Representative in accordance with clause 3.6.

Subsubcontractor Deed of Covenant

A subsubcontractor deed of covenant in the form set out in the Schedule of Collateral Documents.

Subsubcontractor Design Certificate

The certificate set out in the Schedule of Collateral Documents.

Table of Variation Rates and Prices

The table (if any) so described in the Subcontract Particulars, containing rates and prices to be used for the purposes of valuing Variations under clause 11.3.

Territory

When used:

in a geographical sense, the Australian Capital Territory; and

in any other sense, the body politic established by section 7 of the Australian Capital Territory (Self Government) Act 1988 (Cth).

Territory Environmental Management System

The environmental management system applicable to the Site (if any) available from the Territory.

Territory Environmental Plan

The environmental plan applicable to the Site (if any) available from the Territory.

Territory Environmental Requirements

The Environmental Management System and Environmental Plan which relate to the Site, the Subcontract Works or the Subcontractor's Activities and includes any procedures, instructions and requirements which have been developed or issued under the Territory Environmental Management System (if any) or Territory Environmental Plan (if any) (as the case may be).

Territory Requirements

Includes all policies, plans, manuals, guidelines, instructions (including departmental procurement policy instructions) and other Territory requirements which are, or may become, applicable to the Site, the Subcontract Works or the Subcontractor's Activities.  To the extent that any of the requirements would require or suggest the insertion of provisions into this Subcontract, then:

those provisions will be incorporated by reference into this Subcontract; and

any ambiguity, discrepancy or inconsistency arising out of the incorporation by reference will be resolved by the MCC Contract Administrator.

Variation

Unless otherwise stated in the Subcontract, means any change to the Subcontract Works including any addition, increase, decrease, omission, deletion, demolition or removal to or from the Subcontract Works.

WHS Legislation

Means:

Work Health and Safety Act 2011 (ACT) and Work Health and Safety Regulation 2011 (ACT);

Work Health and Safety Regulation 2011 (ACT);

all instruments issued under the Work Health and Safety Act 2011 or the Work Health and Safety Regulation 2011;

all laws that replace the above laws; and

all other laws applicable in the Australian Capital Territory dealing with work health and safety matters.

WOL

Whole of life.

WOL Cost

The total of the direct/indirect, recurring/non-recurring, fixed/variable financial costs to the Territory arising out of, or in any way in connection with, the Subcontract Works over the whole life of the Subcontract Works including the costs of designing and constructing the Subcontract Works prior to Completion and operating and maintaining the Subcontract Works after Completion.

WOL Objectives

Means balancing:

WOL Cost;

the useful life of the Subcontract Works;

the reliability and availability for use of the Subcontract Works throughout their useful life;

the operability and maintainability of the Subcontract Works throughout their useful life;

the value for money achieved by the Territory from the design, construction, operation and maintenance of the Subcontract Works;

the achievement of the ESD Principles; and

the achievement of the specific additional matters (if any) relating to WOL specified in the Subcontract Particulars.

WOL Plan

The plan described in the Subcontract Particulars.

Work Health and Safety Plan

The work health and safety plan prepared by the Subcontractor and approved by the Contractor's Representative, which can be either Subcontract specific or site specific, and must:

set out in adequate detail the procedures the Subcontractor will implement to manage the Subcontractor's Activities from a work health and safety perspective;

describe how the Subcontractor proposes to ensure the Subcontractor's Activities are performed consistently with Statutory Requirements in relation to work health and safety;

address the matters specified in the Contract Particulars; and

be in accordance with the Subcontract and not be inconsistent with the Contractor's Work Health and Safety Plan.

Workers Compensation Insurance

A policy of insurance in the form prescribed by Statutory Requirements in each State and Territory in which the Subcontractor's Activities are to be performed or the Subcontractor's employees are employed or normally reside, to insure against liability for death of or injury to persons employed by the Subcontractor as required by the Statutory Requirements.

Interpretation

In this Subcontract, unless the context otherwise indicates:

words in the singular include the plural and vice versa;

references to a person include an individual, firm, corporation or unincorporated body;

except in clause 1.1, headings are for convenience only and do not affect the interpretation of this Subcontract;

references to any party to this Subcontract include its successors or permitted assigns;

a reference to a party, clause, Annexure, Schedule, or exhibit is a reference to a party, clause, Annexure, Schedule or exhibit of or to this Subcontract;

references to this Subcontract and any deed, agreement or instrument are deemed to include references to this Subcontract or such other deed, agreement or instrument as amended, novated, supplemented, varied or replaced from time to time;

words denoting any gender include all genders;

references to any legislation or to any section or provision of any legislation include any:

statutory modification or re-enactment of or any statutory provision substituted for that legislation, section or provision; and

ordinances, by-laws, regulations and other statutory instruments issued under that legislation, section or provision;

no rule of construction applies to the disadvantage of a party on the basis that the party put forward the Subcontract or any part;

a reference to "$" is to Australian currency;

where under the Subcontract:

a direction is required to be given or must be complied with; or

payment of money must be made (other than under clause 12.5),

within a period of 7 days or less from a specified event, then Saturdays, Sundays and public holidays in the place in which the Site is situated will not be counted in computing the number of days;

for the purposes of clauses 10.8, 10.9, 10.10 and 10.11:

any extension of time stated in days; or

any reference to "day",

will exclude public holidays and include only those days which are stated in the Subcontractor's approved program under clause 10.2 as working days;

for the purposes of clauses 12.4  and 12.5, references to "business days" are to days other than:

a Saturday or Sunday or the 27th, 28th, 29th, 30th or 31st day of December; or

a public or bank holiday in the Australian Capital Territory under the Holidays Act 1958 (ACT);

other than as set out in paragraphs (k), (l) and (m) references to "day" are references to calendar days;

the words "including" and "includes", and any variants of those words, will be read as if followed by the words "without limitation";

the word "subsubcontractor" will include subsubcontractors, suppliers and consultants and the word "subsubcontract" will include a contract with a subsubcontractor;

where a clause contains two options, the option specified in the Subcontract Particulars will apply;

derivatives of a word or expression which has been defined in clause 1.1 will have a corresponding meaning to that assigned to it in clause 1.1; and

unless agreed or notified in writing by the Contractor's Representative, a reference to Standards Australia standards, overseas standards or other similar reference documents in the Subcontract Works Description is a reference to the edition last published prior to the preparation of the Design Documentation.  If requested by the Contractor's Representative, the Subcontractor must make copies of all Standards Australia standards, overseas standards or other similar reference documents referred to in the Subcontract Works Description and Design Documentation available to the Contractor's Representative.

Miscellaneous

This Subcontract is subject to and is to be construed in accordance with the laws of the State or Territory set out in the Subcontract Particulars.

None of the terms of the Subcontract can be waived, discharged or released at law or in equity unless:

to the extent that the term involves a right of the party seeking to waive the term or one party seeking to waive an obligation of the other party - this is done by written notice to the other party; or

otherwise, both parties agree in writing.

This Subcontract constitutes the entire agreement and understanding between the parties and will take effect according to its tenor despite:

any prior agreement in conflict or at variance with the Subcontract; or

any correspondence or other documents relating to the subject matter of the Subcontract which may have passed between the parties prior to the Award Date and which are not included in the Subcontract.

Where a party comprises two or more persons, each person will be jointly and severally bound by the party's obligations under the Subcontract.

Any provision in this Subcontract which is illegal, void or unenforceable will be ineffective to the extent only of such illegality, voidness or unenforceability and such illegality, voidness or unenforceability will not invalidate any other provision of the Subcontract.

This Subcontract, the Project Documents and Territory Material are confidential.  The Subcontractor must:

not disclose any of the Subcontract, Territory Material or the Project Documents without the prior written consent of the Contractor except to the extent that the disclosure is required for the Subcontractor to carry out its obligations under the Subcontract; and

ensure that any subsubcontract made in connection with this Subcontract contains enforceable obligations requiring the subsubcontractor to comply with the Subcontractor's obligations arising under this clause 1.3(f) as if the subsubcontractor were the Subcontractor.

In this clause “Territory Material” means all material provided by the Territory to the Contractor, and which has been provided by the Contractor to the Subcontractor including documents, equipment, machinery and data (stored by any means).

The Subcontractor must indemnify the Contractor against:

any liability to or claim by a third party including a subsubcontractor or Other Contractor; and

all costs, losses and damages suffered or incurred by the Contractor,

arising out of or in connection with any breach by the Subcontractor of a term of this Subcontract.

All obligations to indemnify under this Subcontract survive termination of the Subcontract.

COMMENCEMENT

Nature of Subcontract

The Subcontractor must carry out the Subcontractor's Activities in accordance with the Subcontract.

The Subcontractor acknowledges that:

it has been engaged by the Contractor under this Subcontract for the vicarious performance of part of the Contractor's obligations under the Managing Contractor Contract;

the Contractor will be:

responsible to the Territory for the performance of the Subcontractor's Activities; and

vicariously liable to the Territory for all acts, omissions and defaults of the Subcontractor (and those of the employees and agents of the Subcontractor) relating to or in any way connected with the Subcontractor's Activities; and

it must perform all of the Subcontractor's Activities so as to ensure that they comply with the requirements of, and the Contractor discharges its obligations under, the Managing Contractor Contract.

Subcontractor's Obligations

The Subcontractor must:

immediately following the Award Date, commence to carry out the Subcontractor's Activities;

subject to clause 2.3(a), commence construction of the Subcontract Works on Site by no later than the date specified in the Subcontract Particulars;

unless otherwise expressly stated, carry out the Subcontractor's Activities at its cost; and

if requested by the Contractor's Representative, must execute a Subcontractor Deed of Covenant (duly completed with all relevant particulars) within the period specified by the Contractor's Representative in such a request and deliver the executed Subcontractor Deed of Covenant to the Contractor's Representative.

Contractor's Obligations

The Contractor must:

give the Subcontractor sufficient access to the Site to allow it to commence work on the Site on the later of:

satisfaction of the following conditions precedent to access:

the Subcontractor having provided to the Contractor's Representative:

the Approved Security required under clause 4.1; and

evidence satisfactory to the Contractor's Representative under clause 5.5(c) that the Subcontractor has effected the insurances required in accordance with clause 5.5;

the Site Management Plan and the Work Health and Safety Plan having been finalised under clause 9.2; and

any other conditions set out in the Subcontract Particulars; and

the date specified in the Subcontract Particulars; and

subject to other provisions of the Subcontract affecting access, continue to allow the Subcontractor sufficient access to the Site to enable it to carry out the Subcontractor's Activities.

Delayed Access

Failure by the Contractor to give access as required by clause 2.3(a) will not be a breach of the Subcontract but will entitle the Subcontractor to:

an extension of time to any relevant Date for Completion where it is otherwise so entitled under clause 10.7; and

have the Subcontract Price increased by any extra costs reasonably incurred by it which arise directly out of the Contractor's delay in giving the Subcontractor access to the Site, as determined by the Contractor's Representative.

The Subcontractor's entitlement under paragraph (b) will be its only right to payment of money arising from the Contractor's failure to give access as required by clause 2.3(a) and will be subject to the Subcontractor complying with clause 16.

PERSONNEL

Contractor's Representative

The Contractor's Representative will give directions and carry out all of the other functions of the Contractor's Representative under the Subcontract as the agent of the Contractor (and not as an independent certifier, assessor or valuer).

The Subcontractor must:

comply with any direction by the Contractor's Representative given or purported to be given under a provision of the Subcontract; and

not comply with any direction of the Contractor other than as expressly stated in the Subcontract.

Except where the Subcontract otherwise provides, the Contractor's Representative may give a direction orally but will as soon as practicable confirm it in writing.

Replacement of Contractor's Representative

The Contractor may at any time replace the Contractor's Representative, in which event the Contractor will appoint another person as the Contractor's Representative and notify the Subcontractor of that appointment.

Any substitute Contractor's Representative appointed under this clause 3.2 will be bound by anything done by the former Contractor's Representative to the same extent as the former Contractor's Representative would have been bound.

Parties' Conduct

Without limiting any of the rights or obligations of the Contractor and Subcontractor under the Subcontract, the Contractor and Subcontractor must co-operate with each other in carrying out their obligations under the Subcontract.

Contractor's Representative's Representative

The Contractor's Representative may:

by written notice to the Subcontractor appoint persons to exercise any of the Contractor's Representative's functions under the Subcontract;

not appoint more than one person to exercise a specific function under the Subcontract; and

revoke any appointment under paragraph (a) by notice in writing to the Subcontractor.

As at the Award Date, the Contractor's Representative is deemed to have appointed the persons set out in the Subcontract Particulars to carry out the functions set out in the Subcontract Particulars.

All references in the Subcontract to Contractor's Representative include a reference to a representative appointed under this clause 3.4.

Subcontractor's Representative

The Subcontractor must ensure that the Subcontractor's Representative is present on the Site at all times reasonably necessary to ensure that the Subcontractor is complying with its obligations under the Subcontract.

A direction is deemed to be given to the Subcontractor if it is given to the Subcontractor's Representative.

Key People

The Subcontractor must:

employ those people specified in the Subcontract Particulars, including the Subcontractor's Representative, in the jobs specified in the Subcontract Particulars;

subject to paragraph (c), not replace the people referred to in paragraph (a) without the Contractor's Representative's prior written approval; and

if any of the people referred to in paragraph (a) die, become seriously ill or resign from the employment of the Subcontractor, replace them with persons approved by the Contractor's Representative of at least equivalent experience, ability and expertise.

Removal of Persons

The Contractor's Representative may by notice in writing instruct the Subcontractor to remove any person from the Site or the Subcontractor's Activities who in the reasonable opinion of the Contractor's Representative is guilty of misconduct or is incompetent or negligent.

The Subcontractor must ensure that this person is not again employed in the Subcontractor's Activities.

Industrial Relations

In this Subcontract the following terms are defined:

“Adverse Ruling” means a ruling by any court, tribunal, board, commission or other entity with jurisdiction to determine employee and industrial relations matters to the effect that the Subcontractor or subsubcontractor breached its Employee and Industrial Relations Obligations.

“Employee” means a natural person who is employed under a contract of service (excluding professional or information technology services) to provide the Subcontractor or a subsubcontractor with his or her labour.

“Employee and Industrial Relations Obligations” mean compliance with:

Prescribed Legislation;

the orders, directions or decisions of any court, tribunal, board, commission or other entity with jurisdiction to consider the interpretation, breach or any other matter concerning any Prescribed Legislation;

Industrial Instruments; and

the IRE Strategy.

Note:	Examples of Employee and Industrial Relations Obligations may include payment of remuneration; training; annual holidays; long service leave entitlements; work health and safety requirements; workers’ compensation; injury management, (including rehabilitation); legal age of employment; discrimination; freedom of association and superannuation. This list is non exhaustive.

“Ethical Suppliers Declaration” means a statutory declaration in the form set out in this Subcontract at Annexure 2 (or such other modified form of statutory declaration as approved by the Contractor or Territory and advised to the Subcontractor from time to time).

“Full Details” means the details of:

      - the nature of the breach or offence or alleged breach or offence;

any conviction recorded or adverse finding made in respect of the breach or offence;

any penalty or orders imposed by a court, tribunal, board, commission or other entity in respect of the breach or offence and the maximum penalty that could have been imposed under the Prescribed Legislation;

the name of the court, tribunal, board, commission or other entity; the State or Territory in which the proceeding or prosecution is brought; the date on which the proceeding or prosecution was commenced and the number or description assigned to the proceeding or prosecution by the court, tribunal, board, commission or other entity; and

the name of the person or other legal entity against which the finding or conviction was made or the proceeding or prosecution was initiated.

“Industrial Instruments” means an award or agreement, however designated, that:

      - is made under or recognised by an industrial law; or

      - concerns the relationship of an employer and the employer’s employees.

“IRE Certificate” has the same meaning as set out in the IRE Strategy.

“Prescribed Legislation” means:

      - Industrial Instruments applicable to the Subcontractor, a supplier or subsubcontractor;

      - Long Service Leave Act 1976 (ACT);

      - Work Safety Act 2008 (ACT);

      - Long Service Leave (Portable Schemes) Act 2009 (ACT);

      - Workers’ Compensation Act 1951 (ACT);

      - Workplace Relations Act 1996 (Cth);

      - Fair Work Act 2009 (Cth);

      - Superannuation Guarantee (Administration) Act 1992 (Cth);

      - Building and Construction industry Improvement Act 2005 (Cth);

      - Workplace Gender Equality Act 2012 (Cth);

      - Paid Parental Leave Act 2010 (Cth);

      - Payroll Tax Act 1987 (ACT);

      - Work Health and Safety Act 2011 (ACT);

      - any Regulations made under the above Acts;

      - any laws of the Commonwealth or the Australian Capital Territory which vary or replace the above Acts or Regulations, or any part of them; and

      - any other Acts or Regulations of the Commonwealth or the Australian Capital Territory, which deal with matters relating to industrial relations, employment and/or workplace safety obligations.

“Prescribed Works or Services” means works or services that require the exertion of labour by Employees.

“Project Compliance Audit” has the same meaning as in the IRE Strategy.

This clause applies to the extent that the Subcontract provides for the performance of Prescribed Works or Services.

The Subcontractor must provide the Contractor with an Ethical Suppliers Declaration:

if requested by the Contractor, at the time the Subcontractor enters into this Subcontract; and

if requested in writing by the Contractor, at the time the Subcontractor provides a payment claim; and

within 7 days of the date of a written request from the Contractor to the Subcontractor to provide the same.

The failure of the Subcontractor to provide the Ethical Suppliers Declaration in accordance with this clause or the making of a false statement in a statutory declaration by the Subcontractor or its representative making the declaration will constitute a substantial breach for the purpose of clause 14.2.

If the Subcontractor fails to provide the Ethical Suppliers Declaration in accordance with this clause, the Contractor may withhold payment of monies due to the Subcontractor until the statutory declaration is received.

The Contractor may by written notice request the Subcontractor obtain a statutory declaration from a subsubcontractor in substantially the same form as the Ethical Suppliers Declaration (subject to necessary modifications to note the changed parties, for example references to “Subcontractor” will be varied to read “subsubcontractor”) and provide the same to the Contractor within 21 days of the date of the written notice.  The Subcontractor must use its reasonable endeavours to ensure the subsubcontractor supplies the declaration to enable the Subcontractor to comply with this clause.

The Subcontractor must ensure terms are included in all agreements with subsubcontractors requiring   subsubcontractors to provide statutory declarations to the Subcontractor to enable it to satisfy this clause.

The Subcontractor (and all subsubcontractors) must comply with all Employee and Industrial Relations Obligations.

Without limiting paragraph (h), Employees must be paid wages at rates and employed under conditions of employment not less favourable than those required by any Prescribed Legislation which applies to the Subcontractor (or subsubcontractor, as applicable).

The Subcontractor and all subsubcontractors must keep proper records and documents evidencing:

the wages paid to Employees;

so far as practicable, the time worked by Employees;

payments made to third parties on behalf of Employees; and

compliance with all Employee and Industrial Relations Obligations.

The Subcontractor must, at all reasonable times allow, and must require its subsubcontractors to allow, the Contractor or any person authorised by the Contractor (including any person conducting a Project Compliance Audit):

to enter upon the Site to inspect the conditions in which Employees are employed;

to enter upon the Site or any premises occupied by the Subcontractor or subsubcontractor, to inspect and copy, as applicable, their:

wage books;

time sheets;

records evidencing payment of superannuation entitlements;

records evidencing payment of long service leave entitlements; and

other records relevant to establishing compliance with the Employee and Industrial Relations Obligations;

to enter upon the Site or any premises occupied by the Subcontractor or subsubcontractor, to interview any persons as necessary to demonstrate the compliance or otherwise of the Subcontractor and any subsubcontractors with their Employee and Industrial Relations Obligations.

The Subcontractor must take all reasonable actions and comply with all reasonable requests of the Territory, the Contractor or their respective authorised persons, and must require its subsubcontractors to take all reasonable actions and comply with all reasonable requests to ensure compliance with this clause (or the equivalent condition in any agreement with a subsubcontractor). The Subcontractor (and any subsubcontractor) will have no claim against the Territory, the Contractor or their respective authorised persons for costs incurred by it in responding to any requests of the Territory, the Contractor or their respective authorised persons made  in accordance with or under this clause.

If at any time during the term of the Subcontract, an Adverse Ruling is made regarding the Subcontractor, the Subcontractor must within 7 days of the making of the Adverse Ruling provide a statutory declaration by an authorised representative of the Subcontractor setting out:

the Full Details of the Adverse Ruling;

if applicable, any additional information which in the opinion of the Subcontractor is relevant to the Adverse Ruling, including the Subcontractor’s grounds for any objection to the Adverse Ruling being relied upon as a ground for termination of this Subcontract;

if applicable, details of any information on which the Adverse Ruling is based which in the opinion of the Subcontractor is incorrect, incomplete or otherwise unfairly prejudicial to the Subcontractor for purposes of its dealings with the Contractor under this Subcontract; and

if applicable, any existing or planned remedial measures which the Subcontractor has taken or will be taking to prevent a breach or offence similar to the non compliance, breach or offence on which the Adverse Ruling is based from recurring.

The failure of the Subcontractor to provide the statutory declaration in accordance with paragraph (m) or the making of a false statement in a statutory declaration by the Subcontractor or its representative making the declaration will constitute a substantial breach for the purpose of clause 14.2.

Following the receipt of the statutory declaration or expiration of the period specified in paragraph (m), whichever comes first, the Contractor may give the Subcontractor a written notice under clause 14.3.

In addition to any other rights set out in this Subcontract the Territory may take such action against the Subcontractor as provided for in the IRE Strategy in the event of an Adverse Ruling being made against the Subcontractor.

The remedies under this clause are in addition to and do not limit any other rights or remedies of the Contractor under this Subcontract or otherwise at law.

The Subcontractor must ensure all agreements with subsubcontractors contain provisions:

requiring subsubcontractors to comply with all Employee and Industrial Relations Obligations applicable to the subsubcontractor and its employees; and

imposing obligations on the subsubcontractor in the same form as those set out in this clause and imposed on the Subcontractor (subject to any necessary variation to reflect the different parties).

The Subcontractor must ensure all subsubcontractors engaged to perform Prescribed Works or Services under an agreement entered into:

hold a current IRE Certificate;

maintain a current IRE Certificate during the term of their agreement; and

that these obligations are included in the relevant agreement with the subsubcontractor.

The Subcontractor must hold an IRE Certificate and must maintain a current IRE Certificate during the term of the Subcontract.

Project Review

The Subcontractor must:

meet monthly (or at such other times as the Contractor's Representative may require) with the Contractor's Representative and any other persons whom the Contractor's Representative nominates;

discuss the reports it has prepared under clauses 8.17 and  17.4 and such other matters as the Contractor's Representative may from time to time require;

promptly and fully respond to any questions which the Contractor's Representative asks in relation to any report; and

if it requires instructions from the Contractor, make all necessary recommendations as to the action required.

The Contractor's Representative must:

before each meeting – prepare an agenda for that meeting; and

after each meeting – prepare minutes of the meeting and distribute them to all attendees of the meeting.

SECURITY

Form

The Subcontractor must provide security to the Contractor:

in the form of Approved Security;

in the amount set out in the Subcontract Particulars; and

within 14 days of the Award Date.

Release

The Contractor must:

within 14 days of the issue of a Notice of Completion for the Subcontract Works or for each and every Stage, release from the security held under clause 4.1, 50% of the security required under clause 4.1;

within 14 days of the expiration of the last Defects Liability Period (excluding any extensions under clause 9.11), release such amount of the security under clause 4.1 then held, as the Contractor's Representative determines to be reasonable, having regard to the work to which the remaining Defects Liability Periods apply, to ensure the Contractor's interests are not prejudiced; and

release the balance of the security under clause 4.1 then held when:

the last Defects Liability Period has expired; and

the Subcontractor has complied with all its obligations under the Subcontract.

Interest

The Contractor:

is not obliged to pay the Subcontractor interest on:

the Approved Security; or

subject to paragraph (b), the proceeds of the Approved Security if it is converted into cash; and

does not hold the proceeds or money referred to in subparagraph (i) on trust for the Subcontractor.

If the Contractor makes a call upon any security held under clause 4.1 and obtains cash as a consequence:

the Contractor will pay simple interest, at the rate applying to damages for the purpose of clause 12.13, on the amount of any cash obtained in excess of the sum to which the Contractor is entitled at the time of such call; and

the sum attracting interest pursuant to subparagraph (i) will be further reduced by any unsatisfied amounts which subsequently become payable (whether as a debt, by way of damages or otherwise) by the Subcontractor to the Contractor at the time such amounts become payable.

Related Company Guarantee

The Subcontractor must, if so requested in writing by the Contractor, provide to the Contractor on the date set out in the request a deed of guarantee, undertaking and substitution:

in the form set out in the Schedule of Collateral Documents; and

duly executed by the Subcontractor and the Related Body Corporate of the Subcontractor nominated in the Contractor's request.

RISKS AND INSURANCE

Risk of Subcontract Works

The parties acknowledge that under the Managing Contractor Contract the Territory is required to effect the Construction Risks Insurance.

The Contractor will provide details of the broker for the Construction Risks Insurance upon request by the Subcontractor and the Subcontractor in order for the Subcontractor to review and satisfy itself as to those terms.

The Contractor bears the risk in respect of any Contractor Risk.

Except to the extent that it arises from a Contractor Risk or is covered by the Construction Risks Insurance, the Subcontractor will bear the risk of and indemnify the Contractor against:

any loss of or damage to:

the Subcontract Works or a Stage;

Plant, Equipment and Work; and

unfixed goods and materials (whether on or off Site), including anything provided by the Contractor to the Subcontractor or brought onto Site by a subsubcontractor, used or to be used in carrying out the Subcontractor's Activities,

until:

in the case of loss of or damage to the Subcontract Works or a Stage, a Notice of Completion is issued for the Subcontract Works or the Stage; and

otherwise, a Notice of Completion is issued for the Subcontract Works or the last Stage to reach Completion; and

after the issue of a Notice of Completion for the Subcontract Works or a Stage, any loss of or damage to the Subcontract Works or the Stage arising from any act or omission of the Subcontractor during the Defects Liability Period or from an event which occurred prior to the issue of the Notice of Completion  for the Subcontract Works or the Stage.

Other Risks

Except to the extent that it arises from a Contractor Risk or is covered by the Construction Risks Insurance, the Subcontractor will bear the risk and indemnify the Contractor against:

any loss of or damage to property of the Contractor; and

any liability to or claims by a third party in respect of loss of or damage to property or injury to or death of persons,

other than caused by, or arising out of, or in any way in connection with, the Subcontractor's Activities provided that the Subcontractor's responsibility to indemnify the Contractor will be reduced to the extent that an act or omission of the Territory, the MCC Contract Administrator, the Contractor, the Contractor's Representative or an Other Contractor may have contributed to the loss, damage, injury or death.

Reinstatement

During the period during which the Subcontractor bears the risk of loss or damage, and to the extent the Subcontractor bears the risk of loss or damage, under clause 5.1, the Subcontractor must:

subject to paragraph (b), promptly replace or otherwise make good any loss of, or repair the damage to, the Subcontract Works or a Stage, any Plant, Equipment and Work or any unfixed goods and materials used or to be used in carrying out the Subcontractor's Activities; and

where the loss or damage arises from a Contractor Risk, only comply with paragraph (a) to the extent directed by the Contractor's Representative.

The Subcontractor will bear the cost of such replacement, making good or repair except to the extent that the loss or damage arises from a Contractor Risk or is covered by the Construction Risks Insurance, in which event this replacement, making good or repair will, to the extent the loss or damage arises from a Contractor Risk (but subject to paragraph (b)), be treated as if it were a Variation the subject of a direction by the Contractor's Representative and clause 11.3 applied.

Contractor Insurance Obligations

The Contractor must:

from the Award Date effect Public Liability Insurance and the other insurance (if any) specified in the Subcontract Particulars; and

provide the Subcontractor with evidence satisfactory to the Subcontractor that the policy is current as required by the Subcontractor from time to time.

This insurance is subject to the exclusions, conditions and excesses noted on the policies and the Subcontractor must:

satisfy itself of the nature and extent of the Contractor's insurance;

if required by the Subcontractor, take out insurance to:

insure any risks not insured by the Contractor's insurance or the Construction Risks Insurance; or

cover any such exclusions, conditions or excesses in that insurance,

which the Subcontractor wants to insure against or cover.

Subcontractor Insurance Obligations

The Subcontractor must:

from the Award Date effect and maintain the following insurance:

Public Liability Insurance;

Workers Compensation Insurance in each State and Territory in which the Subcontractor's Activities are to be performed or the Subcontractor's employees are employed or normally reside;

Professional Indemnity Insurance for the amount included for it in the Subcontract Particulars; and

such other insurances on such terms as are set out in the Subcontract Particulars,

each of which is to be:

for the respective amount referred to in the Subcontract Particulars;

with reputable insurers having a Standard and Poors, Moodys, A M Best, Fitch's or equivalent rating agency's financial strength rating of A - or better; and

on terms which are satisfactory to the Contractor's Representative (confirmation of which must not be unreasonably withheld or delayed);

in relation to the Workers Compensation Insurance:

ensure that to the extent permitted by law, the insurance policy extends to provide indemnity to the Territory and the Contractor in respect of any statutory liability to the Subcontractor's employees; and

ensure that each of its subsubcontractors legally required to do so, has Workers Compensation Insurance covering the subsubcontractor in respect of its statutory liability to employees, in the same manner as the Subcontractor is required to do so under paragraph (a)(ii);

provide the Contractor's Representative with evidence satisfactory to the Contractor's Representative that each policy is current as required by the Contractor's Representative from time to time;

ensure that:

if the insurer gives the Subcontractor notice of expiry, cancellation or rescission of any required insurance policy, the Subcontractor as soon as possible informs the Contractor in writing that the notice has been given and effects replacement insurance on terms and subject to limits acceptable to the Contractor's Representative, whose acceptance will not be unreasonably withheld; and

if the Subcontractor cancels, rescinds or fails to renew any required insurance policy, the Subcontractor as soon as possible obtains replacement insurance as required by this Subcontract and informs the Contractor in writing as soon as possible of the identity of the replacement insurer, and provides such evidence as the Contractor's Representative reasonably requires that the replacement insurance complies in all relevant respects with the requirements of this Subcontract;

ensure that it:

does not do or omit to do anything whereby any insurance may be prejudiced;

if necessary, takes all possible steps to rectify any situation which might prejudice any insurance;

renews any required insurance policy if it expires during the relevant period, unless appropriate replacement insurance is obtained;

does not cancel or allow an insurance policy to lapse during the period for which it is required by the Subcontract without the prior written consent of the Contractor's Representative;

immediately notifies the Contractor's Representative (in writing) of any event which may result in a required insurance policy lapsing, being cancelled or rescinded; and

complies fully with its duty of disclosure and obligations of utmost good faith toward the insurer and in connection with all of the required insurance policies; and

ensure that any subsubcontractors that perform any design work forming part of the Subcontractor's Activities also maintain Professional Indemnity Insurance in the same manner and on the same terms as those required to be obtained by the Subcontractor under clause 5.5(a)(iii), for not less than the amount referred to in the Subcontract Particulars.

The obtaining of insurance as required under this clause 5.5 will not in any way limit, reduce or otherwise affect any of the obligations, responsibilities and liabilities of the Subcontractor under any other provisions of the Subcontract or otherwise at law or in equity.

Failure to Insure

If the Subcontractor fails to:

provide evidence satisfactory to the Contractor's Representative that a policy is current; or

obtain insurance in accordance with clause 5.5,

the Contractor may, without prejudice to any other rights it may have, take out the relevant insurance and the cost will be a debt due from the Subcontractor to the Contractor.

Period of Insurance

The insurance which the Contractor is required to obtain and the insurance the Subcontractor is required to obtain under this clause 5 must be maintained:

in the case of Public Liability Insurance and Workers Compensation Insurance, until the latest of:

the end of the last Defects Liability Period;

the date upon which all Defects have been rectified in accordance with the Subcontract; and

the date upon which the Subcontractor ceases to carry out the Subcontractor's Activities; and

in the case of Professional Indemnity Insurance, until the expiration of the period specified in the Subcontract Particulars following the latest of:

the last Date of Completion; and

the date upon which the Subcontractor ceases to carry out the Subcontractor's Activities.

Notice of Potential Claim

The Subcontractor must:

as soon as possible inform the Contractor in writing of any occurrence that may give rise to a claim under an insurance policy required by the Subcontract or under the Construction Risks Insurance;

keep the Contractor informed of all significant developments concerning the claim, except in circumstances where the Contractor is making a claim against the Subcontractor; and

ensure that its subsubcontractors similarly inform the Subcontractor and the Contractor in respect of occurrences which may give rise to claims by them,

provided that, in respect of Professional Indemnity Insurance, the Subcontractor:

subject to paragraph (e), is not required to provide details of individual claims; and

must notify the Contractor if the estimated total combined value of claims made against the Subcontractor and claims which may arise from circumstances reported by the Subcontractor to its insurer in a policy year would potentially reduce the available limit of policy indemnity for that year below the amount required by the Subcontract.

Procedure upon Loss or Damage

If loss of or damage to any part of the Subcontract Works or a Stage occurs whilst the Construction Risks Insurance is in place:

the Subcontractor must:

make the Subcontract Works or the Stage and the Site safe and secure;

notify the Territory’s Construction Risks Insurance broker and comply with their instructions; and

promptly consult with the Contractor's Representative to discuss the steps to be taken to ensure that, to the greatest extent possible, the Subcontractor continues to comply with its other obligations under this Subcontract;

ensure that, to the greatest extent possible, the Subcontractor continues to comply with its other obligations under this Subcontract.

Cross Liability

This clause 5.10 does not apply to Professional Indemnity Insurance or Workers Compensation Insurance.

Where the Subcontract requires insurance to provide cover to more than one insured, the Subcontractor must ensure that the insurance policy provides that:

the insurance (with the exception of limits of liability) will operate in the same manner as if there were a separate policy of insurance covering each named insured;

the insurer waives all rights, remedies or relief to which it might become entitled by subrogation against any of the parties to whom coverage extends and that failure by any insured to observe and fulfil the terms of the policy will not prejudice the insurance in regard to any other insured; and

a notice to the insurer by one insured will be deemed to be notice on behalf of all insureds.

DESIGN AND DOCUMENTATION

Contractor's Documents

The Contractor must provide to the Subcontractor the documents and number of copies of those documents specified in the Subcontract Particulars.

Subcontractor's Design

The Subcontractor must:

design the parts of the Subcontract Works which the Subcontract requires it to design in accordance with the Subcontract Works Description and the other requirements of the Subcontract and for this purpose (but without limitation) prepare all relevant Design Documentation;

as part of the program it is to prepare under clause 10.2, submit to the Contractor's Representative for approval a documentation program which makes allowance for the Design Documentation to be submitted to the Contractor's Representative in a manner and at a rate which will give the Contractor's Representative a reasonable opportunity to review the Design Documentation within the period of time within which the Contractor's Representative may review the Design Documentation under clause 6.3; and

submit the Design Documentation it prepares to the Contractor's Representative in accordance with the documentation program approved by the Contractor's Representative under paragraph (b).

Contractor's Representative may Review Design Documentation

The Contractor's Representative may:

review any Design Documentation, or any resubmitted Design Documentation, prepared and submitted by the Subcontractor; and

within the number of days set out in the Subcontract Particulars of the submission by the Subcontractor of such Design Documentation or resubmitted Design Documentation, reject the Design Documentation if in the Contractor's Representative's reasonable opinion the Design Documentation does not comply with the requirements of the Subcontract.

If any Design Documentation is rejected, the Subcontractor must submit amended Design Documentation to the Contractor's Representative.

The Subcontractor must not commence construction of any part of the Subcontract Works to which any Design Documentation which it has submitted to the Contractor's Representative applies, unless the Contractor's Representative has had the number of days set out in the Subcontract Particulars to review the Design Documentation and has not rejected the Design Documentation.

No Obligation to Review

Without limiting the Contractor's obligations and liability to the Territory under the Managing Contractor Contract:

the Contractor's Representative does not assume or owe any duty of care to the Subcontractor to review, or in reviewing, the Design Documentation submitted by the Subcontractor for errors, omissions or compliance with the Subcontract; and

no review of, comments upon, consent to or rejection of, or failure to review or comment upon or consent to or reject, any Design Documentation prepared by the Subcontractor or any other direction by the Contractor's Representative about, or any other act or omission by the Contractor's Representative or otherwise by or on behalf of the Contractor in relation to, the Design Documentation will:

relieve the Subcontractor from, or alter or affect, the Subcontractor's liabilities or responsibilities whether under the Subcontract  or otherwise according to law; or

prejudice the Contractor's rights against the Subcontractor whether under the Subcontract  or otherwise according to law.

Copies of Design Documentation

For the purposes of clauses 6.2(c) and 6.3, the Subcontractor must submit or resubmit to the Contractor's Representative the number of copies specified in the Subcontract Particulars of any Design Documentation in:

hard copy; and

electronic copy,

in each case in accordance with the requirements set out in the Subcontract Particulars.

Fitness for Purpose

The Subcontractor warrants that:

the Design Documentation it prepares will be fit for its intended purpose; and

upon Completion, the Subcontract Works or each Stage will, to the extent that they have been designed by the Subcontractor, be fit for their intended purpose.

Availability

The Subcontractor must keep available for the use of the Contractor's Representative, the Contractor and any person authorised by either the Contractor's Representative or the Contractor:

on the Site, one complete set of the Subcontract Works Description, all Design Documentation issued by the Contractor's Representative under clause 8.8 (if Option 1 of that clause applies), any documents provided by the Contractor under clause 6.1 and all Project Documents; and

at any area off-Site where the Subcontractor's Activities are being carried out, one complete set of each of those items specified in paragraph (a) insofar as they are relevant to the Subcontractor's Activities being carried out in that area.

Licence over Project Documents

The Subcontractor grants to the Contractor a perpetual, royalty-free, irrevocable, non-exclusive, worldwide licence to exercise all rights of the owner of the Intellectual Property Rights in the Project Documents, including to use, re-use, reproduce, communicate to the public, modify and adapt any of the Project Documents.

This licence:

arises, for each Project Document, immediately the Project Document is:

produced; or

provided, or required to be provided, to the Contractor or the Contractor's Representative,

under, for the purposes of or in connection with the Subcontract, the Subcontractor's Activities or the Subcontract Works by, for or on behalf of the Subcontractor;

includes an unlimited right to sub-licence;

without limitation, extends to:

any subsequent operation, maintenance or servicing of, or additions, alterations or repairs to the Subcontract Works; and

in the case of the corresponding licence granted by the Contractor to the Territory - use in any way for any other Territory project; and

survives the termination of this Subcontract on any basis.

Intellectual Property Warranties

The Subcontractor warrants that:

the Subcontractor owns all Intellectual Property Rights in the Project Documents or, to the extent that it does not, is entitled to grant the assignments and licences contemplated by this Subcontract;

use by the Contractor or any sublicensee or subsublicensee of the Project Documents in accordance with this Subcontract will not infringe the rights (including Intellectual Property Rights and Moral Rights) of any third party;

neither the Contractor nor any sublicensee or subsublicensee is liable to pay any third party any licence or other fee in respect of the use of the Project Documents, whether by reason of Intellectual Property Rights or Moral Rights of that third party or otherwise; and

the use by the Contractor or by any sublicensee or subsublicensee of the Project Documents in accordance with this Subcontract will not breach any laws (including any laws in respect of Intellectual Property Rights and Moral Rights).

Intellectual Property Rights

The Subcontractor must:

ensure that the Subcontractor's Activities do not infringe any patent, registered design, trade mark or name, copyright, Moral Rights or other protected right; and

indemnify the Contractor against any claims against, or costs, losses or damages suffered or incurred by, the Contractor arising out of, or in any way in connection with, any actual or alleged infringement of any patent, registered design, trade mark or name, copyright, Moral Rights or other protected right.

Resolution of Ambiguities

If there is any ambiguity, discrepancy or inconsistency in the documents which make up the Subcontract or between the Subcontract and any Design Documentation (which the Subcontractor is entitled to use for construction purposes under clause 6.3) or any other Project Document:

the order of precedence in the Subcontract Particulars will apply;

where the ambiguity, discrepancy or inconsistency is between the Subcontract and any part of the Design Documentation or any other Project Document, the higher standard, quality or quantum will prevail but if this does not resolve the ambiguity, discrepancy or inconsistency, the Subcontract will prevail;

if it is discovered by the Subcontractor or the Contractor's Representative, then the party discovering it must promptly give notice to the other; and

the Contractor's Representative must instruct the Subcontractor as to the course it must adopt within 14 days of the notice under paragraph (c).

Access to Premises and Project Documents

The Subcontractor must:

at the request of the Contractor's Representative at any time during the execution of the Subcontractor's Activities and the period of 10 years following the issue of a Notice of Completion for the Subcontract Works:

provide access to its premises and make the Project Documents available for inspection and copying by the Contractor's Representative or any other person nominated by the Contractor's Representative;

provide to the Contractor's Representative such copies of the Project Documents as the Contractor's Representative or any nominated person may require;

provide all such facilities and assistance and answer all questions of the Contractor's Representative or any nominated person; and

make available any officers, employees, agents or subsubcontractors for interviews with the Contractor's Representative or any nominated person;

as a condition precedent to Completion of each Stage or the Subcontract Works, deliver to the Contractor's Representative a copy of the installed version of each item of software comprising the IT Equipment incorporated in that Stage or the Subcontract Works, in a storage medium reasonably satisfactory to the Contractor, together with a copy of all documentation, including licence terms, warranty terms and operating manuals associated with each item of such software; and

ensure that any subsubcontract made in connection with this Subcontract contains enforceable obligations requiring the subsubcontractor to comply with the Subcontractor's obligations arising under this clause 6.12 as if the subsubcontractor were the Subcontractor.

Design Certification

Without limiting the Contractor's obligations and liability to the Territory under the Managing Contractor Contract and the Subcontractor's obligations, where the Subcontract requires the Subcontractor to design any part of the Subcontract Works, the Subcontractor must, with each payment claim under clause 12.2 and as a condition precedent to Completion of the Subcontract Works or a Stage (as the case may be), provide the Contractor's Representative with:

a certificate in the form of the Subcontractor Design Certificate which certifies that (to the extent then applicable):

the Design Documentation complies with:

subject to clause 8.3(a), all Statutory Requirements (including the WHS Legislation); and

the requirements of the Subcontract; and

the Subcontract Works comply or the Stage complies (as the case may be) with the Design Documentation which the Subcontractor is entitled to use for construction purposes under clause 6.3(c); and

a corresponding certificate from each subsubcontractor that performs design work forming part of the Subcontractor's Activities in the form of the Consultant Design Certificate or Subsubcontractor Design Certificate (as the case may be) which certifies that (to the extent then applicable):

all design carried out by that subsubcontractor complies with:

subject to the subsubcontract, all Statutory Requirements (including the WHS Legislation); and

the requirements of the subsubcontract; and

the Subcontract Works comply or the Stage complies (as the case may be) with the design carried out by that subsubcontractor,

except to the extent set out in such certificates.

Samples

The Subcontractor must:

obtain each sample or range of samples required by the Subcontract; and

submit the sample or range of samples it obtains to the Contractor's Representative in accordance with the program approved by the Contractor's Representative under clause 10.2, as updated with the approval of the Contractor's Representative under clause 10.2.

The Contractor's Representative may:

review the sample or range of samples, or any resubmitted sample or range of samples, submitted by the Subcontractor; and

within the number of days set out in the Subcontract Particulars of the submission of such sample or range of samples or resubmitted sample or range of samples, reject the sample or range of samples.

If any sample or range of samples is rejected, the Subcontractor must submit an amended or substituted sample or range of samples to the Contractor's Representative.

The Subcontractor must not commence construction of any part of the Subcontract Works to which the sample or range of samples which it has submitted to the Contractor's Representative applies unless the Contractor's Representative has had the number of days set out in the Subcontract Particulars to review the sample or range of samples and has not rejected the sample or samples.

Without limiting the Contractor's obligations and liability to the Territory under the Managing Contractor Contract:

the Contractor's Representative does not assume or owe any duty of care to the Subcontractor to review, or in reviewing, the sample or range of samples submitted by the Subcontractor for errors, omissions or compliance with the Subcontract; and

no review of, comments upon, consent to or rejection of, or failure to review or comment upon or consent to or reject, any sample or range of samples prepared by the Subcontractor or any other direction by the Contractor's Representative about, or any other act or omission by the Contractor's Representative or otherwise by or on behalf of the Contractor in relation to, the sample or range of samples will:

relieve the Subcontractor from, or alter or affect, the Subcontractor's liabilities or responsibilities whether under the Subcontract or otherwise according to law; or

prejudice the Contractor's rights against the Subcontractor whether under the Subcontract or otherwise according to law.

SITE

Subcontractor to Inform Itself

The Subcontractor warrants that it has, and it will be deemed to have, done everything that would be expected of a prudent, competent and experienced contractor in:

assessing the risks which it is assuming under the Subcontract; and

ensuring that the Subcontract Price contains sufficient allowances to protect it against any of these risks eventuating.

Site Information

Without limiting clause 7.7:

the Contractor has made available to the Subcontractor, before the Award Date, certain information, data and documents which were obtained by the Contractor, either itself or from the Territory for the purposes of the MCC Works or the Subcontract Works from investigations either it or the Territory carried out as to the conditions on, in, under or in the vicinity of the Site insofar as such information, data and documents are relevant to the Subcontract Works;

the Contractor does not warrant, guarantee or make any representation about the accuracy or adequacy of any such information, data and documents made available to the Subcontractor;

the Subcontractor acknowledges that such information, data and documents do not form part of the Subcontract and that clause 7.7 applies to the information, data and documents; and

to the extent permitted by law, the Contractor will not be liable upon any Claim by the Subcontractor arising out of, or in any way in connection with, that information, data and documents.

Notice of Latent Conditions

Clauses 7.3 and 7.4 apply unless the Subcontract Particulars state that they do not apply.

If the Subcontractor considers it has encountered or found a Latent Condition, it must immediately give the Contractor's Representative notice in writing.

After receipt of a notice from the Subcontractor, the Contractor's Representative must within 21 days of receipt of the Subcontractor's notice:

determine whether a Latent Condition has been encountered or found; and

notify the Subcontractor of the Contractor's Representative's determination.

Subcontractor's Entitlement

If the Contractor's Representative determines that a Latent Condition has been encountered or found, the Subcontractor will be entitled to:

an extension of time to any relevant Date for Completion where it is otherwise so entitled under clause 10.7; and

be paid by the Contractor any extra costs reasonably incurred by the Subcontractor after the giving of a notice under clause 7.3 arising from the Latent Condition, as determined by the Contractor's Representative and added to the Subcontract Price.

To the extent permitted by law, the Subcontractor's entitlement under this clause 7.4 will be its only right to make a Claim arising out of, or in any way in connection with, the Latent Condition.

Site Access

The Contractor:

is not obliged to:

provide the Subcontractor with sole access to the Site; or

carry out any work or provide any facilities to the Subcontractor (other than as stated in the Subcontract) which may be necessary to enable the Subcontractor to obtain adequate access to carry out the Subcontractor's Activities; and

must use reasonable endeavours to ensure that any Other Contractors engaged by the Contractor or the Territory comply with the reasonable requirements of the Subcontractor as to matters concerning industrial relations, insurance and hours of working.

The Subcontractor acknowledges and agrees that the Territory and the Contractor may engage Other Contractors to work upon or in the vicinity of the Site at the same time as the Subcontractor.

The Contractor may from time to time impose such reasonable restrictions upon the Subcontractor's right of access as may be reasonably necessary to facilitate the work being carried out by Other Contractors and the Subcontractor must observe, any carry out the Subcontractor's Activities subject to, such reasonable restrictions.

Subcontractor's Obligation to Provide Access

In carrying out the Subcontractor's Activities, the Subcontractor must:

minimise disruption or inconvenience to the Territory, the MCC Contract Administrator, the Contractor, the Contractor's Representative and any person authorised by any of them to occupy, use or attend upon the Site in their occupation or use of, or attendance upon, any part of the Site, including any occupation or use of a part of the Subcontract Works or a Stage under clause 13.5;

at all reasonable times give the Territory, the MCC Contract Administrator, the Contractor, the Contractor's Representative and any person authorised by any of them access to the Subcontract Works, the Site or any areas off-Site where the Subcontractor's Activities are being carried out; and

provide the Territory, the MCC Contract Administrator, the Contractor and the Contractor's Representative with every reasonable facility necessary for the supervision, examination and testing of the Subcontractor's Activities.

Non-Reliance

The Subcontractor:

warrants that it did not in any way rely upon:

any information, data, representation, statement or document made by or provided to the Subcontractor by the Contractor or anyone on behalf of the Contractor; or

the accuracy or adequacy of any such information, data, representation, statement or document,

for the purposes of entering into the Subcontract, except to the extent that any such information, data, representation, statement or document forms part of the Subcontract;

warrants that it enters into this Subcontract based on its own investigations, interpretations, deductions, information and determinations; and

acknowledges that it is aware that the Contractor has entered into the Subcontract relying upon the warranties in paragraphs (a) and (b).

CONSTRUCTION

Description of Subcontract Works

Subject to clause 6.11, the Subcontractor must construct the Subcontract Works in accordance with:

the Subcontract Works Description and any Design Documentation issued by the Contractor's Representative under clause 8.8 (if Option 1 of that clause applies);

any Design Documentation prepared by the Subcontractor in accordance with the requirements of the Subcontract, and which the Subcontractor is entitled to use for construction purposes under clause 6.3;

any direction of the Contractor's Representative given or purported to be given under a provision of the Subcontract, including any Variation directed by the Contractor's Representative by a document titled "Variation Order"; and

the other requirements of the Subcontract.

All Work Included

The Subcontractor has allowed for the provision of all Plant, Equipment and Work, materials and other work necessary for the Subcontractor's Activities, whether or not expressly mentioned in the Subcontract Works Description or any Design Documentation.

Any such Plant, Equipment and Work, materials and other work:

must be undertaken and provided by the Subcontractor; and

forms part of the Subcontractor's Activities and will not entitle the Subcontractor to make a Claim except as otherwise provided for in the Subcontract.

Statutory Requirements

The Subcontract Particulars describe the Approvals which exist at the Award Date or which the Territory or the Contractor will obtain after the Award Date.

In carrying out the Subcontractor's Activities, the Subcontractor must:

unless otherwise specified in the Subcontract Particulars, comply with all applicable Statutory Requirements;

without limiting paragraph (a):

apply for and obtain all Approvals other than those referred to in the Subcontract Particulars; and

give all notices and pay all fees and other amounts which it is required to pay in respect of the carrying out of its Subcontract obligations; and

promptly give the Contractor's Representative copies of all documents (including Approvals and other notices) that any authority, body or organisation having jurisdiction over the Subcontract Works or the carrying out of the Subcontractor's Activities issues to the Subcontractor.

Change in Statutory Requirements or Variance with Subcontract

If:

there is any change in a Statutory Requirement after the Award Date; or

a Statutory Requirement is at variance with the Subcontract ,

then:

the party discovering this must promptly notify the other;

the Contractor's Representative will instruct the Subcontractor as to the course it is to adopt insofar as the Subcontractor's Activities are affected by the change or variance (as the case may be); and

the Subcontract Price will be:

increased by any extra costs reasonably incurred by the Subcontractor; or

decreased by any saving made by the Subcontractor,

in carrying out the Subcontractor's Activities after the giving of the notice under paragraph (c) and arising directly from the change or variance (as the case may be) or the Contractor's Representative's instruction, in either case as determined by the Contractor's Representative.

Subcontracting

The Subcontractor:

must not without the prior written approval of the Contractor's Representative, subcontract any work described in the Subcontract Particulars except to a subsubcontractor named in the Subcontract Particulars;

will :

not be relieved of any of its liabilities or obligations under the Subcontract, including those under clause 2.2; and

remain responsible for all subsubcontractors and for all work which is or may be subsubcontracted, as if it was itself executing the work, whether or not any subsubcontractors default or otherwise fail to observe any of the requirements of the relevant subsubcontract;

will be vicariously liable to the Contractor for all acts, omissions and defaults of its subsubcontractors (and those of the employees and agents of its subsubcontractors) relating to, or in any way connected with, the Subcontractor's Activities;

must ensure that each subsubcontract contains provisions:

which bind the subsubcontractor to participate in any novation required by the Contractor  under clause 14.5(a)(ii); and

as otherwise required by this Subcontract; and

must, if requested by the Contractor's Representative:

execute;

procure the relevant subsubcontractor to execute; and

deliver to the Contractor's Representative,

a Subsubcontractor Deed of Covenant or Consultant Deed of Covenant (as the case may be), duly completed with all relevant particulars:

as a condition precedent to seeking the prior written approval of the Contractor's Representative under paragraph (a); or

when such approval is not required, within the time required by the Contractor's Representative and in any event before commencement of work by the relevant subsubcontractor.

No Subsubcontractor Deed of Covenant or Consultant Deed of Covenant will be construed in any way to modify or limit any of the rights, powers or remedies of the Contractor against the Subcontractor whether under the Subcontract or otherwise.

Subsubcontractor Warranties

The Subcontractor must, as a condition precedent to Completion of the Subcontract Works or any Stage specified in the Subcontract Particulars, procure and provide the Contractor with the warranties described in the Subcontract Particulars:

from the relevant subsubcontractor undertaking or supplying the work or item the subject of the warranty; and

in the form of the Collateral Warranty.

No Collateral Warranty will be construed in any way to modify or limit any of the rights, powers or remedies of the Territory or the Contractor (as the case may be) against the Contractor, the Subcontractor or the Subsubcontractors (as the case may be) whether under the Subcontract or otherwise.

If the Subcontractor is unable to or fails for any reason to provide any Collateral Warranty required by this Subcontract:

the Subcontractor is deemed to have provided the Collateral Warranty itself on like terms;

the Territory or the Contractor (as the case may be) will be entitled to elect to take an assignment of all the right, title and interest in the Subcontractor's rights against the subsubcontractor in relation to the Subcontractor's Activities; and

for the purpose of paragraph (d), the Subcontractor irrevocably appoints the Territory or the Contractor (as the case may be) as its lawful attorney to execute any instrument necessary to give effect to the assignment.

No assignment under this clause will be construed in any way to modify or limit any of the rights, powers or remedies of the Territory or the Contractor against the Subcontractor or the subsubcontractor whether under the Subcontract or otherwise.

Provisional Sum Work

For each item of Provisional Sum Work, the Contractor's Representative will give the Subcontractor an instruction either deleting that item of Provisional Sum Work from the Subcontract or requiring the Subcontractor to proceed with the relevant work.

If any item of Provisional Sum Work is deleted from the Subcontract:

the Subcontract Price will be reduced by the amount allowed for the item of Provisional Sum Work in the Subcontract Particulars;

the Contractor may engage an Other Contractor to carry out the item of Provisional Sum Work; and

the Contractor will not be liable upon any Claim by the Subcontractor arising out of, or in any way in connection with, the deletion of the item of Provisional Sum Work.

Design for Provisional Sum Work to be Prepared by Contractor - Option 1

If the Subcontractor is instructed to proceed with an item of Provisional Sum Work, the Contractor's designers will progressively prepare the Design Documentation for the item of Provisional Sum Work.

The Subcontractor must attend such design and other meetings as required by the Contractor's Representative to assist these designers in preparing the Design Documentation for the Provisional Sum Work and to advise upon:

buildability issues and the choice of materials to be incorporated in the Subcontract Works; and

the sufficiency and completeness of the Design Documentation.

8.8	Design for Provisional Sum Work to be Prepared by Subcontractor - Option 2

If the Subcontractor is instructed to proceed with an item of Provisional Sum Work, the Subcontractor will progressively prepare the Design Documentation for the item of Provisional Sum Work.

The Subcontractor must inform the Contractor's Representative when the Design Documentation is being discussed at design and other meetings and the Contractor's Representative may attend all such meetings.

Tendering Provisional Sum Work

Where the Subcontractor is instructed to proceed with an item of Provisional Sum Work, it must, unless otherwise directed by the Contractor's Representative, be carried out under subsubcontracts entered into by the Subcontractor as follows:

after the Design Documentation for the item of Provisional Sum Work has been prepared (and, if prepared by the Subcontractor, is in accordance with the requirements of the Subcontract and the Subcontractor is entitled to use it for construction purposes under clause 6.3), the Subcontractor must invite tenders:

from at least 3 persons as either specified in the Subcontract Particulars or otherwise proposed by the Subcontractor and approved by the Contractor's Representative; and

on the terms of a subsubcontract containing similar terms to the Subcontract and approved by the Contractor's Representative (for the purpose of this clause, each form of subsubcontract referred to in the Subcontract Particulars is approved);

the Subcontractor must give the Contractor's Representative such details of each tender as the Contractor's Representative may require;

the Subcontractor must recommend to the Contractor's Representative which tenderer it believes should be accepted and, if this tenderer is not the lowest priced tenderer, it must give reasons why the lowest priced tenderer is not recommended; and

the Subcontractor must then enter into a subsubcontract with a tenderer as instructed by the Contractor's Representative.

Price Adjustment for Tendered Provisional Sum Work

After the Subcontractor is instructed to enter into a subsubcontract for an item of Provisional Sum Work under clause 8.9:

the Subcontract Price will, if the amount tendered by the tenderer with whom the Subcontractor is instructed to enter into the subsubcontract is more or less than the amount allowed in the Subcontract Particulars for that item of Provisional Sum Work, be adjusted by the amount of the difference, with no further allowance for overhead and profit except as set out in clause 8.12; and

any Variation to that work will be dealt with under clause 11.

Price Adjustment for Other Provisional Sum Work

If the Contractor's Representative directs that an item of Provisional Sum Work is not to be put out to tender in accordance with the procedure in clause 8.9, the Subcontract Price will be adjusted for the item of Provisional Sum Work by the difference between:

the amount allowed for the item of Provisional Sum Work in the Subcontract Particulars; and

either:

an amount agreed between the Subcontractor and the Contractor's Representative; or

if they fail to agree, an amount determined by the Contractor's Representative under clause 11.3(b) or 11.3(c)(ii) as if the item of Provisional Sum Work were a Variation.

Further Allowance for Provisional Sum Work

If, after each and every item of Provisional Sum Work has been deleted under clause 8.7, put out to tender under clause 8.9 or priced under clause 8.11, the total net increase to the Subcontract Price after all adjustments under clauses 8.7, 8.10 and 8.11 exceeds the percentage set out in the Subcontract Particulars of the total amount allowed in the Subcontract Particulars for Provisional Sum Work, the Subcontract Price will be further increased by the percentage set out in the Subcontract Particulars of the amount by which the total net increase to the Subcontract Price exceeds the percentage set out in the Subcontract Particulars of the total amount allowed in the Subcontract Particulars.

Co-operation with Other Contractors

Without limiting clause 8.17(a)(iii), the Subcontractor must:

permit Other Contractors to carry out their work;

fully co-operate with Other Contractors;

carefully co-ordinate and interface the Subcontractor's Activities with the work carried out or to be carried out by Other Contractors; and

carry out the Subcontractor's Activities so as to avoid interfering with, disrupting or delaying the work of Other Contractors.

Setting Out

The Subcontractor must:

set out the Subcontract Works in accordance with the requirements of the Subcontract; and

carry out any survey which may be necessary for this purpose.

Survey

The Subcontractor must as a condition precedent to Completion of the Subcontract Works or of any Stage specified in the Subcontract Particulars, submit to the Contractor's Representative a certificate signed by a licensed surveyor stating that:

the whole of the Subcontract Works or the Stage are within any particular boundaries stipulated in the Subcontract except only for parts of the Subcontract Works or Stage specifically required by the Subcontract to be outside those boundaries; and

where so required by the Subcontract Works Description, structural elements of the Subcontract Works or the Stage are within the tolerances specified.

Safety

The Subcontractor must carry out the Subcontractor's Activities safely and in a manner that does not put the health and safety of persons at risk.

The Subcontractor must carry out the Subcontractor's Activities in a manner that protects property.

If the MCC Contract Administrator or the Contractor's Representative reasonably considers there is a risk to the health and safety of people or damage to property arising from the Subcontractor's Activities, the MCC Contract Administrator or the Contractor's Representative (as the case may be) may direct the Subcontractor to change its manner of working or to cease working.

Work Health and Safety Management

The Subcontractor must:

ensure that in carrying out the Subcontractor's Activities:

it complies with all Statutory Requirements and other requirements of the Subcontract for work health and safety management;

all subsubcontractors comply with the requirements referred to in this clause 8.17; and

it complies with its duty under the WHS Legislation to consult, cooperate and coordinate activities with all other persons who have a work health and safety duty in relation to the same matter;

without limiting the Subcontractor's obligations under this Subcontract or at law, notify the Contractor's Representative and the MCC Contract Administrator immediately after it notifies the regulator (if required), of all work health and safety matters arising out of, or in any way in connection with, the Subcontractor's Activities, including the occurrence of notifiable incidents within the meaning of the WHS Legislation and provide copies of all referable notices and communications issued by a regulator or agent of the regulator to the Contractor’s Representative immediately upon receiving the same;

regularly review its Work Health and Safety Plan, continue to update and amend its Work Health and Safety Plan and submit it (as necessary) in accordance with clause 9.2 and the WHS Legislation;

institute systems to obtain regular written assurances from each Other Contractor and subsubcontractor about their ongoing compliance with the WHS Legislation including the due diligence obligation contained in the WHS Legislation;

provide the written assurances obtained under paragraph (e), together with written assurances from the Subcontractor about the Subcontractor's ongoing compliance with the WHS Legislation, to the Contractor's Representative;

provide the Contractor's Representative with a written report at each meeting in accordance with clause 3.9 on all work health and safety matters (including matters concerning or arising out of, or in connection with, this clause 8.17), or any other relevant matters as the Contractor's Representative may require from time to time, including a summary of the Subcontractor's compliance with the WHS Legislation;

exercise a duty of the utmost good faith to the Contractor and the Territory in carrying out the Subcontractor's Activities to enable the Contractor and the Territory to discharge their duties under the WHS Legislation;

ensure its subcontracts include provisions equivalent to the obligations of the Subcontractor in this clause 8.17;

ensure that, if any Statutory Requirement, including in the State or Territory in which the Works are situated or the Subcontractor's Activities are carried out (as the case may be), requires that:

a person:

be authorised or licensed (in accordance with the WHS Legislation) to carry out any work at that workplace, that person is so authorised or licensed, and complies with any conditions of such authorisation or licence; or

has prescribed qualifications or experience, or if not, is to be supervised by a person who has prescribed qualifications or experience (as defined in the WHS Legislation), that person has the required qualifications or experience or is so supervised; or

a workplace, plant or substance (or design), or work (or class of work) be authorised or licensed, that workplace, plant or substance, or work is so authorised or licensed;

not direct or allow a person to carry out work, or use plant or a substance at a workplace unless the authorisation, licensing, prescribed qualifications or experience required by any Statutory Requirement and paragraph (i) are met;

without limiting the Subcontractor's obligations under this Subcontract or at law:

provide any information or copies of documentation held by the Subcontractor or a subsubcontractor to the Contractor's Representative and the MCC Contract Administrator within 14 days of a request by the Contractor's Representative or the MCC Contract Administrator (and in the case of notifiable incidents, immediately and if not immediately, as soon as that information is in the possession of the Subcontractor), to enable the Territory and the Contractor to comply with their obligations under the WHS Legislation; and

provide copies of:

all notices and communications issued by a regulator, agent of the regulator or a health and safety representative to the Subcontractor or a subsubcontractor; and

all notices, communications and undertakings given by the Subcontractor or a subsubcontractor to the regulator, agent of the regulator or a health and safety representative,

in connection with or related to the Subcontractor's Activities or the Subcontract Works to the Contractor's Representative and the MCC Contract Administrator within 14 days of receipt or submission of the notice, communication or undertaking by the Subcontractor or subsubcontractor (as the case may be); and

if requested by the Contractor's Representative or required by the WHS Legislation, produce evidence of any Approvals including any authorisations, licences, prescribed qualifications or experience, or any other information relevant to work health and safety (as the case may be) to the satisfaction of the Contractor's Representative before the Subcontractor or any subsubcontractor commences such work;

take all reasonable actions and comply with all reasonable requests of the Contractor or its authorised persons regarding any safety audits in respect of the Site (including any audits under the Territory’s WHS Active Certification Policy);

without limiting paragraph (d), at all reasonable times allow the Territory, the Contractor, or their respective authorised persons:

to enter upon the Site to conduct a safety audit;

to enter upon the Site or any premises occupied by the Subcontractor to inspect and copy any records relevant to a safety audit; and

to enter upon the Site or any premises occupied by the Subcontractor to interview any person as part of a safety audit;

without limiting the Subcontractor's obligations under this Subcontract or at law, immediately notify the Contractor's Representative and the MCC Contract Administrator upon becoming aware of the issue of any improvement notice, infringement notice, non-disturbance notice, notice of entry or prohibition notice referable to the Site or the Works and provide copies of all referable notices and communications issued by a regulator or agent of the regulator to the Contractor's Representative and the MCC Contract Administrator immediately upon receiving the same;

without limiting the Subcontractor's obligations under this Subcontract or at law promptly notify the Contractor's Representative and the MCC Contract Administrator upon becoming aware of the issue of any provisional improvement notice referable to the Site or the Works and provide copies of all referable notices and communications issued by a regulator or agent of the regulator to the Contractor's Representative and the MCC Contract Administrator promptly upon receiving the same; and

subject to paragraph (b) and without limiting the Subcontractor's obligations under this Subcontract or at law, notify the Contractor's Representative promptly (and in any event within 12 hours of such matter arising) of all work, health and safety matters arising out of, or in any way in connection with, the Subcontractor’s Activities.

The Subcontractor must ensure that it and all its employees, subsubcontractors and suppliers comply with the WHS Management Plan of the appointed principal contractor of the Site as defined in the WHS Legislation, and all directions, notices and any other notifications issued for or on behalf of the principal contractor referable to work health and safety matters.

In this clause “regulator”, “improvement notice”, “infringement notice”, “non-disturbance notice”, “notice of entry”, “modifiable incident”, “prohibition notice” and “provisional Improvement notice” have the same meaning as in the WHS Legislation.

Plant, Equipment and Work

The Subcontractor must not remove from the Site any Plant, Equipment and Work without the Contractor's Representative's prior written approval except for the purpose of achieving Completion as contemplated under clause 8.19(b).

Cleaning Up

The Subcontractor must:

in carrying out the Subcontractor's Activities, keep the part of the Site used for the Subcontractor's Activities and the Subcontract Works clean and tidy and free of refuse; and

as a condition precedent to Completion of the Subcontract Works and each Stage, remove all rubbish, materials and Plant, Equipment and Work from the part of the Site relevant to the Subcontract Works or the Stage.

The Environment

The Subcontractor must:

ensure that in carrying out the Subcontractor's Activities:

other than to the extent identified in writing by the Contractor's Representative, it complies with all Statutory Requirements and other requirements of the Subcontract for the protection of the Environment;

it does not cause any Environmental Incident;

without limiting subparagraph (ii), it does not cause or contribute to Contamination of the Site or any other land, air or water, or cause or contribute to any Contamination emanating from the Site;

it immediately notifies the Contractor's Representative of:

any non-compliance with the requirements of this clause 8.20;

a breach of any Statutory Requirement for the protection of the Environment;

any Environmental Incident; or

the receipt of any notice, order or communication received from an authority for the protection of the Environment; and

its subsubcontractors comply with the requirements referred to in this clause 8.20; and

clean up and restore the Environment, including any Contamination or Environmental Harm, arising out of, or in any way in connection with, the Subcontractor's Activities, whether or not it has complied with all Statutory Requirements or other requirements of the Subcontract for the protection of the Environment.

Urgent Protection

The Contractor or the Territory may take any action necessary to protect the Subcontract Works, other property, the Environment, or to prevent or minimise risks to the health and safety of persons, which the Subcontractor must take but does not take.

Valuable Objects Found on Site

Any things of value or archaeological or special interest found on or in the Site will, as between the parties, be the property of the Contractor.

Where such an item is found the Subcontractor must:

immediately notify the Contractor's Representative;

protect it and not disturb it further; and

comply with any instructions of the Contractor's Representative in relation to the item.

The Subcontract Price will be increased by the extra costs reasonably incurred by the Subcontractor in complying with the Contractor's Representative's instructions, as determined by the Contractor's Representative.

The Contractor May Act

The Contractor may, either itself or by a third party, carry out an obligation under the Subcontract which the Subcontractor was obliged to carry out but which it failed to carry out within the time required in accordance with the Subcontract.

The costs, expenses and damages suffered or incurred by the Contractor in so carrying out such a Subcontractor obligation will be a debt due from the Subcontractor to the Contractor.

Access Hours

Unless otherwise agreed in writing between the Subcontractor and the Contractor's Representative, the hours of access applicable to the Subcontractor's Activities to be carried out on Site are those set out in the Subcontract Particulars.

Imported Items

Clause 8.25 does not apply unless the Subcontract Particulars state that it applies.

The Subcontract Price will be adjusted in respect of any imported item required for the Subcontract Works for which:

the Subcontractor submitted the information requested by the Contractor's Representative in its tender as to the potential for imported items to be subject to exchange rate fluctuations; and

there has been an exchange rate fluctuation between:

the rate submitted by the Subcontractor in its tender; and

the rate prevailing at the date upon which the Subcontractor stated in its tender it would pay for the imported item.

In these circumstances, the Subcontract Price will be adjusted by the difference in the cost of the imported item (in Australian dollars) calculated using the information submitted by the Subcontractor in its tender on the basis of:

the exchange rate submitted by the Subcontractor in its tender; and

the exchange rate prevailing at the date upon which the Subcontractor stated in its tender it proposed to pay for the imported item.

The exchange rate in paragraph (d) will be that quoted by the same bank from which the exchange rate in paragraph (c) was obtained.

Any imported items (whether subject to adjustment under this clause or not) will not be subject to adjustment for rise and fall in costs.

In this clause 8.25, a reference to tender means the tender submitted by the Subcontractor to the Contractor.

Salvaged Materials

Subject to clause 8.22, unless expressly stated to the contrary in the Subcontract or directed by the Contractor's Representative, all materials, plant, equipment, fixtures and other things salvaged from the Site or from the Subcontract Works are the property of the Subcontractor.

Project Signboards

If requested by the Contractor's Representative, the Subcontractor must provide the number of project signboards specified in the Subcontract Particulars, each of which must:

be in the dimensions specified in the Subcontract Particulars;

set out:

the name of the project;

the names of the parties to the Subcontract;

the name of the Contractor's Representative;

a general description of the Subcontract Works;

a contact name and phone number (including after hours number) for the principal contractor pursuant to the WHS Legislation;

a contact name and phone number for the Subcontractor;

the Date for Completion;

the location of the Site office (if any); and

any other information specified in the Subcontract Particulars.

The Subcontractor must, within 14 days of the commencement of the Subcontractor's Activities on Site, submit the proposed layout of the project signboards to the Contractor's Representative for approval.

Once approved by the Contractor's Representative, the Subcontractor must:

fix the project signboards in the locations directed by the Contractor's Representative;

maintain the project signboards until the last Date of Completion; and

dismantle and remove the project signboards within 7 days of the last Date of Completion.

Measurements and Dimensions

Without limiting clause 8.14:

the Subcontractor must obtain and check all relevant measurements and dimensions on Site before proceeding with the Subcontractor's Activities;

the layout of plant, equipment, ductwork, pipework and cabling shown in the Subcontract Works Description (if any) is to be taken as diagrammatic only and all measurements and dimension information concerning the Site required to carry out the Subcontractor's Activities must be obtained and checked by the Subcontractor; and

the Contractor will not be liable upon any Claim by the Subcontractor resulting from the Subcontractor's failure to obtain and check measurements and dimension information concerning the Site as required by this clause.

Territory's Actions

Under the Managing Contractor Contract:

the Territory may, either itself or by a third party, carry out an obligation under the Managing Contractor Contract which the Contractor was obliged to carry out but which it failed to carry out within the time required in accordance with the Managing Contractor Contract; and

the costs, expenses and damages suffered or incurred by the Territory in so carrying out such a Managing Contractor Contract obligation will be a debt due from the Contractor to the Territory.

The Subcontractor must indemnify the Contractor against any liability of the kind referred to in paragraph 8.28(b) to the extent that the liability arises out of or in any way in connection with an obligation under the Subcontract which the Subcontractor was obliged to carry out but which it failed to carry out within the time required in accordance with the Subcontract.

QUALITY

Construction

The Subcontractor must in carrying out the Subcontractor's Activities:

use workmanship:

of:

the standard prescribed in the Subcontract; or

to the extent it is not so prescribed, a standard consistent with the best industry standards for work of a nature similar to the Subcontract Works and which is at least to the same standard as that found in the development referred to in the Subcontract Particulars; and

which is fit for its purpose;

use materials:

which:

comply with the requirements of the Subcontract; or

if not fully described in the Subcontract, are new and consistent with the best industry standards for work of a nature similar to the Subcontract Works and which are at least to the same standard as those found in the development referred to in the Subcontract Particulars; and

of merchantable quality, which are fit for their purpose and consistent with the nature and character of the Subcontract Works; and

comply with the requirements of the Subcontract and, to the extent they are not inconsistent, the requirements of the MFPE, the Building Code of Australia and all relevant standards of Standards Australia.

Project Plans

The Subcontractor:

must carry out the Subcontractor's Activities in accordance with, and otherwise implement, the Project Plans; and

for the purposes of subparagraph (i), must:

prepare draft Project Plans based on the outline approach to preparing the Project Plans, and performing the Subcontractor's Activities to be covered by the Project Plans, submitted by the Subcontractor in its tender for the Subcontractor's Activities and otherwise in accordance with the requirements of the Subcontract and submit them to the Contractor's Representative so as to ensure that there is no delay or disruption to the Subcontractor's Activities and in any event no later than the number of days set out in the Subcontract Particulars after the Award Date for each Project Plan;

not commence any of the Subcontractor's Activities to which any Project Plan applies, unless the Contractor's Representative has had the number of days set out in the Subcontract Particulars to review the draft Project Plans and has not rejected them;

if any draft Project Plan is rejected, submit an amended draft of the Project Plan to the Contractor's Representative;

in any event, finalise each Project Plan so as to ensure that there is no delay or disruption to the Subcontractor's Activities and in any event in accordance with the requirements of the Subcontract to the satisfaction of the Contractor's Representative;

after the Project Plans have been finalised, continue to correct any defects in or omissions from a Project Plan (whether identified by the Contractor's Representative or the Subcontractor) and submit an amended draft of the Project Plan to the Contractor's Representative, after which:

the Subcontractor must continue to comply with the requirements of the then current Project Plan until the process in subparagraph (ii) has been completed in respect of the amended draft Project Plan; and

subsubparagraphs B - D will apply (to the extent applicable); and

document and maintain detailed records of inspections or audits undertaken as part of any Project Plan.

The Subcontractor will not be relieved from compliance with any of its Subcontract obligations or from any of its liabilities whether under the Subcontract or otherwise according to law as a result of:

the implementation of, and compliance with, the requirements of any Project Plan;

any direction by the Contractor's Representative concerning a Project Plan or the Subcontractor's  compliance or non-compliance with a Project Plan;

any audit or other monitoring by the Contractor's Representative of the Subcontractor's compliance with a Project Plan; or

any failure by the Contractor's Representative, or anyone else acting on behalf of the Contractor, to detect any defect in or omission from a Project Plan including where any such failure arises from any negligence on the part of the Contractor's Representative or other person.

Contractor's Representative's Right to Inspect

The Contractor's Representative may at any time inspect the Subcontractor's Activities.

The Subcontractor however acknowledges that:

the Contractor's Representative owes no duty to the Subcontractor to:

inspect the Subcontractor's Activities; or

review construction for errors, omissions or compliance with the requirements of this Subcontract if it does so inspect; and

no inspection of the Subcontractor's Activities or review of construction by the Contractor's Representative will in any way lessen or otherwise affect:

the Subcontractor's obligations whether under this Subcontract or otherwise according to law; or

the Contractor's rights against the Subcontractor whether under this Subcontract or otherwise according to law.

Testing

The Subcontractor must carry out all tests required by the Subcontract or directed by the Contractor's Representative.

All tests are to be carried out in accordance with any procedure:

set out in the Subcontract which may apply to the tests; or

if no procedure exists, as reasonably directed by the Contractor's Representative.

Costs of Testing

If:

the Contractor's Representative directs the Subcontractor to carry out a test which:

is not otherwise required by the Subcontract; or

does not relate to a Defect in respect of which the Contractor's Representative gave an instruction under clause 9.6; and

the results of the test show the work is in accordance with the Subcontract,

the reasonable costs incurred by the Subcontractor in carrying out the test will be determined by the Contractor's Representative and added to the Subcontract Price.

Defects

Subject to paragraphs (b) and (c), the Subcontractor must correct all Defects.

If, prior to the expiration of the Defects Liability Period for the Subcontract Works or a Stage, the Contractor's Representative discovers or believes there is a Defect, the Contractor's Representative may give the Subcontractor an instruction specifying the Defect and doing one or more of the following:

requiring the Subcontractor to correct the Defect, or any part of it, and specifying the time within which this must occur;

subject to the Contractor having first complied with clause 8.11 of the Managing Contractor Contract,  requiring the Subcontractor to carry out a Variation to overcome the Defect, or any part of it, and specifying the time within which this must be carried out; or

advising the Subcontractor that the Contractor will accept the work, or any part of it, despite the Defect.

Correction of Defect or Variation

If an instruction is given under clause 9.6(a) or (b), the Subcontractor must correct the Defect or carry out the Variation:

within the time specified in the Contractor's Representative's instruction; and

if after Completion, at times and in a manner which cause as little inconvenience to the occupants of the Subcontract Works or the Stage as is reasonably possible.

Claim for Correction of Defect

Where an instruction is given under clause 9.6(a):

the Subcontractor will only be entitled to make a Claim for correcting the Defect (or the relevant part) if the Defect (or the relevant part) is something for which the Subcontractor is not responsible; and

where the Subcontractor is so entitled to make a Claim, the work involved in the correction of the Defect will be treated as if it were a Variation the subject of a direction by the Contractor's Representative and clause 11.3 applied.

Claim for Variation

Where a Variation has been instructed under clause 9.6(b) and:

the Subcontractor is not responsible for the Defect (or the relevant part):

the Subcontract Price will be adjusted in accordance with clause 11.3; and

the Subcontractor will be entitled to an extension of time to any relevant Date for Completion where it is otherwise so entitled under clause 10.7; or

the Subcontractor is responsible for the Defect (or the relevant part):

the Contractor's Representative will determine:

the value of the Variation in accordance with clause 11.3; and

the cost of correcting the Defect (or the relevant part) as if clause 9.8(b) applied;

the Subcontract Price will be adjusted by the difference between the valuations under subparagraph (i) as follows:

if the value under subparagraph (i)A is greater than the cost under subparagraph (i)B, the Subcontract Price will be increased by the excess; or

if the value under subparagraph (i)B is greater than the cost under subparagraph (i)A, the Subcontract Price will be decreased by the difference and will be a debt due from the Subcontractor to the Contractor; and

the Subcontractor may not claim an extension of time to any Date for Completion.

Acceptance of Work

If:

an instruction is given under clause 9.6(c) prior to the expiration of the Defects Liability Period; and

the Subcontractor is responsible for the Defect (or the relevant part),

the amount determined by the Contractor's Representative which represents the cost of correcting the Defect (or the relevant part) will be a debt due from the Subcontractor to the Contractor.

Extension of Defects Liability Period

If:

the Contractor's Representative gives the Subcontractor an instruction under clause 9.6(a) or (b) during the Defects Liability Period; and

the Subcontractor is responsible for the Defect (or the relevant part),

the Defects Liability Period will be extended for the work required by the instruction by the period set out in the Subcontract Particulars, commencing upon completion of the correction of the Defect (or the relevant part) or completion of the Variation.

Common Law Rights not Affected

Neither the Contractor's rights, nor the Subcontractor's liability, whether under the Subcontract or otherwise according to law in respect of Defects, whether before or after the expiration of the Defects Liability Period, will be affected or limited by:

the rights conferred upon the Contractor or Contractor's Representative by this clause 9 or any other provision of the Subcontract;

the failure by the Contractor or the Contractor's Representative to exercise any such rights; or

any instruction of the Contractor's Representative under clause 9.6.

Commissioning and Handover

Without limiting clause 8.17(a)(iii) or the Subcontractor's obligations or liabilities, or the Contractor's or the Contractor's Representative's rights under clause 13, the Subcontractor must:

fully co-operate with Other Contractors and otherwise to take all steps necessary to ensure:

the timely, efficient and comprehensive commissioning of the Subcontract Works; and

the smooth handover of the Subcontract Works to the Contractor and the initial occupation of the Subcontract Works by the Territory;

without limiting paragraph (a):

comply with the:

Commissioning and Handover Plan; and

Commissioning, Handover and Takeover Guidelines; and

in consultation with the Contractor's Representative, provide the Contractor with such other specific assistance as may be required by the Contractor's Representative to facilitate the timely, efficient and comprehensive commissioning of the Subcontract Works and the smooth handover of the Subcontract Works to the Contractor and the initial occupation of the Subcontract Works by the Territory;

as a condition precedent to Completion, hand to the Contractor's Representative, Other Contractor or other person nominated by the Contractor's Representative all Project Documents which are required for the use, operation and maintenance of the Subcontract Works or the relevant Stage; and

as and when reasonably required by the Contractor's Representative, meet with the Contractor's Representative, and such Other Contractors or other persons as are nominated by the Contractor's Representative with a view to ensuring that the Territory, the Contractor, and the Other Contractors or other persons have sufficient information to enable the Territory, the nominated Other Contractors or other persons to:

operate the Subcontract Works;

maintain the Subcontract Works; or

perform such other activities as may be required by the Contractor or the Territory in respect of the Subcontract Works.

Maintenance during Defects Liability Period

To the extent set out in the Subcontract Particulars, the Subcontractor must ensure that during the Defects Liability Period for the Subcontract Works or each Stage such planned and unplanned maintenance is carried out:

as required by the Commissioning and Handover Plan; and

as is otherwise necessary to ensure that the Subcontract Works are, or each Stage is, throughout and at the end of the Defects Liability Period in a condition fit for their intended purpose.

Defects Liability Period Review and Report

Without limiting clause 9.6, the Subcontractor must maintain adequate records of all calls, attendances, recommendations and actions taken in respect of all Defects during the Defects Liability Period.

Within 14 days of the end of the Defects Liability Period for the Subcontract Works or a Stage, the Subcontractor must provide a report to the Contractor's Representative in a form satisfactory to the Contractor's Representative which sets out:

adequate records of all calls, attendances, recommendations and actions taken in respect of all Defects;

recommendations for the future maintenance of the Subcontract Works;

any matters in respect of work health and safety issues; and

any other matters specified in the Subcontract Particulars or required by the Contractor's Representative.

TIME

Progress and Time for Completion

The Subcontractor must:

regularly and diligently progress the Subcontractor's Activities; and

achieve Completion of the Subcontract Works or each Stage by the relevant Date for Completion.

Programming

The Contractor must:

on the Award Date, provide the Subcontractor with a copy of the Contractor's Program insofar as it is relevant to the Subcontractor's Activities; and

thereafter, promptly provide the Subcontractor with a copy of amendments to the Contractor's Program insofar as they are relevant to the Subcontractor's Activities.

The Subcontractor must:

within 14 days of the Award Date prepare a program of the Subcontractor's Activities which is consistent with the Contractor's Program and must contain the details required by the Subcontract or which the Contractor's Representative otherwise reasonably directs;

update the program periodically at least at intervals of no less than that specified in the Subcontract Particulars to take account of:

changes to the program and the Contractor's Program; or

delays which may have occurred, including any for which the Subcontractor is granted an extension of time under clause 10.8;

give the Contractor's Representative copies of all programs for approval;

ensure that the subsubcontractors adhere to the program; and

provide all programs in a format compatible with the software described in the Subcontract Particulars.

Subcontractor Not Relieved

Any review of, comments upon or approval of, or any failure to review or comment upon, a program by the Contractor's Representative will not:

relieve the Subcontractor from or alter its liabilities or obligations under the Subcontract, especially (without limitation) the obligation to achieve Completion by each Date for Completion;

evidence or constitute the granting of an extension of time or an instruction by the Contractor's Representative to accelerate, disrupt, prolong or vary any or all of the Subcontractor's Activities; or

affect the time for the carrying out of the Contractor's or Contractor's Representative's Subcontract  obligations.

Acceleration by Subcontractor

If the Subcontractor chooses to accelerate progress then despite clause 3.3:

neither the Contractor nor the Contractor's Representative will be obliged to take any action to assist or enable the Subcontractor to achieve Completion before any Date for Completion; and

the time for the carrying out of the Contractor's or the Contractor's Representative's obligations will not be affected.

Delays Entitling Claim

If the Subcontractor is, or is likely to be, delayed:

prior to the Date for Completion of the Subcontract Works or a Stage, by an Act of Prevention or a cause described in the Subcontract Particulars in a manner which will prevent it from achieving Completion of the Subcontract Works or the Stage by the relevant Date for Completion; or

after the Date for Completion of the Subcontract Works or a Stage, by an Act of Prevention in a manner which will delay it in achieving Completion of the Subcontract Works or the Stage,

the Subcontractor may claim an extension of time.

Claim

To claim an extension of time the Subcontractor must:

within 14 days of the commencement of the occurrence causing the delay submit a written claim to the Contractor's Representative for an extension to the relevant Date for Completion which:

gives detailed particulars of the delay and the occurrence causing the delay; and

states the number of days extension of time claimed together with the basis of calculating that period, including evidence that it will be delayed in achieving Completion in the manner set out in clause 10.7(c); and

if the effects of the delay continue beyond the period of 14 days after the commencement of the occurrence causing the delay and the Subcontractor wishes to claim an extension of time in respect of the further delay, submit a further written claim to the Contractor's Representative:

every 14 days after the first written claim until 7 days after the end of the effects of the delay; and

containing the information required by paragraph (a).

Conditions Precedent to Extension

Subject to clause 10.14, it is a condition precedent to the Subcontractor's entitlement to an extension of time that:

the Subcontractor must give the written claim required by clause 10.6 as required by that clause;

the cause of the delay was beyond the reasonable control of the Subcontractor;

the Subcontractor must have actually been, or be likely to be, delayed by:

prior to the Date for Completion of the Subcontract Works or the Stage, an Act of Prevention or a cause described in the Subcontract Particulars in a manner which will prevent it from achieving Completion of the Subcontract Works or the Stage by the relevant Date for Completion unless that date is extended; or

after the Date for Completion of the Subcontract Works or the Stage, an Act of Prevention in a manner which will delay it in achieving Completion of the Subcontract Works or the Stage;

the Subcontractor must not have been given an instruction under clause 10.13; and

the Contractor is entitled to grant the extension of time under clause 10.6 of the Managing Contractor Contract.

Extension of Time

Subject to clause 10.9, if the conditions precedent in clause 10.7 have been satisfied, the relevant Date for Completion will be extended by (subject to paragraph (b)) a reasonable period determined by the Contractor's Representative and notified to the Subcontractor within 21 days of the Subcontractor's written claim under clause 10.6.

The period determined by the Contractor's Representative under this clause 10.8 cannot exceed the period approved by the MCC Contract Administrator under clause 10.6 of the Managing Contractor Contract.

Reduction in Extension of Time

The Contractor's Representative will reduce any extension to the relevant Date for Completion it would otherwise have notified to the Subcontractor under clause 10.8 to the extent that the Subcontractor:

contributed to the delay; or

failed to take all steps necessary both to preclude the cause of the delay and to avoid or minimise the consequences of the delay.

Unilateral Extensions

Whether or not the Subcontractor has made, or is entitled to make, a claim for an extension of time under this clause 10, the Contractor's Representative may, in the Contractor's Representative's absolute discretion  (subject to clause 10.6 of the Managing Contractor Contract) at any time and from time to time by written notice to the Subcontractor and the Contractor, unilaterally extend any Date for Completion.

The parties acknowledge that:

the Contractor's Representative is not required to exercise the Contractor's Representative's discretion under this clause 10.10 for the benefit of the Subcontractor;

this clause 10.10 does not give the Subcontractor any rights; and

the exercise or failure to exercise the Contractor's Representative's discretion under this clause 10.10 is not capable of being the subject of a dispute or difference for the purposes of clause 15.1 or otherwise subject to review.

Agreed Damages

This clause 10.11 applies unless the Subcontract Particulars state that it does not apply.

The Subcontractor will be entitled to be paid the amount in the Subcontract Particulars for each day by which the Date for Completion of the Subcontract Works or a Stage is extended due to a breach of the Subcontract by the Contractor.

This amount:

is the agreed damages which will be payable by the Contractor in these circumstances; and

will be a limitation upon the Contractor's liability to the Subcontractor for any delay or disruption which:

the Subcontractor encounters in carrying out the Subcontractor's Activities; and

arises out of, or in any way in connection with, the breach of the Subcontract by the Contractor,

and the Subcontractor will not be entitled to make, nor will the Contractor be liable upon, any Claim in these circumstances other than for the amount which is payable by the Contractor under this clause 10.11.

Suspension

The Contractor's Representative:

may (subject to the Contractor having first complied with clause 8.11 of the Managing Contractor Contract) instruct the Subcontractor to suspend and, after a suspension has been instructed, to re-commence, the carrying out of all or a part of the Subcontractor's Activities; and

is not required to exercise the Contractor's Representative's power under subparagraph (i) for the benefit of the Subcontractor.

If a suspension under this clause 10.12 arises as a result of:

the Subcontractor's failure to carry out its obligations in accordance with the Subcontract, the Subcontractor will not be entitled to make any Claim against the Contractor arising out of, or in any way in connection with, the suspension; or

a cause other than the Subcontractor's failure to carry out its obligations in accordance with the Subcontract:

an instruction to suspend under this clause 10.12 will entitle the Subcontractor to:

be paid by the Contractor the extra costs reasonably incurred by it as a result of the suspension as determined by the Contractor's Representative; and

an extension of time to any relevant Date for Completion where it is otherwise so entitled under clause 10.7;

the Subcontractor must take all steps possible to mitigate the extra costs incurred by it as a result of the suspension; and

the Subcontractor will not be entitled to make any Claim against the Contractor arising out of, or in any way in connection with, the suspension other than under this subparagraph (ii).

Except to the extent permitted by the relevant Security of Payment Legislation, the Subcontractor may only suspend the Subcontractor's Activities when instructed to do so under this clause 10.12.

Instruction to Accelerate

If the Subcontractor gives the Contractor's Representative a claim under clause 10.6, the Contractor's Representative may (subject to the Contractor having first complied with clause 8.11 of the Managing Contractor Contract):

instruct the Subcontractor to accelerate the Subcontractor's Activities by taking those measures which are necessary to overcome or minimise the extent and effects of some or all of the delay including, if required, in order to achieve Completion of the Subcontract Works or the Stage by the relevant Date for Completion; and

give such an instruction whether or not the cause of delay for which the Subcontractor has given its claim under clause 10.6 otherwise entitles the Subcontractor to an extension of time to any relevant Date for Completion.

Partial Acceleration

If the Contractor's Representative gives the Subcontractor an instruction to accelerate under clause 10.13 requiring it to accelerate the Subcontractor's Activities and it only applies to part of the delay, the Subcontractor's entitlement to any extension of time which it otherwise would have had will only be reduced to the extent to which the instruction to accelerate requires the Subcontractor to accelerate to overcome the delay.

Acceleration

If the Contractor's Representative gives an instruction to the Subcontractor under clause 10.13:

the Subcontractor must accelerate the Subcontractor's Activities to overcome or minimise the extent and effect of some or all of the delay as instructed, including, if required, in order to achieve Completion of the Subcontract Works or the Stage by the relevant Date for Completion;

if the Subcontractor would, but for the instruction, have been entitled to an extension of time to the relevant Date for Completion for the cause of delay, the Subcontractor will be entitled to be paid:

the extra costs reasonably incurred by it and directly attributable to accelerating the Subcontractor's Activities; and

that percentage of the amount under subparagraph (i) stipulated in the Subcontract Particulars; and

subject to clause 10.14, the Subcontractor will not be entitled to make any Claim against the Contractor, arising out of, or in any way in connection with, the cause of delay and the instruction other than for the amount which is payable by the Contractor under this clause 10.15.

Contractor's Rights to Liquidated Damages Not Affected

The Contractor's rights to:

liquidated damages under clause 13.7; or

be indemnified under clause 13.8,

for a failure by the Subcontractor to achieve Completion of the Subcontract Works or a Stage by any relevant Date for Completion are not affected by the Contractor's Representative giving the Subcontractor an instruction to accelerate under clause 10.13.

VARIATIONS

Variation Price Request

At any time prior to the Date of Completion of the Subcontract Works or a Stage (but without limiting clauses 5.3 and 9.6), the Contractor's Representative may (subject to the Contractor having complied with clause 8.11 of the Managing Contractor Contract) issue a document titled "Variation Price Request" to the Subcontractor which will set out details of a proposed Variation which the Contractor is considering with respect to the Subcontract Works or a Stage.

The Subcontractor must immediately take all action required under any relevant subsubcontract in relation to each subsubcontractor that would be involved in carrying out the proposed Variation.

Within 14 days of the receipt of a "Variation Price Request" the Subcontractor must provide the Contractor's Representative with a written notice in which the Subcontractor sets out:

the adjustment (if any) to the Subcontract Price to carry out the proposed Variation; and

the effect (if any) which the proposed Variation will have on the then approved program, including each Date for Completion.

Variation Order

Whether or not the Contractor's Representative has issued a "Variation Price Request" under clause 11.1, the Contractor's Representative may (subject to the Contractor having complied with clause 8.11 of the Managing Contractor Contract) at any time prior to the Date of Completion of the Subcontract Works or a Stage (but without limiting clauses 5.3 and 9.6), instruct the Subcontractor to carry out a Variation by a written document titled "Variation Order" in which the Contractor's Representative will state one of the following:

the proposed adjustment to the Subcontract Price as set out in the Subcontractor's notice under clause 11.1 (if any) is agreed and the Subcontract Price will be adjusted accordingly;

any adjustment to the Subcontract Price will be determined under clauses 11.3(b) and 11.3(c); or

the Variation is to be carried out as daywork and any adjustment to the Subcontract Price will be determined under clause 11.3(d).

No Variation will invalidate the Subcontract irrespective of the nature, extent or value of the work the subject of the Variation.

Cost of Variation

Subject to clauses 9.9(b) and 11.9, the Subcontract Price will be increased or decreased for all Variations which have been the subject of a direction by the Contractor's Representative:

as agreed under clause 11.2(a);

if paragraph (a) does not apply, in accordance with the rates or prices included in the Table of Variation Rates and Prices, if and insofar as the Contractor's Representative determines that those rates or prices are applicable to or it is reasonable to use them for valuing, the Variation, to which will be added:

the following percentage or percentages of the amount determined:

where the adjustment to the Subcontract Price is to be an increase, those percentages specified in the Subcontract Particulars for non-time related on-site overheads and preliminaries and off-site overheads and profit; or

where the adjustment to the Subcontract Price is to be a decrease, the percentage specified in the Subcontract Particulars for off-site overheads and profit; and

any reasonable costs and expenses incurred by the Subcontractor arising from the Variation delaying the Subcontractor;

to the extent paragraph (b) does not apply, by a reasonable amount:

to be agreed between the parties; or

failing agreement, determined by the Contractor's Representative,

to which will be added:

the following percentage or percentages of the amount determined:

where the adjustment to the Subcontract Price is to be an increase, those percentages specified in the Subcontract Particulars for non-time related on-site overheads and preliminaries and off-site overheads and profit; or

where the adjustment to the Subcontract Price is to be a decrease, the percentage specified in the Subcontract Particulars for off-site overheads and profit; and

any reasonable costs and expenses incurred by the Subcontractor arising from the Variation delaying the Subcontractor; or

by the amount determined by the Contractor's Representative under clause 11.6.

Omissions

If a Variation the subject of a direction by the Contractor's Representative omits any part of the Subcontract Works or a Stage, the Contractor may thereafter carry out this omitted work either itself or by engaging Other Contractors.

Daywork

If the Subcontractor is given an instruction under clause 11.2(c) or clause 12.19(d) to carry out work as daywork, the Subcontractor must:

carry out the daywork in an efficient manner; and

after the instruction, each day provide the Contractor's Representative with a written report signed by the Subcontractor which:

records particulars of all resources used by the Subcontractor for the execution of the daywork; and

includes the particulars and copies of time sheets, wages sheets, invoices, receipts and other documents evidencing the cost of the daywork.

The Contractor's Representative may direct the manner in which matters are to be recorded.

Valuation of Daywork

In determining the value of work which the Contractor's Representative instructed was to be carried out as daywork, the Contractor's Representative will have regard to:

the amount of wages and allowances paid or payable by the Subcontractor at:

the rates pertaining at the Site at the time as established by the Subcontractor to the reasonable satisfaction of the Contractor's Representative; or

other reasonable rates approved by the Contractor's Representative;

the percentage stated in the Subcontract Particulars of the wages paid or payable under paragraph (a);

the amount of hire charges in respect of plant approved by the Contractor's Representative for use on the work in accordance with the hiring rates and conditions:

agreed between the Contractor's Representative and the Subcontractor; or

failing agreement, reasonably determined by the Contractor's Representative;

the reasonable amounts paid for services, subcontracts and professional fees; and

the actual cost to the Subcontractor at the Site of all materials supplied and required for the work,

to which will be added:

the percentages of the amounts determined under paragraphs (a) - (e) specified in the Subcontract Particulars for non-time related on-site overheads and preliminaries and off-site overheads and profit; and

any reasonable costs and expenses incurred by the Subcontractor arising from the Variation delaying the Subcontractor.

Variations Requested by Subcontractor

The Subcontractor may, for its convenience, request the Contractor's Representative to direct a Variation.  Any such request must be in writing and must contain the following details:

a description of the Variation;

the additional or reduced costs or time involved in the Variation and any proposal for sharing any savings in costs with the Contractor including the amount;

any benefits which will flow to the Territory from the Variation; and

the effect which the Variation will have upon the future cost of operating and maintaining the Subcontract Works.

Contractor's Representative's Determination

After a request is made by the Subcontractor in accordance with clause 11.7, the Contractor's Representative will, in the Contractor's Representative's absolute discretion, give a written notice to the Subcontractor:

rejecting the request; or

(subject to the Contractor having complied with clause 8.11 of the Managing Contractor Contract) approving the request either conditionally or unconditionally.

The Contractor's Representative will not be obliged to exercise the Contractor's Representative's discretion for the benefit of the Subcontractor.

Variation Approved by Contractor's Representative

If the Contractor's Representative issues a written notice under clause 11.8 approving the Subcontractor's request under clause 11.7:

unless otherwise agreed, the Subcontractor will not be entitled to make a Claim against the Contractor  arising out of, or in any way in connection with, the Variation;

if the Subcontractor's request offered to share savings in cost with the Contractor, the Subcontract Price will be reduced by or adjusted in accordance with the Subcontractor's offer; and

the Subcontractor will be responsible for all parts of the Subcontract Works which are in any way affected by the Variation.

Managing Contractor Contract Variation

Where:

a Variation the subject of a direction by the Contractor's Representative arises out of, or in any way in connection with, a Variation under the Managing Contractor Contract; or

any work which is otherwise to be treated and valued as a Variation under clause 11.3 is work,

which the Contractor is required to carry out under the terms of the Managing Contractor Contract (whether itself or through the Subcontractor) and for which the Contractor:

is entitled to additional payment under the Managing Contractor Contract; or

would otherwise have been entitled to additional payment under the Managing Contractor Contract had it done everything required under the Managing Contractor Contract to preserve its entitlement,

then any increase in the Subcontract Price under clause 11.3 will be limited to the extent to which (as the case may be) the amount of:

the Contractor’s entitlement; or

the entitlement the Contractor would otherwise have had,

to additional payment, is attributable to the Subcontractor's Activities relevant to the Variation or work (as the case may be) less any amount attributable to (and payable directly to the Contractor under the Managing Contractor Contract on account of) the Contractor’s non-time related on-site overheads and preliminaries, off-site overheads and profit and delay costs relating to the Variation or work (as the case may be).

PAYMENT

Payment Obligation

Subject to clause 12.15 and to any other right to set-off which the Contractor may have, the Contractor will pay the Subcontractor:

the Subcontract Price; and

any other amounts which are payable by the Contractor to the Subcontractor under the Subcontract.

Payment Claims

Subject to clause 12.3, the Subcontractor must give the Contractor's Representative claims for payment on account of the Subcontract Price and all other amounts then payable by the Contractor to the Subcontractor under the Subcontract:

at the times stated in the Subcontract Particulars until Completion or termination of the Subcontract (whichever is earlier);

unless terminated earlier, after Completion or the Defects Liability Period (as the case may be), within the time required by clause 12.9 or 12.11 (as the case may be);

in the format set out in the Schedule of Collateral Documents or in any other format which the Contractor's Representative reasonably requires;

which are based on the Table of Variation Rates and Prices or the Schedule of Rates to the extent these are relevant;

which show separately the amounts (if any) claimed on account of:

the Subcontract Price; and

all other amounts then payable by the Contractor to the Subcontractor under the Subcontract; and

which set out or attach sufficient details, calculations, supporting documentation and other information in respect of all amounts claimed by the Subcontractor:

to enable the Contractor's Representative to fully and accurately determine (without needing to refer to any other documentation or information) the amounts then payable by the Contractor to the Subcontractor under the Subcontract; and

including any such documentation or information which the Contractor's Representative may by written notice from time to time require the Subcontractor to set out or attach, whether in relation to a specific payment claim or all payment claims generally.

Conditions Precedent

The Subcontractor's entitlement to submit a payment claim under clause 12.2 is conditional upon the Subcontractor having:

provided the Contractor with Approved Security for the amount (if any) required under clause 4.1 and any related company guarantee required under clause 4.4;

obtained the insurance required by clause 5.5 and (if requested) provided evidence of this to the Contractor's Representative;

complied with its programming obligations under clause 10.2;

complied with clause 12.16;

complied with clause 12.22;

complied with clause 12.23;

provided the Contractor's Representative with duly executed copies of:

any Subsubcontractor Deed of Covenant or Consultant Deed of Covenant (as the case may be) that the Subcontractor is required to obtain under the Subcontract; and

the certificates (if any) required under clause 6.13;

if clause 14.5(b), 14.8(b)(ii), or 14.10(b)(ii) applies - complied with clause 14.5(b), 14.8(b)(ii) or 14.10(b)(ii) (as the case may be); and

provided all relevant information as required under the WHS Legislation or under this Subcontract arising out of or in connection with work health and safety.

If the Subcontractor has not satisfied the conditions in paragraph (a) at the time of submitting a payment claim, then:

the payment claim is deemed to have been invalidly submitted under clause 12.2;

the Contractor's Representative will not be obliged to include in any payment statement under clause 12.4 any amount included in the payment claim; and

the Contractor will not be liable to pay any amount included in the payment claim.

If the Subcontractor:

submits a payment claim; and

has failed to comply with the requirements of clause 12.2(f) in relation to any amount (or portion of any amount) claimed in the payment claim,

then:

the Subcontractor will not be entitled to payment of;

the Contractor's Representative will not be obliged to include in any payment statement under clause 12.4; and

the Contractor will not be liable to pay,

the amount (or the portion of the amount) claimed in the payment claim in relation to which the Subcontractor has failed to comply with the requirements of clause 12.2(f), unless:

the Contractor's Representative (in its absolute discretion and without being under any obligation to exercise this discretion for the benefit of the  Subcontractor) issues a written notice to the  Subcontractor identifying the documentation or information which the Subcontractor has failed to provide under clause 12.2(f); and

the Subcontractor provides that documentation or information to the Contractor's Representative within the time required in the Contractor's Representative's notice.

Payment Statements

The Contractor's Representative:

must, within 10 business days of receiving a payment claim submitted or purported to be submitted in accordance with clause 12.2; or

may, if the Subcontractor fails to submit any such claim in accordance with clause 12.2, at any time,

give the Subcontractor (with a copy to the Contractor), on behalf of the Contractor, a payment statement which is in the form set out in the Schedule of Collateral Documents (if any) and which states:

the payment claim to which it relates (if any);

the Subcontractor's total value of entitlement to payment under the Subcontract;

the amount already paid to the Subcontractor;

the amount (if any) which the Contractor's Representative believes to be then payable by the Contractor to the Subcontractor on account of the Subcontract Price and otherwise in accordance with the Subcontract, and which the Contractor proposes to pay to the Subcontractor; and

if the amount in paragraph (f) is less than the amount claimed in the payment claim:

the reason why the amount in paragraph (f) is less than the amount claimed in the payment claim; and

if the reason for the difference is that the Contractor has retained, deducted, withheld or set-off payment for any reason, the reason for the retention, deduction, withholding or setting-off.

Any evaluation, or issue of a payment statement, by the Contractor's Representative will not:

constitute approval of any work nor will it be taken as an admission or evidence that the part of the Subcontract Works covered by the payment statement has been satisfactorily carried out in accordance with the Subcontract; or

constitute a waiver of the requirements of clauses 12.2 and 12.3 in relation to any payment claim other than to the extent (if any) to which the Contractor expressly waives such requirements in respect of the payment claim the subject of the payment statement.

Payment

Within the number of business days stated in the Subcontract Particulars of the Contractor receiving a payment statement under clause 12.4, the Contractor will pay the Subcontractor the amounts set out as then payable in the payment statement.

Payment on Account

Any payment of moneys under clause 12.5 is not:

evidence of the value of work or that work has been satisfactorily carried out in accordance with the Subcontract;

an admission of liability; or

approval by the Contractor or the Contractor's Representative of the Subcontractor's performance or compliance with the Subcontract,

but is only to be taken as payment on account.

Unfixed Goods and Materials

Unfixed goods or materials will not be included in the value of work in a payment statement under clause 12.4 unless:

the Contractor's Representative is satisfied that the unfixed goods and materials have not been prematurely ordered and are necessary to enable the Subcontractor to comply with its obligations under the Subcontract;

the Subcontractor gives the Contractor's Representative with its payment claim under clause 12.2:

additional Approved Security equal to the payment claimed for the unfixed goods and materials; and

such evidence as may be required by the Contractor's Representative that title to the unfixed goods and materials will vest in the Territory upon payment by the Territory to the Contractor under the Managing Contractor Contract in respect of the unfixed goods and materials;

the unfixed goods and materials are clearly marked as the property of the Territory and are on the Site or available for immediate delivery to the Site; and

the unfixed goods and materials are properly stored in a place approved by the Contractor's Representative.

Upon payment by the Territory to the Contractor under the Managing Contractor Contract in respect of a payment schedule which includes unfixed goods and materials, title in the unfixed goods and materials will vest in the Territory.

Release of Additional Approved Security

If the Subcontractor has given the Contractor additional Approved Security for payment for unfixed goods and materials, the Contractor must release it to the Subcontractor once those goods and materials are incorporated into the Subcontract Works.

Completion Payment Claim and Notice

Within 28 days (or such longer period agreed in writing by the Contractor's Representative) after the issue of a Notice of Completion for the Subcontract Works or a Stage, the Subcontractor must give the Contractor's Representative:

a payment claim which complies with clause 12.2 and which must include all amounts which the Subcontractor claims from the Contractor on account of all amounts payable under the Subcontract; and

notice of any other amounts which the Subcontractor claims from the Contractor,

in respect of any fact, matter or thing arising out of, or in any way in connection with, the Subcontractor's Activities or the Subcontract which:

in the case of the Subcontract Works, occurred prior to the Date of Completion of the Subcontract Works; or

in the case of a Stage, occurred prior to the Date of Completion of the Stage, insofar as the fact, matter or thing relates to the Stage.

The payment claim and notice required under this clause 12.9 are in addition to the other notices which the Subcontractor must give to the Contractor's Representative under the Subcontract in order to preserve its entitlements to make any such Claims.

Without limiting the previous paragraph, the Subcontractor cannot include in this payment claim or notice any Claims which are barred by clause 16.5.

Release after Completion Payment Claim and Notice

After the date for submitting the payment claim and notice under clause 12.9 has passed, the Subcontractor releases the Contractor from any Claim in respect of any fact, matter or thing arising out of, or in any way in connection with, the Subcontractor's Activities or the Subcontract which:

in the case of the Subcontract Works, occurred prior to the Date of Completion of the Subcontract Works; or

in the case of a Stage, occurred prior to the Date of Completion of the Stage, insofar as the fact, matter or thing relates to the Stage,

except for any Claim included in a payment claim or notice under clause 12.9 which is given to the Contractor's Representative within the time required by, and in accordance with the terms of, clause 12.9.

Final Payment Claim and Notice

Within 28 days (or such longer period agreed in writing by the Contractor's Representative) after the end of the Defects Liability Period for the Subcontract Works or a Stage, the Subcontractor must give the Contractor's Representative:

a payment claim which complies with clause 12.2 and which must include all amounts which the Subcontractor claims from the Contractor on account of all amounts payable under the Subcontract; and

notice of any other amounts which the Subcontractor claims from the Contractor,

in respect of any fact, matter or thing arising out of, or in any way in connection with, the Subcontractor's Activities or the Subcontract which:

in the case of the Subcontract Works, occurred during the Defects Liability Period for the Subcontract Works; or

in the case of a Stage, occurred during the Defects Liability Period for the Stage, insofar as the fact, matter or thing relates to the Stage.

The payment claim and notice required under this clause 12.11 are in addition to the other notices which the Subcontractor must give to the Contractor's Representative under the Subcontract in order to preserve its entitlements to make any such Claims.

Without limiting the previous paragraph, the Subcontractor cannot include in this payment claim or notice any Claims which are barred by clause 16.5.

Release after Final Payment Claim and Notice

After the date for submitting the payment claim and notice under clause 12.11 has passed, the Subcontractor releases the Contractor from any Claim in respect of any fact, matter or thing arising out of, or in any way in connection with, the Subcontractor's Activities or the Subcontract which:

in the case of the Subcontract Works, occurred during the Defects Liability Period for the Subcontract Works; or

in the case of a Stage, occurred during the Defects Liability Period for the Stage, insofar as the fact, matter or thing relates to the Stage,

except for any Claim included in a payment claim or notice under clause 12.11 which is given to the Contractor's Representative within the time required by, and in accordance with the terms of, clause 12.11.

Interest

The Contractor will pay simple interest at the rate stated in the Subcontract Particulars on any:

amount which has been set out as payable by the Contractor's Representative in a payment statement under clause 12.4, but which is not paid by the Contractor within the time required by the Subcontract; and

damages (excluding any agreed damages payable under clause 10.11).

This will be the Subcontractor's sole entitlement to interest including damages for loss of use of, or the cost of borrowing, money.

Correction of Payment Statements

The Contractor's Representative may, in any payment statement:

correct any error in any previous payment statement; and

modify any previous payment statement,

issued by the Contractor's Representative.

Right of Set-Off

The Contractor may:

deduct from moneys otherwise due to the Subcontractor:

any debt or other moneys due from the Subcontractor to the Contractor; and

any claim to money which the Contractor may have against the Subcontractor whether for damages (including liquidated damages) or otherwise,

whether under the Subcontract or otherwise at law relating to the Subcontract Works or the Subcontractor's Activities; and

without limiting paragraph (a), deduct any debt or claim referred to in paragraphs (a)(i) or (a)(ii) from any moneys which may be or thereafter become payable to the Subcontractor by the Contractor in respect of any Variation the subject of a "Variation Order" under clause 11.2.

Payment of Workers and Subcontractors

The Subcontractor must with each payment claim under clause 12.2 provide the Contractor's Representative with:

a statutory declaration, together with any supporting evidence which may be reasonably required by the Contractor's Representative, duly signed by the Subcontractor or, where the Subcontractor is a corporation, by a representative of the Subcontractor who is in a position to know the facts declared, that, except to the extent disclosed in the statutory declaration (such disclosure to specify all relevant amounts, workers and subsubcontractors):

all workers who have at any time been employed by the Subcontractor on the Subcontractor's Activities have at the date of the payment claim been paid all moneys due and payable to them in respect of their employment on the Subcontractor's Activities; and

all subsubcontractors have been paid all moneys due and payable to them in respect of the Subcontractor's Activities; and

documentary evidence that, except to the extent otherwise disclosed (such disclosure to specify all relevant amounts and workers), as at the date of the payment claim, all workers who have been employed by a subsubcontractor have been paid all moneys due and payable to them in respect of their employment on the Subcontractor's Activities.

The Contractor is entitled to withhold from any payment which would otherwise be due to the Subcontractor under the Subcontract the amount disclosed as unpaid under this clause 12.16.

GST

Subject to paragraph (b), where any supply occurs under or in connection with the Subcontract or the Subcontract Works for which GST is not otherwise provided, the party making the supply (Supplier) will be entitled to increase the amount payable for the supply by the amount of any applicable GST.

Where an amount is payable to the Supplier for a supply under or in connection with the Subcontract or the Subcontract Works which is based on the actual or reasonable costs incurred by the Supplier, the amount payable for the supply will be reduced by the amount of any input tax credits available to the Supplier (or a representative member on the Supplier's behalf) in respect of such costs before being increased for any applicable GST under paragraph (a).

As a condition precedent to any amount on account of GST being due from the recipient to the Supplier in respect of a taxable supply, the Supplier must provide a tax invoice to the recipient in respect of that supply.

If the amount paid to the Supplier in respect of the GST (whether because of an adjustment or otherwise):

is more than the GST on the supply, then the Supplier shall refund the excess to the recipient; or

is less than the GST on the supply, then the recipient shall pay the deficiency to the Supplier.

In this clause:

GST means the tax payable on taxable supplies under the GST Legislation;

GST Legislation means A New Tax System (Goods and Services Tax) Act 1999 (Cth) and any related Act imposing such tax or legislation that is enacted to validate, recapture or recoup such tax; and

terms defined in GST Legislation have the meaning given to them in GST Legislation.

Quantities in Schedule of Rates

The items of work and quantities in any Schedule of Rates are estimated and not guaranteed.  The Subcontractor will not be entitled to make any Claim against the Contractor if the items of work or quantities are incorrect in that they:

contain an incorrect quantity;

contain an item which should not have been included; or

omit an item which should have been included.

Limits of Accuracy

If a Schedule of Rates exists and:

the actual quantity of an item required to carry out the Subcontractor's Activities is greater or less than the quantity shown in the Schedule of Rates;

the Subcontractor has accepted a rate for the item referred to in paragraph (a); and

the actual quantity of the item referred to in paragraph (a) is outside the limits of accuracy stated in the Subcontract Particulars,

the rate will only apply to the quantities within those limits of accuracy and quantities outside those limits of accuracy will:

if so instructed by the Contractor's Representative, be carried out by the Subcontractor as daywork; or

otherwise have their value determined by:

agreement between the Subcontractor and the Contractor's Representative; or

failing agreement, the Contractor's Representative using reasonable rates.

Security of Payment Legislation

The Subcontractor agrees with the Contractor that:

a payment claim submitted to the Contractor's Representative under clause 12.2 which also purports to be a payment claim under the relevant Security of Payment Legislation is received by the Contractor's Representative as agent for the Contractor;

unless otherwise notified to the Subcontractor by the Contractor in writing, the Contractor's Representative will give payment statements and carry out all other functions of the Contractor under the relevant Security of Payment Legislation as the agent of the Contractor;

to the extent permitted by and for the purposes of the relevant Security of Payment Legislation, the "reference dates" are those of the dates prescribed in clauses 12.2(a) and 12.2(b) on which the Subcontractor has satisfied the requirements of clause 12.3(a); and

a reference to a "payment statement" is also a reference to a "payment schedule" for the purposes of the relevant Security of Payment Legislation.

Failure by the Contractor's Representative to set out in a payment statement issued under the relevant Security of Payment Legislation or otherwise an amount which the Contractor is entitled to retain, deduct, withhold or set-off from the amount which would otherwise be payable to the Subcontractor by the Contractor will not prejudice:

the Contractor's Representative's ability or power to set out in a subsequent payment statement an amount which the Contractor is entitled to retain, deduct, withhold or set-off from the amount which would otherwise be payable to the Subcontractor by the Contractor; or

the Contractor's right to subsequently exercise its right to retain, deduct, withhold or set-off any amount under this Subcontract.

The Subcontractor agrees that the amount set out in the payment statement in accordance with clause 12.4(f) is, to the extent permitted by and for the purposes of the relevant Security of Payment Legislation, the amount of the "progress payment" calculated in accordance with the terms of this Subcontract, which the Subcontractor is entitled to in respect of the Subcontract.

The Subcontractor irrevocably chooses the person set out in the Subcontract Particulars as, to the extent permitted by and for the purposes of the relevant Security of Payment Legislation and to the extent that the relevant Subcontractor's Activities are to be carried out in the Territory, as authorised nominating authority.

The Subcontractor must not at any time, without the written consent of the Contractor, divulge or suffer or permit its servants, subsubcontractors or agents to divulge to any person any communication, submission or statement made or evidence or information used by or relied upon by the Contractor or any details thereof in respect of an adjudication application made under the relevant Security of Payment Legislation (in this paragraph, the Information).

For the avoidance of doubt:

the Subcontractor's obligation in respect of the Information applies in respect of any subsequent proceedings before a court, arbitrator, expert or tribunal save where the Subcontractor is unable by requirement of law to comply with its obligation in respect of the Information;

notwithstanding the Subcontractor's obligation in respect of the Information, the Contractor has sole and unfettered discretion to divulge or suffer or permit its servants, subcontractors or agents to divulge to any person the Information;

the Contractor may divulge or suffer or permit its servants, subcontractors or agents to divulge to any person any communication, submission or statement made or evidence or information used by or relied upon by the Subcontractor or any details thereof in respect of an adjudication application made under the relevant Security of Payment Legislation; and

any Information which the Contractor provides or relies upon in respect of an adjudication application made under the relevant Security of Payment Legislation is made without prejudice to the Contractor's right to vary, modify, supplement or withdraw the Information in any subsequent proceedings before a court, arbitrator, expert or tribunal.

Accounting Records

The Subcontractor must keep accurate and up to date accounting records including books of account, labour time sheets, invoices for materials, plant hire, final accounts and any other documents or papers which show all details in relation to:

all Variations; and

all other amounts payable to the Subcontractor other than on account of the original Subcontract Price specified in the Subcontract Particulars.

Cost Allocation Advice

Without limiting clause 12.2, for the purposes of assisting the Territory to report on an accrual basis, the Subcontractor must, with each payment claim under clause 12.2, provide the Contractor's Representative  with accurate information which apportions monthly costs against buildings, infrastructure and expenses for all work completed in the previous month, in a format approved by the Contractor's Representative .

Facilities and Infrastructure Accounting

Without limiting clause 12.2, for the purposes of assisting the Territory to bring all completed facilities and infrastructure to account, as a condition precedent to Completion of the Subcontract Works or a Stage, the Subcontractor must provide a cost report to the Contractor's Representative which sets out:

details of the Subcontract Price (or part) paid in respect of the Subcontract Works or the Stage;

the matters specified in the Subcontract Particulars; and

any other matters required by the Contractor's Representative.

Not used

Completion

Subcontractor to Notify

Nothing in this clause 13 limits the Subcontractor's obligations or liabilities, or the Contractor's or the Contractor's Representative's rights, under clause 9.13.

The Subcontractor must give the Contractor's Representative written notice 28 days, and then again 14 days, before it anticipates achieving Completion of the Subcontract Works or a Stage.

Contractor's Representative to Inspect

The Contractor's Representative must:

promptly, and in any event no later than 14 days after receiving the Subcontractor's second written notice under clause 13.1(b) or a notice under paragraph (d) (as the case may be), inspect the Subcontract Works or the Stage; and

if:

satisfied that Completion has been achieved, issue a notice to the Contractor and the Subcontractor:

stating the date upon which the Contractor's Representative determines Completion was achieved; and

containing a list of any minor Defects of the type described in paragraph (a) of the definition of "Completion" in clause 1.1; or

not satisfied that Completion has been achieved, issue a notice so advising the Subcontractor and the Contractor.

If the Contractor's Representative issues a notice under paragraph (b)(ii), the Subcontractor must:

proceed to bring the Subcontract Works or the Stage to Completion; and

when it considers it has achieved Completion, give the Contractor's Representative written notice to that effect (after which this clause 13.2 will reapply).

Unilateral Issue of Completion Notice

If at any time a notice required to be given by the Subcontractor to the Contractor's Representative under clause 13.1(b) or 13.2 is not given by the Subcontractor yet the Contractor's Representative is of the opinion that Completion of the Subcontract Works or a Stage has been achieved, the Contractor's Representative may issue a Notice of Completion under clause 13.2(b)(i) for the Subcontract Works or the Stage.

Take Over Upon Completion

Upon the issue of a Notice of Completion, the Subcontractor must:

hand over the Subcontract Works or the Stage to the Contractor; and

correct all Defects listed in the Notice of Completion as soon as possible.

Part of the Subcontract Works or a Stage

The Subcontractor must, if written notice is given to the Subcontractor by the Contractor's Representative, allow the Territory or the Contractor to occupy or use any part of the Subcontract Works or a Stage although the whole of the Subcontract Works or the Stage has not reached Completion.

If any such notice is given by the Contractor's Representative,  the Contractor must allow the Subcontractor reasonable access to the part of the Subcontract Works or the Stage referred to in the notice and being occupied or used by the Contractor, to enable the Subcontractor to bring the Subcontract Works or the relevant Stage of which the area being occupied or used forms part to Completion.

Without limiting paragraph (a), the Contractor's Representative may, at any time by written notice to the Subcontractor, direct:

that any part of the Subcontract Works or any part of a Stage is to be a new Stage notwithstanding the whole of the Subcontract Works or a Stage has not reached Completion; and

the Date for Completion for any new Stage or Stages.

A notice under paragraph (a) or (c) will not limit or affect the obligations of the Subcontractor under the Subcontract, including the obligation of the Subcontractor to achieve Completion of the Subcontract Works or each Stage by the relevant Date for Completion.

Effect of Notice of Completion

A Notice of Completion will not:

constitute approval by the Contractor of the Subcontractor's performance of its Subcontract obligations;

be taken as an admission or evidence that the Subcontract Works or the Stage complies with the Subcontract; or

prejudice any rights or powers of the Contractor or Contractor's Representative.

Liquidated Damages

If the Date of Completion of the Subcontract Works or a Stage has not occurred by the Date for Completion for the Subcontract Works or the Stage, the Subcontractor must pay liquidated damages at the rate specified in the Subcontract Particulars for every day after the Date for Completion until the Date of Completion or the Subcontract is terminated, whichever is first.

This amount is an agreed genuine pre-estimate of the Contractor's damages if the Date of Completion does not occur by the Date for Completion, but is exclusive of damages which the Contractor will suffer if:

the Date of Completion has not occurred by the Date for Completion; and

the Contractor incurs a liability to the Territory as contemplated by clause 13.8.

The amount payable under this clause 13.7 will be a debt due from the Subcontractor to the Contractor.

Liability to the Territory

In addition to any other liability under this Subcontract (including the liability under clause 13.7), the Subcontractor must indemnify the Contractor against any costs, losses, expenses or damages (whether liquidated or unliquidated) which the Contractor pays or is liable to pay the Territory under the Managing Contractor Contract or otherwise to the extent that such payment or liability arises out of or in any way in connection with the Date of Completion of the Subcontract Works or a Stage not occurring by the Date for Completion for the Subcontract Works or the Stage.

Incentive

Clause 13.9 does not apply unless the Subcontract Particulars state that it applies.

If Completion of the Subcontract Works or a Stage occurs before the relevant Incentive Date the Contractor must pay the Subcontractor the incentive stipulated in the Subcontract Particulars.

The Contractor must pay the incentive for every day after the Date of Completion of the Subcontract Works or the Stage to (and including) the relevant Incentive Date.

TERMINATION

Preservation of Rights

Subject to clause 14.6, nothing in this clause 14 or that the Contractor does or fails to do pursuant to this clause 14 will prejudice the right of the Contractor to exercise any right or remedy (including recovering damages) which it may have where the Subcontractor breaches (including repudiates) the Subcontract.

Subcontractor Default

The Contractor may give a written notice under clause 14.3 to the Subcontractor if the Subcontractor:

does not commence the Subcontractor's Activities in accordance with the requirements of the Subcontract;

suspends the Subcontractor's Activities in breach of clause 10.12 or otherwise does not proceed with the Subcontractor's Activities regularly and diligently;

fails to provide security as required by clause 4.1 or the related company guarantee as required under clause 4.4;

fails to comply with any of its obligations under clause 5.5 or 5.7;

fails to comply with any of its obligations under clause 8.16 or 8.17;

fails to comply with any of its obligations under clause 3.8(c) or 3.8(m);

fails to use the materials or standards of workmanship required by the Subcontract;

does not comply with any direction of the Contractor's Representative made in accordance with the Subcontract;

is found to have made (or had made by its representative) a false statement in a statutory declaration provided under this Subcontract; or

is otherwise in substantial breach of the Subcontract.

Contents of Notice of Default

A notice under this clause 14.3 must state:

that it is a notice under clause 14.3;

the breach relied upon; and

that the Contractor requires the Subcontractor to remedy the breach within the number of days set out in the Subcontract Particulars of receiving the notice.

Termination for Insolvency or Breach

If:

an Insolvency Event occurs to the Subcontractor, or where the Subcontractor comprises 2 or more persons, to any one of those persons; or

the Subcontractor does not remedy a breach of Subcontract the subject of a notice under clause 14.3 within the number of days set out in the Subcontract Particulars of receiving the notice under clause 14.3,

then the Contractor may by written notice to the Subcontractor terminate the Subcontract.

Contractor's Entitlements after Termination

Subject to clause 14.1, if the Contractor terminates the Subcontract under clause 14.4, or if the Subcontractor repudiates the Subcontract and the Contractor otherwise terminates the Subcontract:

the Contractor will:

be entitled to take over and use, or require the Subcontractor to remove from the Site, the Plant, Equipment and Work and all materials, equipment and other things intended for the Subcontract Works;

be entitled to require the Subcontractor to novate to the Contractor or the Contractor's nominee, any or all subsubcontracts between the Subcontractor and its subsubcontractors as required by the Contractor;

to the extent permitted by the relevant Security of Payment Legislation, not be obliged to make any further payments to the Subcontractor, including any money the subject of a payment claim under clause 12.2 or a payment statement under clause 12.4; and

be entitled to recover from the Subcontractor any costs, losses or damages incurred or suffered by it as a result of, or arising out of, or in any way in connection with, such termination; and

the Subcontractor must immediately hand over to the Contractor all copies of:

documents provided by the Contractor in connection with the Subcontractor's Activities; and

Project Documents prepared by the Subcontractor to the date of termination (whether complete or not).

Subcontractor's Entitlements after Termination

If the Contractor repudiates the Subcontract and the Subcontractor terminates the Subcontract, the Subcontractor will:

be entitled to claim an amount determined in accordance with clause 14.8 as if the Contractor had terminated the Subcontract under clause 14.7; and

not be entitled to a quantum meruit.

This clause 14.6 will survive the termination of the Subcontract.

Termination for Convenience

Without prejudice to any of the Contractor's other rights under this Subcontract, the Contractor may:

at any time for its sole convenience, and for any reason, by written notice to the Subcontractor terminate the Subcontract effective from the time stated in the Contractor's notice or if no such time is stated, at the time the notice is given to the Subcontractor; and

thereafter, at its absolute discretion, complete the uncompleted part of the Subcontract Works either itself or by engaging Other Contractors.

Costs

If the Contractor terminates the Subcontract under clause 14.7, the Subcontractor:

will be entitled to payment of the following amounts as determined by the Contractor's Representative:

for work carried out prior to the date of termination, the amount which would have been payable if the Subcontract had not been terminated and the Subcontractor submitted a payment claim for work carried out to the date of termination;

the cost of goods or materials reasonably ordered by the Subcontractor for the Subcontract Works for which the Subcontractor is legally bound to pay provided that:

the value of the goods or materials is not included in the amount payable under subparagraph (i); and

title in the goods and materials will vest in the Territory upon payment by the Territory to the Contractor under the Managing Contractor Contract in respect of those goods and materials; and

the reasonable cost of removing from the Site all labour, Plant, Equipment and Work and other things used in the Subcontractor's Activities; and

must:

take all steps possible to mitigate the costs referred to in paragraphs (a)(ii) and (a)(iii); and

immediately hand over to the Contractor all copies of:

documents provided by the Contractor in connection with the Subcontractor's Activities; and

Project Documents prepared by the Subcontractor to the date of termination (whether complete or not).

The amount to which the Subcontractor is entitled under this clause 14.8 will be a limitation upon the Contractor's liability to the Subcontractor arising out of, or in any way in connection with, the termination of the Subcontract (whether under clause 14.7 or deemed to be under clause 14.7 through the operation of clause 14.6(a)) and the Subcontractor will not be entitled to make any Claim against the Contractor arising out of, or in any way in connection with, the termination of the Subcontract  other than for the amount payable under this clause 14.8.

This clause 14.8 will survive the termination of the Subcontract by the Contractor under clause 14.7 or by the Subcontractor following repudiation by the Contractor.

Termination of Managing Contractor Contract

If the Managing Contractor Contract is terminated at any time for any reason, the Contractor may:

terminate the Subcontract by notice in writing to the Subcontractor; or

without the consent of the Subcontractor, novate the Subcontract by assigning the Contractor's rights and obligations under the Subcontract to the Territory or a person nominated by the Territory.

If the Subcontract is novated under paragraph (b), the Subcontractor must upon demand by the Contractor execute any instrument required by the Contractor to give effect to the novation.

Consequences Following Managing Contractor Contract Termination

If the Subcontract is terminated under clause 14.9(a) or in accordance with any Subcontractor Deed of Covenant entered into by the Subcontractor under clause 8.5, then the Subcontractor:

will be entitled to the payment of the following amounts as determined by the Contractor's Representative:

for work carried out prior to the date of termination, the amount which would have been payable if the Subcontract had not been terminated and the Subcontractor submitted a payment claim for work carried out to the date of termination;

the cost of goods or materials reasonably ordered by the Subcontractor for the Subcontract Works for which the Subcontractor is legally bound to pay provided that:

the value of the goods or materials is not included in the amount payable under subparagraph (i); and

title in the goods and materials will vest in the Territory upon payment by the Territory to the Contractor under the Managing Contractor Contract in respect of those goods and materials; and

the reasonable cost of removing from the Site all labour, Plant, Equipment and Work and other things used in the Subcontractor's Activities; and

must:

take all steps possible to mitigate the costs referred to in subparagraphs (a)(ii) and (a)(iii); and

immediately hand over to the Contractor all copies of:

documents provided by the Contractor in connection with the Subcontractor's Activities; and

Project Documents prepared by the Subcontractor to the date of termination (whether complete or not).

The amount to which the Subcontractor is entitled under this clause 14.10 will be a limitation upon the Contractor’s liability to the Subcontractor arising out of, or in any way in connection with, the termination of the Subcontract under clause 14.9 and the Subcontractor will not be entitled to make any Claim against the Contractor arising out of, or in any way in connection with, the termination of the Subcontract other than for the amount payable under this clause 14.10.

Clauses 14.9 and 14.10 will survive termination of the Subcontract by the Contractor under clause 14.9.

DISPUTES

Notice of Dispute

If a dispute or difference arises between the Subcontractor and the Contractor or between the Subcontractor and the Contractor's Representative in respect of any fact, matter or thing arising out of, or in any way in connection with, the Subcontractor's Activities, the Subcontract Works or the Subcontract, or either party's conduct before the Subcontract, the dispute or difference must be determined in accordance with the procedure in this clause 15.

Where such a dispute or difference arises, either party may give a notice in writing to the Contractor's Representative and the other party specifying:

the dispute or difference;

particulars of the party's reasons for being dissatisfied; and

the position which the party believes is correct.

Expert Determination

If the dispute or difference is in relation to a direction of the Contractor's Representative under one of the clauses referred to in the Subcontract Particulars and is not resolved within 14 days after a notice is given under clause 15.1, the dispute or difference must be submitted to expert determination.

The Expert

The expert determination under clause 15.2 is to be conducted by:

the independent industry expert specified in the Subcontract Particulars; or

where no such independent industry expert is specified or paragraph (b) applies, an independent industry expert appointed by the person specified in the Subcontract Particulars.

If the expert appointed under this clause 15.3:

is unavailable;

declines to act;

does not respond within 14 days to a request by one or both parties for advice as to whether he or she is able to conduct the determination;

does not enter into the agreement in accordance with clause 15.9(b) within 14 days of his or her appointment under this clause 15; or

does not make a determination within the time required by clause 15.8,

the jurisdiction of the expert shall lapse and a further expert must be appointed under paragraph (a).

If there has been an appointment under paragraph (a) and one of the events in paragraph (b) has occurred, the further expert appointed under paragraph (a) shall not be an expert previously appointed under paragraph (a) in respect of the same dispute or difference.

Not Arbitration

An expert determination conducted under this clause 15 is not an arbitration and the expert is not an arbitrator.  The expert may reach a decision from his or her own knowledge and expertise.

Procedure for Determination

The expert will:

act as an expert and not as an arbitrator;

proceed in any manner he or she thinks fit;

conduct any investigation which he or she considers necessary to resolve the dispute or difference;

examine such documents, and interview such persons, as he or she may require; and

make such directions for the conduct of the determination as he or she considers necessary.

Disclosure of Interest

The expert must:

disclose to the parties any:

interest he or she has in the outcome of the determination;

conflict of interest;

conflict of duty;

personal relationship which the expert has with either party, or either party's  representatives, witnesses or experts; and

other fact, matter or thing which a reasonable person may regard as giving rise to the possibility of bias; and

not communicate with one party to the determination without the knowledge of the other.

Costs

Each party will:

bear its own costs in respect of any expert determination; and

pay one-half of the expert's costs.

Conclusion of Expert Determination

Unless otherwise agreed between the parties, the expert must notify the parties of his or her decision upon an expert determination conducted under this clause 15 within 28 days from the acceptance by the expert of his or her appointment.

Agreement with Expert

The expert will not be liable to the parties arising out of, or in any way in connection with, the expert determination process, except in the case of fraud.

The parties must enter into an agreement with the appointed expert on the terms set out in the Schedule of Collateral Documents or such other terms as the parties and the expert may agree.

Determination of Expert

The determination of the expert:

must be in writing;

will be substituted for the relevant direction of the Contractor's Representative unless a party gives notice of appeal to the other party within 21 days of receiving such determination in which case, subject to clauses 15.11 and 15.12, any such appeal will be by way of a hearing de novo; and

will be final and binding, unless a party gives notice of appeal to the other party within 21 days of receiving such determination.

Executive Negotiation

If:

clause 15.2 applies, and a notice of appeal is given under clause 15.10; or

clause 15.2 does not apply,

the dispute or difference is to be referred to the Executive Negotiators.

The Executive Negotiators must within:

21 days of:

if the dispute or difference is not one which is to be referred to expert determination under clause 15.2, the notice of dispute given under clause 15.1;  or

otherwise, the notice of appeal given under clause 15.10; or

such longer period of time as the Executive Negotiators may agree in writing,

meet and undertake genuine and good faith negotiations with a view to resolving the dispute or difference and, if they cannot resolve the dispute or difference, endeavour to agree upon a procedure to resolve the dispute or difference (such as mediation or further expert determination).

Arbitration Agreement

If, within:

21 days of:

if the dispute or difference is not one which is to be referred to expert determination under clause 15.2, the notice of dispute given under clause 15.1; or

otherwise, the notice of appeal given under clause 15.10; or

such longer period of time as the Executive Negotiators may agree in writing,

the Executive Negotiators:

or either party refuse or fail to meet and undertake genuine and good faith negotiations with a view to resolving the dispute or difference;

cannot resolve the dispute or difference; or

have not reached agreement upon a procedure to resolve the dispute or difference,

the dispute or difference will be referred to arbitration by a written notice by either party to the other party.

Arbitration

Arbitration pursuant to this clause will be conducted in accordance with the Rules of Arbitration of the International Chamber of Commerce (ICC Rules) current at the time of the reference to arbitration and as otherwise set out in this clause.

The seat of the arbitration will be Melbourne, Australia and hence the proper law of the arbitration shall be Victoria.

Nothing in this clause is intended to modify or vary the rights of appeal contained in the Commercial Arbitration Act 1986 (ACT).  For the avoidance of doubt, the second sentence of Article 28(6) of the ICC Rules (in force from 1 January 1998) or its equivalent in any subsequent version of the ICC Rules shall not apply.

The parties agree that:

they have entered into the arbitration agreement under this clause 15 for the purposes of achieving a just, quick and cheap resolution of any dispute or difference;

any arbitration conducted pursuant to this clause will not mimic court proceedings of the seat of the arbitration and the practices of those courts will not regulate the conduct of the proceedings before the arbitrator; and

in conducting the arbitration, the arbitrator must take into account the matters set out in subparagraphs (i) and (ii).

One arbitrator will be appointed.

All evidence in chief will be in writing unless otherwise ordered by the arbitrator.

Discovery will be governed by the substantive and procedural rules and practices adopted by the Federal Court of Australia at the time of arbitration.

The oral hearing will be conducted as follows:

the oral hearing will take place in Canberra, Australia and all outstanding issues must be addressed at the oral hearing;

the date and duration of the oral hearing will be fixed by the arbitrator at the first preliminary conference.  The arbitrator must have regard to the principles set out in paragraph (d) when determining the duration of the oral hearing;

oral evidence in chief at the hearing will be permitted only with the permission of the arbitrator for good cause;

the oral hearing will be conducted on a stop clock basis with the effect that the time available to the parties will be split equally between the parties so that each party will have the same time to conduct its case unless, in the opinion of the arbitrator, such a split would breach the rules of natural justice or is otherwise unfair to one of the parties;

not less than 28 days prior to the date fixed for the oral hearing, each party will give written notice of those witnesses (both factual and expert) of the other party that it wishes to attend the hearing for cross examination; and

in exceptional circumstances, the arbitrator may amend the date of hearing and extend the time for the oral hearing set under subparagraph (ii).

Unless otherwise ordered, each party may only rely upon one expert witness in respect of any recognised area of specialisation.

Proportional Liability

Notwithstanding anything else, to the extent permissible by law, the expert or the arbitrator (as the case may be) will have no power to apply or to have regard to the provisions of any proportional liability legislation which might, in the absence of this provision, have applied to any dispute referred to arbitration or expert determination pursuant to this clause.

MCC Dispute Procedures

Under the Managing Contractor Contract, disputes and differences between the Contractor and the Territory and the Contractor and the MCC Contract Administrator are required to be determined in accordance with certain procedures which include expert determination, executive negotiation and arbitration.

Within 7 days of the Award Date, the Contractor must provide the Subcontractor with a copy of the provisions in the Managing Contractor Contract setting out the MCC Dispute Procedures.

The Subcontractor agrees that certain disputes and differences of the kind referred to in clause 15.1 will be determined under the MCC Dispute Procedures as set out in clauses 15.16 - 15.18 in lieu of the procedures set out in clauses 15.2 - 15.14.

Managing Contractor Contract Disputes

If:

the Subcontractor gives a notice under clause 15.1;

the dispute or difference relates, in whole or in part, to either:

an alleged breach of the Subcontract by the Contractor, which, assuming the breach has actually occurred, has been caused, or contributed to, by an act or omission (including breach of the Managing Contractor Contract) of the Territory; or

a direction given by the Contractor's Representative relating to a particular subject matter, in circumstances where a direction has been given by the MCC Contract Administrator to the Contractor relating, in whole or in part, to that subject matter, or otherwise relates, in whole or in part, to any other fact, matter or circumstance arising out of or in connection with the Managing Contractor Contract; and

the Contractor is not barred from making, or has not waived its entitlement to make, a Claim against the Territory in respect of the act, omission or direction,

the Contractor may within 7 days of receipt of the notice give a notice to the Subcontractor stating that clause 15.17 applies in relation to the dispute or difference.

Procedure for Managing Contractor Contract Disputes

If a notice is given under clause 15.16 stating that this clause 15.17 applies:

subject to clause 15.18, the Contractor must:

take such steps as are reasonably necessary to progress the Subcontractor’s dispute or difference under the MCC Dispute Procedures;

regularly consult with the Subcontractor to ascertain its views as to the progression of the Subcontractor's dispute or difference; and

use its best endeavours to ensure that the Subcontractor’s views, where relevant, are put to any expert or arbitrator appointed under the MCC Dispute Procedures or any court which may hear any matter relating to the Subcontractor's dispute or difference as between the Contractor and the Territory; and

the Subcontractor must:

comply with the Contractor’s reasonable requirements relating to the conduct of the MCC Dispute Procedures or any relevant court proceedings insofar as they relate to the Subcontractor's dispute or difference;

indemnify the Contractor against all costs and expenses incurred by the Contractor in complying with paragraph (a); and

from time to time as required by the Contractor, lodge with the Contractor reasonable cash or other security against the costs and expenses referred to in subparagraph (b)(ii).

Further Procedures

Where clause 15.17 applies, the following provisions also apply:

the Contractor must not without the prior consent of the Subcontractor (acting reasonably) agree to a settlement with the Territory or any other relevant person of the Subcontractor’s dispute or difference; and

where a determination is made by an expert, an arbitrator or a court in relation to the Subcontractor's dispute or difference as between the Territory and the Contractor:

if the determination is not final and binding upon the Contractor:

the Contractor is not obliged to appeal against that determination unless the Subcontractor gives a notice to the Contractor requiring such an appeal:

within such time as to reasonably enable the Contractor to comply with any relevant requirements relating to the time for commencement of such appeals; and

which contains any particulars required to reasonably enable the Contractor to progress the appeal in accordance with any relevant requirements; and

the parties will be bound by and are to give effect to the determination including any findings as to law or fact unless and until it is reversed, overturned or otherwise changed on appeal as between the Territory and the Contractor; and

if the determination is final and binding upon the Contractor, the parties:

will be bound by and are to give effect to the determination including any findings as to law or fact; and

release each other from any Claim which they may have arising out of or in any way in connection with the subject matter of the Subcontractor's dispute or difference insofar as the determination relates to the dispute or difference.

Continuation of Subcontractor's Activities

Despite the existence of a dispute or difference between the parties the Subcontractor must:

continue to carry out the Subcontractor's Activities; and

otherwise comply with its obligations under the Subcontract.

NOTICES

Notice of Variation

If a direction by the Contractor's Representative, other than a "Variation Order" under clause 11.2, constitutes or involves a Variation, the Subcontractor must, if it wishes to make a Claim against the Contractor arising out of, or in any way in connection with, the direction:

within 7 days of receiving the direction and before commencing work on the subject matter of the direction, give notice to the Contractor's Representative that it considers the direction constitutes or involves a Variation;

within 21 days after giving the notice under paragraph (a), submit a written claim to the Contractor's Representative which includes the details required by clause 16.3(b); and

continue to carry out the Subcontractor's Activities in accordance with the Subcontract and all directions of the Contractor's Representative, including any direction in respect of which notice has been given under this clause 16.1.

Notices of Other Claims

Except for claims for:

an extension of time under clause 10.6;

payment under clause 12.2 of the original Subcontract Price specified in the Subcontract Particulars; or

a Variation instructed in accordance with clause 11.2 or to which clause 16.1 applies,

the Subcontractor must give the Contractor's Representative the notices required by clause 16.3 if it wishes to make a Claim against the Contractor in respect of any direction by the Contractor's Representative or any other fact, matter or thing (including a breach of the Subcontract by the Contractor) under, arising out of, or in any way in connection with, the Subcontractor's Activities or the Subcontract, including anything in respect of which:

it is otherwise given an express entitlement under the Subcontract; or

the Subcontract expressly provides that:

specified costs are to be added to the Subcontract Price; or

the Subcontract Price will be otherwise increased or adjusted,

as determined by the Contractor's Representative.

Prescribed Notices

The notices referred to in clause 16.2 are:

a written notice within 21 days of the first occurrence of the direction or other fact, matter or thing upon which the Claim is based, expressly specifying:

that the Subcontractor proposes to make a Claim; and

the direction or other fact, matter or thing upon which the Claim will be based; and

a written Claim within 21 days of giving the written notice under paragraph (a), which must include:

detailed particulars concerning the direction or other fact, matter or thing upon which the Claim is based;

the legal basis for the Claim, whether based on a term of the Subcontract or otherwise, and if based on a term of the Subcontract, clearly identifying the specific term;

the facts relied upon in support of the Claim in sufficient detail to permit verification; and

details of the amount claimed and how it has been calculated.

Continuing Events

If the direction or fact, matter or thing upon which the Claim under clause 16.1(b) or 16.2 is based or the consequences of the direction or fact, matter or thing are continuing, the Subcontractor must continue to give the information required by clause 16.3(b) every 28 days after the written claim under clause 16.1(b) or 16.3(b) (as the case may be) was submitted or given to the Contractor's Representative, until after the direction or fact, matter or thing upon which the Claim is based has, or the consequences thereof have, ceased.

Time Bar

If the Subcontractor fails to comply with clause 16.1, 16.2, 16.3 or 16.4:

the Contractor will not be liable (insofar as it is possible to exclude such liability) upon any Claim by the Subcontractor; and

the Subcontractor will be absolutely barred from making any Claim against the Contractor,

arising out of, or in any way in connection with, the relevant direction or fact, matter or thing (as the case may be) to which clause 16.1 or 16.2 applies.

Other Provisions Unaffected

Nothing in clauses 16.1-16.5 will limit the operation or effect of any other provision of the Subcontract which requires the Subcontractor to give notice to the Contractor's Representative in order to preserve an entitlement to make a Claim against the Contractor.

Address for Service

Any notice to be given or served under or arising out of a provision of this Subcontract must:

be in writing;

be delivered by hand,  sent by electronic mail, prepaid post or sent by fax, as the case may be, to the relevant address or fax number:

stated in the Subcontract Particulars; or

last notified in writing to the party giving or serving the notice,

for the party to whom or upon which the notice is to be given or served; and

be signed by the party giving or serving the notice or (on the party's behalf) by the solicitor for or attorney, director, secretary or authorised agent of the party giving or serving the notice.

Receipt of Notices

A notice given or served in accordance with clause 16.7 is taken to be received by the party to whom or upon whom the notice is given or served in the case of:

delivery by hand, on delivery;

prepaid post sent to an address in the same country, on the third day after  the date of posting;

prepaid post sent to an address in another country, on the fifth day after the date of posting;

fax, at the time in the place to which it is sent equivalent to the time shown on the transmission confirmation report produced by the fax machine from which it was sent; and

electronic mail, on whichever of the following occurs first:

the other party’s acknowledgment of receipt by any means,

the sender’s electronic mail device recording that the electronic mail has been successfully transmitted to the recipient’s address, or

expiration of two business days after the date on which it was sent without receipt of a notification that the delivery failed,

and if given in two or more ways, on the first of paragraphs (a) to (e) occurring.

WOL

Design and Construction

Without limiting the Subcontractor's other obligations under the Subcontract, the Subcontractor must:

design the parts of the Subcontract Works which the Subcontract requires it to design; and

construct the Subcontract Works,

in a manner which:

complies with the requirements of the WOL Plan; and

achieves the WOL Objectives.

Consultation

The Subcontractor must meet at such times and with such Other Contractors as the Contractor's Representative may require from time to time to:

review the progress of the design and construction of the Subcontract Works against the WOL Plan and the WOL Objectives; and

consult with the Contractor's Representative and the Other Contractors as to any designs, materials or methods of construction which they might recommend to maximise the achievement of the WOL Objectives.

WOL Proposals

Without limiting its other Subcontract obligations, the Subcontractor must at all times in carrying out the Subcontractor's Activities:

use its best endeavours to identify, and recommend to the Contractor's Representative, all reasonably available proposals for maximising the achievement of the WOL Objectives; and

consult with the Contractor's Representative as to:

proposals which it is considering making under paragraph (a); and

possible proposals under paragraph (a) identified by the Contractor.

Reporting

The Subcontractor must provide the Contractor's Representative with a written performance report:

at each meeting in accordance with clause 3.9(a); and

in such form and on such matters as the Contractor's Representative may require from time to time, including a detailed explanation of the Subcontractor's compliance with the WOL Plan.

Post Occupancy Evaluation

The Contractor's Representative may:

at any time carry out (or procure an Other Contractor to carry out) a post occupancy evaluation of the Subcontract Works; and

without limiting paragraph (a):

inspect the Subcontract Works to review the extent to which the Subcontractor has complied with the WOL Plan and otherwise maximised the achievement of the WOL Objectives in the design and construction of the Subcontract Works; and

issue a report to the Territory, the Contractor and the Subcontractor:

stating the extent to which the Subcontractor has complied with the WOL Plan and otherwise maximised the achievement of the WOL Objectives in the design and construction of the Subcontract Works; and

containing a list of any aspects of the Subcontract Works which do not conform with the requirements of the Subcontract.

The Subcontractor:

must consult with the Contractor's Representative and Other Contractors and must provide such other assistance as is necessary, for the purposes of the Contractor's Representative carrying out the requirements in paragraphs (a) and (b); and

acknowledges that the results of the post occupancy evaluation may be used in the evaluation of future tenders submitted by the Subcontractor to the Contractor or the Territory (as the case may be).

Rights and Obligations Not Affected

Neither the Contractor’s rights, nor the Subcontractor’s liability, whether under the Subcontract or otherwise according to law or in equity, whether before or after the expiration of the Defects Liability Period, will be affected or limited by:

the rights conferred upon the Contractor or Contractor's Representative by this clause 17 or the failure by the Contractor or the Contractor's Representative to exercise any such rights;

the obligations imposed upon the Subcontractor by this clause 17 or the Subcontractor's compliance with those obligations; or

any direction of the Contractor's Representative under or purported to be given under the Subcontract, including any comment or direction upon or review, acceptance or rejection of:

any advice, recommendation or other assistance provided by the Subcontractor under this clause 17; or

any post occupancy evaluation carried out (including any report prepared and finalised) under clause 17.5.

GENERAL

Workplace Gender Equality

The Subcontractor must:

comply with its obligations under the Workplace Gender Equality Act 2012 (Cth); and

not enter into a subsubcontract made in connection with this Subcontract with a subsubcontractor named by the Workplace Gender Equality Agency as an employer currently not complying with the Workplace Gender Equality Act 2012 (Cth).

Not used

Not used

IT Equipment

Without limiting any other clause of this Subcontract, the Subcontractor warrants that:

each item of IT Equipment:

is free of defects in materials and workmanship;

complies and operates in accordance with any technical or descriptive specifications of functional, operational, performance or other characteristics specified for that item of IT Equipment in the Subcontract or in any documentation accompanying that IT Equipment; and

correctly interprets dates and correctly performs calculations or functions using dates and its operation, including with related IT Equipment and other parts of the Subcontract Works, will not be adversely affected by the date; and

no virus will be introduced into the Territory's nor the Contractor's systems as a result of the supply by the Subcontractor of any IT Equipment or as a result of any other act or omission of the Subcontractor in connection with carrying out the Subcontractor's Activities.

Without limiting clause 8.6, the Subcontractor must assign to the Contractor, the benefits of warranties given by any supplier from whom the Subcontractor sources any IT Equipment and for that purpose must execute any instrument necessary to give effect to the assignment within 7 days of the Subcontractor becoming entitled to the benefit of such warranties.  The assignment of a warranty pursuant to this clause does not in any way relieve the Subcontractor of the obligation to comply with warranties given by the Subcontractor under this Subcontract.

Protection of Personal Information

The Subcontractor agrees:

to comply with the Australian Privacy Principles when doing any act or engaging in any practice in relation to Personal Information for the purposes of this Subcontract, as if it were an agency as defined in the Privacy Act;

to use Personal Information received, created or held by the Subcontractor for the purposes of this Subcontract only for the purposes of fulfilling its obligations under this Subcontract;

not to disclose Personal Information received, created or held by the Subcontractor for the purposes of this Subcontract  without the prior written approval of the Contractor's Representative;

not to transfer Personal Information received, created or held by the Subcontractor for the purposes of this Subcontract outside Australia, or to allow parties outside Australia to have access to it, without the prior written approval of the Contractor's Representative;

to co-operate with demands or inquiries made by the Federal Privacy Commissioner or the Contractor's Representative in relation to the management of Personal Information in connection with this Subcontract;

to ensure that any person whom the Subcontractor allows to access Personal Information which is received, created or held by the Subcontractor for the purposes of this Subcontract is made aware of, and undertakes in writing to observe, the Australian Privacy Principles;

to comply with policy guidelines laid down by the Territory or issued by the Commonwealth Privacy Commissioner from time to time relating to the handling of Personal Information;

to ensure that records (as defined in the Privacy Act) containing Personal Information received, created or held by the Subcontractor for the purposes of this Subcontract are, at the expiration or earlier termination of this Subcontract, at the Contractor's Representative's election, to be either returned to the Contractor or deleted or destroyed in the presence of a person duly authorised by the Contractor's Representative to oversee such deletion or destruction;

to the naming or other identification of the Subcontractor in reports by the Federal Privacy Commissioner;

to ensure that any subsubcontract made in connection with this Subcontract contains enforceable obligations requiring the subsubcontractor to comply with the Subcontractor's obligations arising out of this clause 18.5, as if the subsubcontractor were the Subcontractor;

to enforce the obligations referred to in subparagraph (x) in accordance with such directions as the Contractor's Representative may give;

that Personal Information collected by the Subcontractor in connection with the Subcontract must not be used for, or in any way relating to, any direct marketing purpose; and

to indemnify the Contractor against any loss, liability or expense suffered or incurred by the Contractor arising out of, or in connection with:

a breach of the obligations of the Subcontractor under this clause 18.5;

a breach of a subsubcontractor's obligations under a subsubcontract as contemplated by subparagraph (x);

the misuse of Personal Information held in connection with this Subcontract by the Subcontractor or a subsubcontractor; or

the disclosure of Personal Information held in connection with this Subcontract by the Subcontractor or a subsubcontractor in breach of an obligation of confidence.

For the purposes of paragraph (a)(xiii), loss, liability or expense includes any compensation paid to a person by or on behalf of the Contractor to settle a complaint arising out of, or in any way in connection with, a breach of this clause 18.5 by the Subcontractor.

The Subcontractor must immediately notify the Contractor in writing if the Subcontractor:

becomes aware of a breach of the obligations under paragraph (a) by itself or by a subsubcontractor;

becomes aware of a breach of a subsubcontractor's obligations under a subsubcontract as contemplated by paragraph (a)(x);

becomes aware that a disclosure of Personal Information may be required by law; or

is approached or contacted by, or becomes aware that a subsubcontractor has been approached or contacted by, the Federal Privacy Commissioner or by a person claiming that their privacy has been interfered with.

The Subcontractor acknowledges that, in addition to the requirements of this clause 18.5, the Subcontractor may also be obliged to comply with other obligations in relation to the handling of Personal Information, such as other provisions in the Privacy Act and State and Territory legislation.

Nothing in this clause 18.5 limits any of the Subcontractor's other obligations or liabilities under the Subcontract.

In this clause 18.5:

Australian Privacy Principle has the meaning given in the Privacy Act;

Personal Information has the meaning given in the Privacy Act;

Privacy Act means the Privacy Act 1988 (Cth); and

received includes collected.

Moral Rights

To the extent permitted by law, the Subcontractor:

must not, and must take all reasonable steps to ensure that its directors, other officers, employees and subsubcontractors do not, sue, enforce any claim, bring any action or exercise any remedy in respect of any breach or alleged breach of any person's Moral Rights (whether before or after the Award Date) in respect of any Project Documents or the Subcontract Works by:

the Contractor;

any third party to whom the Contractor sub-licenses (whether that sub-licence is express or implied), or grants any other right to use, possess, modify, vary or amend any Project Documents or any part of the Subcontract Works (Sub-Licensee);

any third party to whom the Contractor assigns any Intellectual Property Rights in the Project Documents or any part of the Subcontract Works (Assignee); or

any Other Contractors;

without limiting subparagraph (i), consents to any of the Territory, the Contractor, Other Contractors, Sub-Licensees and Assignees:

failing to acknowledge or attribute the Subcontractor's or any other person's authorship of any Project Documents or any part of the Subcontract Works;

falsely attributing authorship of any Project Documents or any part of the Subcontract Works; and

making any modification, variation or amendment of any nature whatsoever to any Project Documents or any part of the Subcontract Works, whether or not:

it results in a material distortion of or destruction or mutilation of the Project Documents or any part of the Subcontract Works; or

it is prejudicial to the honour or reputation of the Subcontractor or any other author of any Project Documents or any part of the Subcontract Works; and

without limiting subparagraphs (i) and (ii), consents to any of the Territory, the Contractor, Other Contractors, Sub-Licensees and Assignees:

using any Project Document or any part of the Subcontract Works other than for the purpose for which it was intended at the time the Project Document or any part of the Subcontract Works (as the case may be) was created;

altering any Project Documents or any part of the Subcontract Works by adding to or removing elements from, or rearranging elements of, the Project Documents or any part of the Subcontract Works, including by combining elements of any of the Project Documents or any part of the Subcontract Works with any other material; or

changing, relocating, demolishing or destroying any building or any artistic work affixed to or forming part of a building (including any part of the Subcontract Works), whether or not it incorporates, is based on, or is constructed in accordance with, any Project Documents.

The Subcontractor must:

in respect of any person who is or may be an author (for the purposes of the Copyright Act 1968 (Cth)) of any Project Documents or any part of the Subcontract Works, obtain from that person, before he or she creates any Project Documents or any part of the Subcontract Works, a duly completed and executed Moral Rights Consent;

ensure that no person creates any Project Documents or any part of the Subcontract Works before that person has duly completed and executed a Moral Rights Consent;

not coerce any person to complete or execute a Moral Rights Consent;

pay to each person who executes a Moral Rights Consent in accordance with this clause 18.6 the sum of $1 on behalf of the Contractor;

within 7 days of a Moral Rights Consent having been executed in accordance with this clause 18.6, provide that Moral Rights Consent to the Contractor's Representative; and

maintain an up-to-date record of the names and addresses of each person who is an author of any Project Documents or any part of the Subcontract Works, and the Project Documents or any part of the Subcontract Works of which each such person is an author, and provide a copy of the record to the Contractor's Representative whenever it is updated.

Freedom of Information

The Freedom of Information Act 1989 (ACT) (FOI Act) gives members of the public rights of access to official documents of the Territory and its agencies.  The FOI Act extends, as far as possible, rights to access information (generally documents) in the possession of the Territory, limited only by considerations for the protection of essential public interest and of the private and business affairs of persons in respect of whom information is collected and held by directorates and public authorities.

The Subcontractor acknowledges that Territory requirements and policies will require certain identifying details of the Subcontract to be made available to the public via the internet.

Long Service Leave

Clause 18.8 only applies if any relevant Long Service Leave Legislation applies to the Subcontractor's Activities.

Without limiting its other obligations or liabilities under this Subcontract or otherwise, the Subcontractor must comply with its obligations under any relevant Long Service Leave Legislation.

If required by any relevant Long Service Leave Legislation, the Subcontractor must pay any levy, charge, contribution or associated amount in respect of the Subcontractor's Activities.

Any amount paid by the Subcontractor under paragraph (b) is deemed to be included in the Subcontract Price and the Subcontractor will have no Claim against the Contractor arising out of or in connection with its obligations under this clause 18.8 or any other obligation under the relevant Long Service Leave Legislation.

In this clause 18.8, Long Service Leave Legislation means:

Long Service Leave (Portable Schemes) Act 2009 (ACT);

the long service leave obligations in the National Employment Standards in the Fair Work Act 2009 (Cth), if applicable; and

any other Act in the Territory addressing long service leave in the building and construction industry.

Assignment

The Subcontractor must not, without the prior written approval of the Contractor and except on the terms and conditions determined in writing by the Contractor, assign, mortgage, charge or encumber the Subcontract or any part or any benefit or moneys or interest under the Subcontract.

For the purpose of but without limiting paragraph (a), an assignment of this Subcontract will be deemed to have occurred where there has been a Change of Control.

Publicity

Without limiting clause 1.3(f), the Subcontractor must:

not furnish any information or issue any document or other written or printed material concerning the Subcontractor's Activities, the MCC Works or the Subcontract Works for publication in the media without the prior written approval of the Contractor's Representative; and

refer any enquiries from the media concerning the Subcontractor's Activities, the MCC Works or the Subcontract Works to the Contractor's Representative.

Not used

Building Code of Australia Certification

Without limiting clauses 6.13, 8.3, 8.4 and 9.1(c), the Subcontractor must provide to the Contractor's Representative written certification from an Accredited Building Surveyor:

at the time it submits any Design Documentation under clause 6.2 for the Subcontract Works or a Stage - that the Design Documentation submitted at that time complies with the Building Code of Australia; and

as a condition precedent to Completion of the Subcontract Works or a Stage - that the Subcontract Works comply or the Stage complies (as the case may be) with the Building Code of Australia.

Not used

COMMERCIAL-IN-CONFIDENCE INFORMATION

20.1	General

In giving effect to the principles of open and accountable government, the Territory may disclose documents and information related to this Subcontract unless it has otherwise agreed, or is otherwise required under law, to keep the information confidential.

20.2	Commercial-in-Confidence Information

Clause 20.2 does not apply unless the Subcontract Particulars state that it applies.

Subject to paragraph (b), the Contractor must keep confidential any information provided to the Contractor by the Subcontractor before or after the Award Date when:

a written request to keep specific information confidential and the justification for keeping such information confidential has been expressly made by the Subcontractor to the Contractor in its tender;

the Contractor agrees (in its absolute discretion) that such information is commercial-in-confidence information;

the Contractor notifies the Subcontractor in writing of its agreement (including the terms of any agreement) under subparagraph (ii); and

such information is identified in the Subcontract Particulars,

(Commercial-in-Confidence Information).

The Contractor's obligation in paragraph (a) does not apply if the Commercial-in-Confidence Information is:

disclosed by the Contractor to its legal or other advisers, or to its officers, employees, contractors or agents in order to comply with its obligations or to exercise its rights under or in connection with this Subcontract;

disclosed by the Contractor to its legal or other advisers, or to its officers, employees, contractors or agents in order to comply with the Contractor's management, reporting or auditing requirements under the Managing Contractor Contract;

disclosed by the Contractor to any responsible Minister or any Ministerial adviser or assistant;

disclosed by the Contractor to in reporting to the Legislative Assembly or its committees;

disclosed to the ombudsman or for a purpose in relation to the protection of public revenue;

disclosed to any Territory directorate, agency or authority by virtue of or in connection with:

its functions, or statutory or portfolio responsibilities; or

the Managing Contractor Contract;

authorised or required by law to be disclosed; or

in the public domain otherwise than due to a breach of paragraph (a).

Not used

National code of practice for the construction industry

General

The Subcontractor must comply with the National Code of Practice for the Construction Industry (“National Code”) from the time of submitting its expression of interest or tender (as relevant) for the Subcontractor’s Activities.

Copies of the National Code are available from http://www.apcc.gov.au/ALLAPCC/APCC%20PUB_DOLAC%20national%20code%20of%20Practice%201997.pdf.

Responsibility not Affected

Compliance with the National Code shall not relieve the Subcontractor from its other obligations under the Subcontract or otherwise arising out of or in connection with the Subcontractor’s Activities or the Works.

Notice of Effect on Compliance with National Code

If a change to the Subcontract is proposed which would affect the Subcontractor's compliance with the National Code, the Subcontractor must immediately give the Contractor a report in writing specifying the extent to which the Subcontractor's compliance with the National Code will be affected.

Records

The Subcontractor must maintain adequate records of compliance with the National Code by the Subcontractor.

Access and Documents

The Subcontractor must produce any document requested by the Contractor or any person authorised by the Contractor, in order to establish compliance with the National Code.

| Subcontract Particulars |
| --- |
| CLAUSE 1 - GLOSSARY OF TERMS, INTERPRETATION AND MISCELLANEOUS |
| Additional Project Plans: (Clause 1.1) |  | ……………………………………………………… |
| Completion - additional conditions precedent to Completion: (Clause 1.1) |  | ……………………………………………………… |
| Contractor: (Clause 1.1) |  | ……………………………………………………… |
| Contractor Environmental Management Plan: (Clause 1.1) |  | ……………………………………………………… |
| Contractor's Representative: (Clause 1.1) |  | ……………………………………………………… |
| Contractor's Commissioning and Handover Plan: (Clause 1.1) |  | ……………………………………………………… |
| Contractor's Site Management Plan: (Clause 1.1) |  | ……………………………………………………… |
| Contractor's Work Health and Safety Plan: (Clause 1.1) |  | ……………………………………………………… |
| Date for Completion: (Clause 1.1) |  | Where there are no Stages, for the Subcontract Works is: ……………………………………………………… Where there are Stages, for each Stage is: Stage Date for Completion ............ ................................. ............ ................................. ............ ................................. ............ ................................. |
| Defects Liability Period: (Clause 1.1) |  | ……………………………………………………… |
| Environmental Requirements (additional): (Clause 1.1) |  | ……………………………………………………… |
| ESD Principles (additional): (Clause 1.1) |  | ……………………………………………………… |
| Executive Negotiators: (Clause 1.1) |  | Contractor: ……………………………………………… Subcontractor: …………………………………………… |
| Incentive Date: (Clause 1.1) |  | Where there are no Stages, for the Subcontract Works is: ……………………………………………………… Where there are Stages, for each Stage is: Stage Incentive Date .................... .................... .................... .................... .................... .................... |
| Managing Contractor Contract: (Clause 1.1) |  | ……………………………………………………… |
| MCC Contract Administrator: (Clause 1.1) |  | ……………………………………………………… |
| MCC Works: (Clause 1.1) |  | ……………………………………………………… |
| Provisional Sum Work: (Clauses 1.1, 8.7, 8.10, 8.11 and 8.12) |  | Work or Goods Amount . . . . . . . . . . . . $…………………………………… . . . . . . . . . . . . $…………………………………… . . . . . . . . . . . . $…………………………………… Total: $……………………………..…… |
| Schedule of Collateral Documents: (Clause 1.1) |  | Approved Security (Unconditional Undertaking) Collateral Warranty Moral Rights Consent Consultant Deed of Covenant Consultant Design Certificate Subcontractor Deed of Covenant Subcontractor Design Certificate Subsubcontractor Deed of Covenant Subsubcontractor Design Certificate Deed of Guarantee, Undertaking and Substitution Payment Claim Expert Determination Agreement |
| Schedule of Rates: (Clause 1.1) |  | ……………………………………………………… |
| Site: (Clause 1.1) |  | ……………………………………………………… |
| Site Management Plan: (Clause 1.1) |  | Security procedures Access to the Site by visitors, pedestrians and vehicles Site induction procedures Safety procedures Emergency procedures Waste management procedures Site maintenance and cleaning procedures Site establishment procedures Dangerous, prohibited and hazardous materials and goods procedures Approval procedures User group and stakeholder procedures Noise management procedures Vehicle and traffic management procedures |
| Special Conditions: (Clause 1.1) |  | ……………………………………………………… |
| Stages of the Subcontract Works: (Clause 1.1) |  | ……………………………………………………… |
| Subcontract - other documents forming part of the Subcontract: (Clause 1.1) |  | ……………………………………………………… |
| Subcontract Price is: (Clause 1.1) |  | (a) a lump sum of $ ; and (b) where a Schedule of Rates exists, the amount calculated by multiplying the quantity of work carried out which is covered by the Schedule of Rates by the rate or price in the Schedule of Rates for that work, neither of which is, unless elsewhere stated, subject to rise and fall in costs. |
| Subcontract Works: (Clause 1.1) |  | ……………………………………………………… |
| Subcontract Works Description: (Clause 1.1) |  | ……………………………………………………… |
| Subcontractor: (Clause 1.1) |  | ……………………………………………………… |
| Subcontractor's Representative: (Clause 1.1) |  | ……………………………………………………… |
| Table of Variation Rates and Prices: (Clause 1.1) |  | ……………………………………………………… |
| WOL Objectives (specific additional): (Clause 1.1) |  | ……………………………………………………… |
| WOL Plan: (Clause 1.1) |  | ……………………………………………………… |
| Work Health and Safety Plan: (Clause 1.1) |  | Matters required to be covered in a Work Health and Safety Management Plan by the WHS Legislation, including: the names, positions and responsibilities of all persons at the workplace whose positions or roles involve specific health and safety responsibilities in connection with the Subcontractor's Activities; the arrangements in place, or to be implemented, between any persons conducting a business or undertaking at the workplace where the Subcontractor's Activities are being undertaken, for consultation, cooperation and coordination of activities in relation to compliance with their duties under the WHS Legislation; the arrangements in place, or to be implemented, for managing any work health and safety incidents that occur, including incident reporting procedures, corrective action procedures, record-keeping and reporting requirements (including project-specific and general reporting and reporting to the Contractor's Representative with respect to work health and safety matters), project-specific emergency plans and first aid procedures; any site-specific health and safety rules, and the arrangements for ensuring that all persons at the workplace are informed of these rules; the arrangements for the collection and recording, and any assessment, monitoring and review of safe work method statements at the workplace; and ensuring that work health and safety is a compulsory agenda item at all meetings in accordance with clause 3.9 of the Conditions of Subcontract and ensuring that the outcomes of those agenda items are communicated to the Contractor's Representative. |
|  |  | If design forms part of the Subcontractor's Activities, proposed design risk assessments, purchasing policies for plant, materials and substances, the process for meeting Statutory Requirements regarding design and the process for addressing design changes relevant to work health and safety considerations. |
|  |  | Management of work health and safety generally, including any work health and safety policy, details of any work health and safety management system (including certification, inspection and audit programs), training and induction programs (including work health and safety generally, emergency procedures and use of emergency equipment), the process of communication, information-sharing and provision of assurances to the Contractor's Representative under clause 8.17 of the Conditions of Subcontract, and dispute resolution on work health and safety matters. |
|  |  | Provision of assurances to the Contractor's Representative regarding compliance with any relevant or applicable requirements or standards (or codes of practice) in accordance with clause 9.1 of the Conditions of Subcontract relating to work health and safety management plans. |
|  |  | Management of subcontractors, including induction, training, development of safe work method statements, job safety assessments or equivalent documentation, the obligation to consult, cooperate and coordinate activities, the process of communication, information-sharing and provision of assurances under clause 8.17 of the Conditions of Subcontract and the process for ensuring subcontractor compliance with the Work Health and Safety Plan. |
|  |  | 6. Management of project hazards and risks generally, including work involving: fall hazards; telecommunications towers; demolition; disturbance or removal of asbestos; structural alterations requiring temporary supports; confined spaces; excavation deeper than 1.5 metres; tunnels; use of explosives; pressurised gas distribution mains and consumer piping; chemical, fuel or refrigerant lines; electrical work, including involving energised electrical installations and services; hazardous atmospheres; tilt-up and precast concrete; roadways or railways used by road or rail traffic; movement of powered mobile plant; artificial extremes of temperature; water or other liquids where there is a risk of drowning; diving; remote or isolated work; above-standard exposure to noise; other hazardous manual tasks; exposure to falling objects; abrasive blasting; and hazardous chemicals. |
| Governing law: (Clause 1.3(a)) |  | Australian Capital Territory |
| CLAUSE 2 - COMMENCEMENT |  |  |
| Date for commencement on Site: (Clauses 2.2(b) and 2.3(a)(ii)) |  | ……………………………………………………… |
| Other conditions precedent to Site access: (Clause 2.3(a)(i)C) |  | ……………………………………………………… |
| CLAUSE 3 - PERSONNEL |  |  |
| Contractor's Representative's representatives and their functions: (Clause 3.4) |  | Representative Functions(s) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |
| Subcontractor's key people: (Clause 3.6(a)) |  | Person Position . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |
| CLAUSE 4 - SECURITY |  |  |
| Security to be provided by the Subcontractor: (Clause 4.1) |  | $.................... or......... % of the Subcontract Price (in the form of two Approved Securities, each for 50% of this amount). |
| CLAUSE 5 - RISKS AND INSURANCE |  |  |
| Insurance policies required to be effected by the Contractor: (Clause 5.4(a)(i)) |  | Public Liability Insurance Amount of Cover: $……..…………. in respect of any one occurrence and $……..…………. in the aggregate, all occurrences during the period of insurance. Other Insurances: ……………………………………………………………. |
| Insurance policies required to be effected by the Subcontractor: (Clause 5.5(a)) |  | Public Liability Insurance Amount of Cover: $……..…………. in respect of any one occurrence and $……..…………. in the aggregate, all occurrences during the period of insurance. Workers Compensation Insurance Amount of Cover: The minimum amount required by statute in each State and Territory in which the Subcontractor's Activities are to be performed or the Subcontractor's employees are employed or normally reside. Professional Indemnity Insurance Amount of Cover: $……. per claim and $…… in the aggregate, all claims during the period of insurance. Other Insurances (Clause 5.5(a)(iv)): ……………………………………………………………. |
| Minimum amount of subsubcontractors' Professional Indemnity Insurance: (Clause 5.5(f)) |  | Professional Indemnity Insurance Amount of Cover: $……. per claim and $…… in the aggregate, all claims during the period of insurance. |
| Period for maintenance of Professional Indemnity Insurance: (Clause 5.7(c)) |  | 11 years. |
| CLAUSE 6 - DESIGN AND DOCUMENTATION |
| Documents and number of copies to be provided by the Contractor to the Subcontractor: (Clause 6.1) |  | Document Copies ............................... ........................ ............................... ......................... |
| Number of days for review: (Clause 6.3(a)(ii) and 6.3(c)) |  | ……………………………………………………… |
| Number of copies of Design Documentation to be submitted by the Subcontractor to the Contractor's Representative: (Clause 6.5) |  | ……………………………………………………… |
| Design Documentation hard copy requirements: (Clause 6.5(a)) |  | Compatible with Autocad 14 To scale Printed in black ink on white or transparent ISO Standard Sheet (size A1, A3, A4 or as determined by the Contractor's Representative) |
| Design Documentation electronic copy requirements: (Clause 6.5(b)) |  | Compatible with Autocad 14 CD-ROM or as determined by the Contractor's Representative |
| Order of precedence of Subcontract documents in the case of any ambiguity, discrepancy or inconsistency: (Clause 6.11(a)) |  | 1. Formal Agreement 2. Special Conditions 3. Conditions of Subcontract 4. Subcontract Particulars 5. Subcontract Works Description 6. Any other documents forming part of the Subcontract (as set out in the relevant item under clause 1.1 in these Subcontract Particulars) 7. Design Documentation which the Subcontractor is entitled to use under clause 6.3(c). |
| Period for sample review: (Clauses 6.14(b)(ii) and 6.14(d)) |  | ……………………………………………………… |
| CLAUSE 7 - SITE |  |  |
| Applicability of latent conditions clauses: (Clauses 7.3 and 7.4) |  | Clauses 7.3 and 7.4 [do/do not] apply. (Clauses 7.3 and 7.4 apply unless otherwise stated) |
| CLAUSE 8 - CONSTRUCTION |  |  |
| Existing Approvals and other Approvals which the Contractor and the Territory are to obtain: (Clauses 8.3 and clause 8.3(b)(i)) |  | ……………………………………………………… |
| Statutory Requirements with which the Subcontractor does not need to comply: (Clause 8.3(a)) |  | ……………………………………………………… |
| Work which requires approval to subcontract or which must be let to one of the named subsubcontractors: (Clause 8.5(a)) |  | Work or Goods Subsubcontractors ................................. ........................................... ................................. ........................................... |
| Stages for which Collateral Warranties are required: (Clause 8.6) |  | ……………………………………………………… |
| Collateral Warranties required to be procured by the Subcontractor from subsubcontractors and provided to the Contractor: (Clause 8.6) |  | ……………………………………………………… |
| Amount allowed for each item of Provisional Sum Work (Clauses 8.7(a), 8.10(a) and 8.11(a)) |  | Item Amount allowed ........................... $........................... ........................... $........................... ........................... $........................... |
| Option for responsibility for preparation of design for Provisional Sum Work: (Clause 8.8) |  | [Option 1/Option 2] applies. (Option 1 applies unless otherwise stated) |
| Subcontractor to invite tenders for Provisional Sum Work from the following tenderers: (Clause 8.9(a)(i)) |  | Work Tenderers ........................... ........................... |
| Form of subsubcontract approved for Provisional Sum Work: (Clause 8.9(a)(ii)) |  | ……………………………………………………… |
| Percentage excess entitling additional profit and attendance: (Clause 8.12) |  | ……………………………………………………… (20% unless otherwise stated) |
| Percentage for additional profit and attendance for Provisional Sum Work exceeding provisional sum allowance by stated percentage: (Clause 8.12) |  | ……………………………………………………… |
| Stages for which a certificate signed by a surveyor is required as condition precedent to Completion: (Clause 8.15) |  | ……………………………………………………… |
| Access hours for Subcontractor's Activities on Site: (Clause 8.24) |  | ……………………………………………………… |
| Imported Items: (Clause 8.25) |  | Clause 8.25 [does/does not] apply. (Clause 8.25 does not apply unless otherwise stated) |
| Number of project signboards: (Clause 8.27(a)) |  |  |
| Project signboard dimensions: (Clause 8.27(a)(i)) |  | ……………………………………………………… |
| Project signboard information (additional): (Clause 8.27(a)(ii)I) |  | ……………………………………………………… |
| CLAUSE 9 – QUALITY |  |  |
| Reference development for purpose of determining minimum standards for workmanship and materials: (Clause 9.1) |  | ……………………………………………………… |
| Number of days for submission of Project Plans: (Clause 9.2(a)(ii)A) |  | Site Management Plan: | ……………………………… |
|  |  | Environmental Management Plan: | ……………………………… |
|  |  | Work Health and Safety Plan: | ……………………………… |
|  |  | Commissioning and Handover Plan: | ……………………………… |
|  |  | Other [SPECIFY]: | ……………………………… |
| Period by which Defects Liability Period will be extended following rectification of a Defect or Completion of a Variation to overcome a Defect: (Clause 9.11) |  | ……………………………………………………… |
| Maintenance required from Subcontractor during Defects Liability Period: (Clause 9.14) |  | Planned: Unplanned: |
| Defects Liability Period Review and Report (additional): (Clause 9.15) |  | ……………………………………………………… |
| CLAUSE 10 - TIME |  |  |
| Maximum intervals between program updates by Subcontractor: (Clause 10.2(b)(ii)) |  | ……………………………………………………… |
| Program format to be compatible with: (Clause 10.2(e)) |  | [Primavera Suretrak/Microsoft Project] or approved equivalent |
| Additional causes of delay entitling Subcontractor to claim an extension of time: (Clauses 10.5(a) and 10.7(c)(i)) |  | Statewide industrial disputation or other industrial disputation caused by the Territory, which in neither case is caused or contributed to by the Subcontractor or any subsubcontractor of the Subcontractor A change in a Statutory Requirement after the Award Date Contractor Risks If clauses 7.3-7.4 apply, Latent Conditions |
| Agreed damages: (Clause 10.11) |  | Clause 10.11 does/does not apply. (Clause 10.11 applies unless otherwise stated) If clause 10.11 applies: Where there are no Stages, the Agreed Damages for the Subcontract Works are: $.........................per working day If there are Stages, the Agreed Damages for each Stage are: Stage Agreed Damages ................. $.......... per working day ................. $.......... per working day ................. $.......... per working day ................. $.......... per working day ................. $.......... per working day |
| Percentage of extra costs reasonably incurred due to acceleration: (Clause 10.15(b)(ii)) |  | .....................% (5% unless otherwise stated) |
| CLAUSE 11 - VARIATIONS |  |  |
| Percentage adjustments for valuing a Variation: (Clauses 11.3(b)(i), 11.3(c)(iii) and 11.6(f)) |  | .....% of amount determined for off-site overheads and profit .....% of amount determined for non-time related on-site overheads and preliminaries |
| Percentage of wages: (Clause 11.6(b)) |  | .....% |
| CLAUSE 12 – PAYMENT |  |  |
| Times for submission of payment claims by the Subcontractor to Contractor's Representative: (Clause 12.2) |  | Monthly on the ............ day of each month OR on Completion of the following milestones: ……………………………………………………… |
| Number of business days for payment: (Clause 12.5) |  | ……………………………………………………… |
| Interest rate: (Clause 12.13) |  | 1. In the case of damages - the Australian Taxation Office-sourced General Interest Charge Rate current at the due date for payment or such other rate nominated in writing from time to time by the Contractor's Representative; or 2. In the case of late payments - the greater of: (a) the rate in (1); and (b) the rate of interest prescribed under any applicable Security of Payment Legislation. |
| Limits of accuracy for quantities in Schedule of Rates: (Clause 12.19(c)) |  | Upper Limit: .................………………………………….. (115% unless otherwise stated) Lower Limit: ……………………………………………… (85% unless otherwise stated) |
| Appointed Adjudicator/Prescribed Appointer/Authorised Nominating Authority: (Clause 12.20(d)) |  | The Chair of the Institute of Arbitrators and Mediators Australia of the Chapter in the Australian Capital Territory. |
| Facilities and infrastructure accounting (additional): (Clause 12.23(b)) |  | ……………………………………………………… |
| CLAUSE 13 – COMPLETION |  |  |
| Liquidated damages payable by Subcontractor when Date of Completion occurs after Date for Completion: (Clause 13.7) |  | If there are no Stages, for the Subcontract Works is: $ . . . . . . . per day. If there are Stages, for each Stage is: Stage Liquidated Damages . . . . . . $. . . . . . . . . per day . . . . . . $. . . . . . . . . per day |
| Incentive for early Completion: (Clause 13.9) |  | Clause 13.9 does/does not apply (Clause 13.9 does not apply unless otherwise stated) If there are no Stages, for the Subcontract Works is: $ ......................... per day If there are Stages, for each Stage is: Stage Incentive . . . . . . . . . . . . . . . per day . . . . . . . . . . . . . . . per day |
| CLAUSE 14 - TERMINATION |  |  |
| Number of days to remedy breach: (Clauses 14.3(c) and 14.4(b)) |  | ……………………………………………………… |
| CLAUSE 15 - DISPUTES |  |  |
| Directions to be subject of an expert determination if disputed: (Clause 15.2) |  | Directions under clauses 2.4(b), 4.2(b), 7.3(a), 7.4(b), 8.4(e), 8.22, 9.5, 9.9(b)(i), 9.10, 10.8, 10.9, 10.12(b)(ii)A.1), 11.3(b), 11.3(c)(ii), 11.3(d), 11.6, 12.4, 12.19(e)(ii), 13.2(b)(ii), 14.8(a) |
| Industry expert who will conduct expert determinations: (Clause 15.3(a)(i)) |  | ……………………………………………………… |
| Nominating authority for expert: (Clause 15.3(a)(ii)) |  | ……………………………………………………… (The President for the time being of The Institute of Arbitrators and Mediators Australia unless otherwise stated) |
| CLAUSE 16 - NOTICES |  |  |
| Address and fax number, for the giving or serving of notices, upon: (Clause 16.7(b)(i)) |  | Contractor: ……………………………………………………………………………………………………………………………………………………………………………………………… Contractor's Representative: ……………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………… Subcontractor: ………………………………………………………………………………………………………………………………………………………………………………………………………………………………............................................... |
| – |  |  |
| CLAUSE 20 - COMMERCIAL-IN-CONFIDENCE INFORMATION |  |  |
| Commercial-in-Confidence Information: (Clause 20.2) | Clause 20.2 [does/does not] apply. (Clause 20.2 does not apply unless otherwise stated) |
| Information which is Commercial-in-Confidence Information: (Clause 20.2) | Specific Information | Justification | Period of Confidentiality |
|  | …………………. | …………………. | ………………… |
| ANNEXURE 1 - COMPLETION |  |
| Number of copies of Final Operation and Maintenance Manuals: (Clause 3(e)) | ………………………………………………………..... |
| Content of manuals (additional): (Clause 3(h)(xii)) | ………………………………………………………..... |
| Number of persons to be trained: (Clause 4(a)) | ………………………………………………………..... |
| Categories of persons to be trained: (Clause 4(a)) | ………………………………………………………..... |

ANNEXURE 1 - COMPLETION

Item 1.	"As-Constructed" Drawings and Documents

Without limiting the definition of "Completion" in clause 1.1 of the Conditions of Subcontract, the Subcontractor must, as a condition precedent to Completion of the Subcontract Works or a Stage:

    - provide to the Contractor's Representative the number of complete sets of the drawings and documents as follows:

| Description | Hard copy format | No of hard copies | Electronic copy format | No of electronic copies |
| --- | --- | --- | --- | --- |
| Wiring diagrams |  |  |  |  |
| Functional diagrams |  |  |  |  |
| "As-Constructed" drawings |  |  |  |  |
| "As-Constructed" lighting and power layout |  |  |  |  |
| "As-Constructed" main switchboard layout |  |  |  |  |
| "As-Constructed" main switchboard schematic drawings |  |  |  |  |
| "As-Constructed" main switchboard circuit index |  |  |  |  |
| "As-Constructed" fire detector layout |  |  |  |  |
| Wiring diagram for the fire alarm control panel |  |  |  |  |
| "As-Constructed" underground cabling layout |  |  |  |  |
| "As-Constructed" distribution board layout |  |  |  |  |
| "As-Constructed" distribution board circuit index |  |  |  |  |
| "As-Constructed" sub mains cabling layout |  |  |  |  |
| "As-Constructed" Site survey |  |  |  |  |
| [INSERT OTHER "AS-CONSTRUCTED" DOCUMENTS REQUIRED. THE ABOVE LIST IS BY WAY OF EXAMPLE ONLY.] |  |  |  |  |

without limiting paragraph (a), ensure that the "As-Constructed" drawings and documents:

are prepared in accordance with the requirements of the Subcontract; and

have the words "As-Constructed" printed in the following locations:

if a document, immediately above the title and reference; and

if a drawing, immediately above the title and drawing number block at the bottom right hand corner of the drawing and immediately to the left of the drawing number block at the top left hand corner of the drawing, parallel to and outside the left hand border of the drawing; and

provide to the Contractor's Representative a comprehensive document and drawing index setting out all documents and drawings prepared by the Subcontractor and by its subsubcontractors.

Item 2.	Warranties

    - Without limiting the definition of "Completion" in clauses 1.1, 8.5(e), 8.6  and 9.1 of the Conditions of Subcontract, the Subcontractor must, as a condition precedent to Completion of the Subcontract Works or a Stage, provide the Contractor's Representative with the following minimum warranties (in the form of the Collateral Warranty) for the following warranty periods:

| Description | Warranty Period |
| --- | --- |
| Mechanical Services | [INSERT] |
| Electrical Services | [INSERT] |
| Fire Services | [INSERT] |
| Security | [INSERT] |
| Plumbing | [INSERT] |
| Drainage | [INSERT] |
| Hardware | [INSERT] |
| Tiling | [INSERT] |
| Painting | [INSERT] |
| Carpet | [INSERT] |
| Access Floor | [INSERT] |
| Lifts | [INSERT] |
| Benches & Cupboards | [INSERT] |
| Windows & Glazing | [INSERT] |
| Metal Roof & Walling | INSERT] |
| Membrane Roofing & Tanking | [INSERT] |
| External Coating Systems | [INSERT] |
| Sun Control Louvres | [INSERT] |
| Toilet Partitions | [INSERT] |
| Partitions | [INSERT] |
| Resilient finishes, e.g. Vinyl | [INSERT] |
| Suspended Ceilings | [INSERT] |
| Doors | [INSERT] |
| Internal Signage | [INSERT] |
| External Signage (signwriting and lettering) | [INSERT] |
| External Signage (excluding signwriting and lettering) | [INSERT] |
| Façade | [INSERT] |
| [INSERT OTHER WARRANTIES. THE WARRANTIES REFERRED TO ABOVE ARE EXAMPLES ONLY] | [INSERT] |

Item 3.	Operation and Maintenance Manuals

Without limiting the definition of "Completion" in clause 1.1 of the Conditions of Subcontract, the Subcontractor must, as a condition precedent to Completion of the Subcontract Works or a Stage:

    - compile specific operation and maintenance manuals for each aspect of the Subcontract Works or the Stage, including obtaining and coordinating information provided by the Subcontractor and its subsubcontractors;

prior to the commencement of commissioning of the Subcontract Works or the Stage, provide one copy of draft operation and maintenance manuals in respect of each aspect of the Subcontract Works or the Stage (Draft Operation and Maintenance Manuals) to the Contractor's Representative for approval;

within 14 days of the completion of the commissioning of the Subcontract Works or the Stage, provide one copy of all operation and maintenance manuals in respect of the Subcontract Works or the Stage which have been amended during commissioning (Draft Amended Operation and Maintenance Manuals) (such amendments being clearly indicated in each Draft Amended Operation and Maintenance Manual) to the Contractor's Representative for approval;

resubmit the Draft Operation and Maintenance Manuals and the Draft Amended Operation and Maintenance Manuals to the Contractor's Representative as necessary; and

once approved by the Contractor's Representative, submit the number of copies of the final, approved versions of the Draft Operation and Maintenance Manuals and the Draft Amended Operation and Maintenance Manuals (Final Operation and Maintenance Manuals) set out in the Subcontract Particulars to the Contractor's Representative.

For the purposes of this Item 3:

catalogues, sales brochures and other documents giving general information in respect of aspects of the Subcontract Works or the Stage will not be acceptable;

all manuals must be sufficiently comprehensive for routine maintenance, overhaul and repairs to be carried out by personnel who are qualified to undertake maintenance work but who are not necessarily familiar with any particular aspect of the Subcontract Works or the Stage; and

without limiting the generality of this Item 3, the manuals must be securely bound in 2 ring binders and include:

a comprehensive list of contents including illustrations and drawings;

function, application, specification and comprehensive technical data of all equipment including sub-assemblies, proprietary items, and system circuit and schematic diagrams where applicable;

a description of the equipment and its principles of operation;

routine maintenance and lubrication schedules;

dismantling and re-assembly procedures;

trouble-shooting suggestions;

a complete lists of parts;

a list of spare parts recommended to be held in stock;

the procedure for ordering spare parts;

clear and comprehensive illustrations and/or drawings with parts readily identifiable;

text which is clearly printed on good quality A4 size matt paper, not less than 95 gsm;

the matters specified in the Subcontract Particulars; and

any other matter required by the Contractor's Representative.

Item 4.	Training

Without limiting the definition of "Completion" in clause 1.1 of the Conditions of Subcontract, the Subcontractor must, as a condition precedent to Completion of the Subcontract Works or a Stage:

    - during commissioning of the Subcontract Works or the Stage, plan, manage and deliver a comprehensive training program in respect of all operational and maintenance aspects of the Subcontract Works or the Stage for the number of and each category of persons set out in the Subcontract Particulars; and

carry out such training using:

trained instructors, fully experienced in respect of all operational and maintenance aspects of the Subcontract Works or the Stage; and

the Final Operation and Maintenance Manuals produced by the Subcontractor, with copies of such manuals to be made available during the training to all trainees.

ANNEXURE 2  - Ethical suppliers declaration

STATUTORY DECLARATION

Statutory Declarations Act 1959 (Cth)

I, [Name, address and occupation of person making declaration] make the following declaration under the Statutory Declarations Act 1959 (Cth),

            - In this declaration a reference to:

- “Subcontract” means an agreement which has or will shortly be entered into between the Contractor and the Subcontractor for the provision of works in respect of the Project.

- “Contractor” means [insert full legal name of Contractor including the ACN/ABN as per that identified on the Subcontract];

- “Subcontractor” means [insert full legal name of Subcontractor including the ACN/ABN as per that identified on the Subcontract];

- “Project” means Project No [insert ACT Government Project no] for [insert sufficient details to identify nature of project];

- the words or terms “Adverse Ruling”, “Employee”, “Employee and Industrial Relations Obligations’, “Industrial Instruments”, “IRE Certificate”, “Prescribed Legislation”, and “Prescribed Works or Services” have the same meaning as defined in the Subcontract; and

- all other capitalised words or terms have the same meaning as defined in the Subcontract.

            - I am authorised on behalf of the Subcontractor to make this declaration.

            - All Employees of the Subcontractor who have at any time been employed by the Subcontractor in respect of the Project have, at the date of this declaration, been paid all moneys due and payable to them in respect of their employment on the work under the Subcontract.

            - The Subcontractor has, at the date of this declaration paid all amounts it is required to pay to third parties on behalf of Employees as required by Prescribed Legislation.

            - All subsubcontractors have been paid all moneys due and payable to them in respect of work under the Subcontract.

            - The Subcontractor holds a current IRE Certificate.

            - The Subcontractor has in the preceding 24 months of the date of this declaration complied with all Prescribed Legislation

□  True	(delete 7A and initial)		□  Not true	(answer 7A)

7A.	The Subcontractor has not complied with the following Prescribed Legislation.

[Insert Full Details of the failure to comply with Prescribed Legislation]

            - The Subcontractor has in the preceding 24 months of the date of this declaration recognised the rights of its Employees to union membership and representation.

□  True	(delete 8A and initial)		□  Not true	(answer 8A)

8A.	The Subcontractor has not recognised the rights of Employees to union membership and representation in the following respects.

[Insert Full Details of how the Subcontractor has not recognised the rights of Employees to union membership and representation]

            - The Subcontractor has in the preceding 24 months of the date of this declaration complied with all amendments to wages and conditions of employment for their Employees as decided by any authorised industrial or wage-setting agency.

□  True	(delete 9A and initial)		□  Not true	(answer 9A)

9A.	The Subcontractor has not complied with all amendments to wages and conditions of employment for their Employees as decided by any authorised industrial or wage-setting agency in the following respects:

[Insert Full Details of how the Subcontractor has failed to comply with all amendments to wages and conditions of employment]

            - In the preceding 24 months of the date of this declaration there have been no findings against the Subcontractor by a court, tribunal, commission, board or other entity with jurisdiction of a breach of any Prescribed Legislation, including a finding of a breach in a non-confidential consent order.

□  True	(delete 10A and initial)		□  Not true	(answer 10A)

10A.	There have been the following findings (Full Details of which are provided) against the Subcontractor by a court, tribunal, commission, board or other entity with jurisdiction of a breach of any Prescribed Legislation:

[Set out Full Details of findings]

            - In the preceding 24 months of the date of this declaration there have been no convictions under the Prescribed Legislation against the Subcontractor.

□  True	(delete 11A and initial)		□  Not true	(answer 11A)

11A.	There have been the following convictions under the Prescribed Legislation against the Subcontractor:

[Set out Full Details of convictions]

12.	There are currently no proceedings or prosecutions against the Subcontractor in respect of a breach of any Prescribed Legislation.

□  True	(delete 12A and initial)		□  Not true	(answer 12A)

12A.	There are currently the following proceedings or prosecutions against the Subcontractor in respect of a breach of Prescribed Legislation.

[Set out Full Details of proceedings or prosecutions]

13.	The Subcontractor has not been required to implement any remedial measures to ensure future compliance with the Prescribed Legislation.

□  True	(delete 13A and initial)		□  Not true	(answer 13A)

13A.	The Subcontractor has been required to implement the following remedial measures to ensure future compliance with the Prescribed Legislation:

[Set out Full Details of the remedial measures implemented]

I understand that a person who intentionally makes a false statement in a statutory declaration is guilty of an offence under section 11 of the Statutory Declarations Act 1959, and I believe that the statements in this declaration are true in every particular.

___________________________________

[Signature of person making the declaration]

____________________________________

[Print name of person making the declaration]

Declared at  [place]  on   [day]  of  [month]  [year]

Before me:

____________________________________

[Signature of person before whom the declaration is made]

____________________________________

[Full name, qualification and address of person before whom the declaration is made (in printed letters)]

Note 1	A person who intentionally makes a false statement in a statutory declaration is guilty of an offence, the punishment for which is imprisonment for a term of 4 years – see section 11 of the Statutory Declarations Act 1959.

Note 2	Chapter 2 of the Criminal Code applies to all offences against the Statutory Declarations Act 1959 – see section 5A of the Statutory Declarations Act 1959.

A statutory declaration under the Statutory Declarations Act 1959 may be made before–

(1)	A person who is currently licensed or registered under a law to practise in one of the following occupations:

Chiropractor	Dentist	Legal practitioner

Medical practitioner	Nurse	Optometrist

Patent attorney	Pharmacist	Physiotherapist

Psychologist	Trade marks attorney	Veterinary surgeon

(2)	A person who is enrolled on the roll of the Supreme Court of a State or Territory, or the High Court of Australia, as a legal practitioner (however described); or

(3)	A person who is in the following list:

Agent of the Australian Postal Corporation who is in charge of an office supplying postal services to the public

Australian Consular Officer or Australian Diplomatic Officer (within the meaning of the Consular Fees Act 1955)

Bailiff

Bank officer with 5 or more continuous years of service

Building society officer with 5 or more years of continuous service

Chief executive officer of a Commonwealth court

Clerk of a court

Commissioner for Affidavits

Commissioner for Declarations

Credit union officer with 5 or more years of continuous service

Employee of the Australian Trade Commission who is:

(a)	in a country or place outside Australia; and

(b)	authorised under paragraph 3 (d) of the Consular Fees Act 1955; and

(c)	exercising his or her function in that place

Employee of the Commonwealth who is:

(a)	in a country or place outside Australia; and

(b)	authorised under paragraph 3 (c) of the Consular Fees Act 1955; and

(c)	exercising his or her function in that place

Fellow of the National Tax Accountants’ Association

Finance company officer with 5 or more years of continuous service

Holder of a statutory office not specified in another item in this list

Judge of a court

Justice of the Peace

Magistrate

Marriage celebrant registered under Subdivision C of Division 1 of Part IV of the Marriage Act 1961

Master of a court

Member of Chartered Secretaries Australia

Member of Engineers Australia, other than at the grade of student

Member of the Association of Taxation and Management Accountants

Member of the Australasian Institute of Mining and Metallurgy

Member of the Australian Defence Force who is:

(a)	an officer; or

(b)	a non-commissioned officer within the meaning of the Defence Force Discipline Act 1982 with 5 or more years of continuous service; or

(c)	a warrant officer within the meaning of that Act

Member of the Institute of Chartered Accountants in Australia, the Australian Society of Certified Practising Accountants or the National Institute of Accountants

Member of:

(a)	the Parliament of the Commonwealth; or

(b)	the Parliament of a State; or

(c)	a Territory legislature; or

(d)	a local government authority of a State or Territory

Minister of religion registered under Subdivision A of Division 1 of Part IV of the Marriage Act 1961

Notary public

Permanent employee of the Australian Postal Corporation with 5 or more years of continuous service who is employed in an office supplying postal services to the public

Permanent employee of:

(a)	the Commonwealth or a Commonwealth authority; or

(b)	a State or Territory or a State or Territory authority; or

(c)	a local government authority;

with 5 or more years of continuous service who is not specified in another item in this list

Person before whom a statutory declaration may be made under the law of the State or Territory in which the declaration is made

Police officer

Registrar, or Deputy Registrar, of a court

Senior Executive Service employee of:

(a)	the Commonwealth or a Commonwealth authority; or

(b)	a State or Territory or a State or Territory authority

Sheriff

Sheriff’s officer

Teacher employed on a full-time basis at a school or tertiary education institution